## NewCon 2019
REPUBLIC OF THE PHILIPPINES
DEPARTMENT OF EDUCATION
CY 2019 BASIC EDUCATIONAL FACILITIES FUND
CONSTRUCTION OF CLASSROOMS
As of February 25, 2019
Category | Region | Division | School ID | School Name | Municipality | LD | No. of Sites | Recommended Building Type | Total No. of Classrooms | Total Project Cost | Contract Amount (DPWH REPORT) | STATUS | PREVIOUS PERCENTAGE ACCOMPLISHMENT | PERCENTAGE ACCOMPLISHMENT | Difference | Issues and Concerns on the Project Implementation | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Target Date of Completion | Actual Date of Completion | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites Ongoing | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL ongoing | No. of CL Completed
K10 | CAR | Abra | 305095 | Quidaoen NHS | SAN JUAN | 0 | 1 | 2STY4CL | 4 | 11725315.4181 | 11459852.32 | Ongoing | 30% | 30% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | CAR | Apayao | 135321 | Magabta ES | KABUGAO (Capital) | 0 | 1 | 1STY3CL | 3 | 8012580.5176 | 7828543.65 | Ongoing | 0.87% | 15% | 14.13% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | CAR | Baguio City | 305270 | Dona Aurora National High School | BAGUIO CITY | 0 | 1 | 4STY8CL | 8 | 24200650.75 | 23174077.5 | Ongoing | 36% | 36% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | CAR | Ifugao |  | Damag Elementary School (Jacmal Annex) | AGUINALDO | 0 | 1 | 2STY6CL | 6 | 17692436.0281 | 17383633.92 | Ongoing | 5% | 16% | 11% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | CAR | Kalinga | 135992 | Lubuagan Central School | LUBUAGAN | 0 | 1 | 2STY4CL | 4 | 11337595.9265 | 11301120.47 | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | CAR | Kalinga | 135992 | Lubuagan Central School | LUBUAGAN | 0 |  | 2STY6CL | 6 | 15111409.3125 | 14922987.75 | Ongoing | 7% | 7% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | CAR | Mt. Province | 136282 | Amolong Elementary School | PARACELIS | 0 | 1 | 1STY3CL | 3 | 5419234.3 | 5404891.44 | Ongoing | 64% | 80% | 16% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | CAR | Mt. Province | 136267 | Apapawan Elementary School | NATONIN | 0 | 1 | 1STY2CL | 2 | 6265625 | 6100000 | Ongoing | 57% | 57% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | CAR | Mt. Province | 136289 | Butigue Elementary School | PARACELIS | 0 | 1 | 3STY12CL | 12 | 32230375 | 32149500 | Ongoing | 37% | 40% | 3% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
SHS | CAR | Mt. Province | 305261 | Paracelis National High School | PARACELIS | 0 | 1 | 4STY12CL | 12 | 35990162.0275 | 35361310.45 | Ongoing | 39% | 45% | 6% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
K10 | CAR | Tabuk City | 220531 | Bulanao East Annex - Greenhills PS | CITY OF TABUK (Capital) | 0 | 1 | 3STY6CL (MODIFIED) | 6 | 20861894.7151 | 20579685.91 | Ongoing | 2% | 20% | 18% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
SHS | CARAGA | Agusan del Norte | 304679 | Bokbokon NHS (Durian NHS Annex) | LAS NIEVES | 1 | 1 | 1STY2CL | 2 | 4803882.3164 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | CARAGA | Agusan del Norte | 211511 | Calayagon ES | BUENAVISTA | 2 | 1 | 1-UNIT 1STY2CL with Toilet Attached and Handwashing Facility | 2 | 3190116.7935 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | CARAGA | Agusan del Norte | 131494 | Cubi-Cubi ES | NASIPIT | 2 | 1 | 1STY3CL with Attached Toilet & Handwashing Facility | 3 | 3965955.5033 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | CARAGA | Agusan del Norte | 131587 | Lawigan ES | TUBAY | 2 | 1 | 1STY3CL with Attached Toilet & Handwashing Facility | 3 | 6254112.7712 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | CARAGA | Agusan del Norte | 317320 | Pupotsan NHS (Magallanes NHS Annex) | MAGALLANES | 2 | 1 | 1-UNIT 1STY3CL with Toilet Attached and Handwashing Facility | 3 | 4488870.8817 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | CARAGA | Agusan del Norte | 317320 | Pupotsan NHS (Magallanes NHS Annex) | MAGALLANES | 2 |  | 3UNITS 1STY2CL | 6 | 11389844.8632 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
SHS | CARAGA | Agusan del Sur | 304710 | Del Monte NHS | TALACOGON | 1 | 1 | 2STY4CL | 4 | 13674100 |  | Ongoing | 25% | 40% | 15% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | CARAGA | Agusan del Sur | 131703 | Guadalupe CES | ESPERANZA | 1 | 1 | 1STY2CL (w/ toilet at each classroom) | 2 | 5619012.5 |  | Ongoing | 25% | 40% | 15% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | CARAGA | Agusan del Sur | 131788 | San Vicente ES | PROSPERIDAD (Capital) | 1 | 1 | 2STY10CL | 10 | 27323137.5 |  | Ongoing | 25% | 40% | 15% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0
K10 | CARAGA | Agusan del Sur | 131714 | Tandang Sora Elementary School | Esperanza | 1 | 1 | 2STY6CL | 6 | 20526187.5 |  | Ongoing | 25% | 40% | 15% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
SHS | CARAGA | Agusan del Sur | 317426 | Buenasuerte National High School | SAN FRANCISCO | 2 | 1 | 1STY4CL W/ TOILET | 4 | 9546086.4619 |  | Ongoing | 25% | 40% | 15% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | CARAGA | Agusan del Sur | 132009 | Quimayong ES | TRENTO | 2 | 1 | 1STY3CL W/ TOILET | 3 | 6937294.5163 |  | Ongoing | 25% | 40% | 15% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | CARAGA | Bayugan City | 131609 | Panaytay ES | CITY OF BAYUGAN | 1 | 1 | 1STY2CL (w/ toilet at each classroom) | 2 | 5603975 |  | Ongoing | 45% | 45% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | CARAGA | Bislig City | 132635 | San Roque Central Elementary School | CITY OF BISLIG | 2 | 1 | 1STY2CL (with Toilet Attached) | 2 | 4991723.1675 |  | Ongoing | 21% | 21% | 0% |  | 19NI0061 | 19NI0061 | August 1, 2019 | August 8, 2019 | August 20, 2019 | August 27, 2019 | August 30, 2019 | LM Construction & General Marketing | 2019-12-26 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
SHS | CARAGA | Cabadbaran City | 330101 | Puting Bato National High School | CITY OF CABADBARAN | 2 | 1 | 2UNITS 2STY4CL | 8 | 20877643.1079 |  | Ongoing | 0% | 50% | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
SHS | CARAGA | Cabadbaran City | 330101 | Puting Bato National High School | CITY OF CABADBARAN | 2 | 1 | 1STY6CL | 6 | 8428891.3993 |  | Ongoing | 0% | 60% | 60% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | CARAGA | Dinagat Island | 132399 | Magsaysay ES | DINAGAT | 0 | 1 | 1STY3CL | 3 | 5213000 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | CARAGA | Dinagat Island | 132370 | Sta Rita ES | CAGDIANAO | 0 | 1 | 1STY2CL | 2 | 3909750 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | CARAGA | Surigao City | 132272 | Surigao City Pilot Sch. | SURIGAO CITY (Capital) | 2 | 1 | 4STY16CL | 16 | 46402225.1422 |  | Ongoing | 18% | 18% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
K10 | CARAGA | Surigao City | 132243 | Vicente Cabilao Mem. ES (Balibayon ES) | SURIGAO CITY (Capital) | 2 | 1 | 1STY2CL | 2 | 4874764.1691 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | CARAGA | Surigao del Norte | 132331 | Anao-aon CES | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 2STY6CL | 6 | 16998458.5409 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | CARAGA | Surigao del Norte | 132378 | Claver Central Elementary School | CLAVER | 2 | 1 | 3STY12CL | 12 | 43451263.9166 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
K10 | CARAGA | Surigao del Sur | 132858 | Britania Elementary School | SAN AGUSTIN | 1 | 1 | 1STY2CL (Grade 1-10 CL) | 2 | 4117215.4101 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
SHS | CARAGA | Surigao del Sur | 317906 | Cresencio S. Lago National High School | MARIHATAG | 1 | 1 | 1STY2CL | 2 | 4117215.4101 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
SHS | CARAGA | Surigao del Sur | 304898 | Marihatag National Agricultural High School | MARIHATAG | 1 | 1 | 1STY2CL | 2 | 4117215.4101 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | CARAGA | Surigao del Sur | 214516 | Mahogany Elementary School | LINGIG | 2 | 1 | 2STY4CL | 4 | 13873357.9727 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | CARAGA | Surigao del Sur | 214518 | Pinanapatan Elementary School | LINGIG | 2 | 1 | 1STY2CL (with Toilet Attached) | 2 | 5670381.2015 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | CARAGA | Tandag City | 132968 | Meliton M. Ajos Memorial Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 1STY2CL (Grade 1-10 CL) | 2 | 4117215.4101 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | NCR | Caloocan City | 305373 | Sampaguita HS | Caloocan City | 1 | 1 | 4STY8CL | 8 | 24060000 |  | Under Procurement | 0% | 0% | 0% | Awaiting on the Approved Authority to Demolished to be issued by the LGU | [10 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | NCR | Caloocan City | 305386 | Deparo High School | Caloocan City | 1 | 1 | 4STY8CL | 8 | 24060000 |  | Under Procurement | 0% | 0% | 0% | exiting bldg - for demolition | [10 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | NCR | Caloocan City | 136633 | Camarin D ES | Caloocan City | 1 | 1 | 4STY8CL | 8 | 24060000 |  | Under Procurement | 0% | 0% | 0% | Awaiting on the Approved Authority to Demolished to be issued by the LGU | [10 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | NCR | Caloocan City | 136633 | Camarin D ES | Caloocan City | 1 |  | 4STY8CL | 8 | 24060000 |  | Under Procurement | 0% | 0% | 0% | Awaiting on the Approved Authority to Demolished to be issued by the LGU | [10 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | NCR | Caloocan City | 136639 | Bagong Silang ES | Caloocan City | 1 | 1 | 4STY8CL | 8 | 24060000 |  | Under Procurement | 0% | 0% | 0% | Awaiting on the Approved Authority to Demolished to be issued by the LGU | [10 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | NCR | Caloocan City | 136613 | Maypajo ES | KALOOKAN CITY | 2 | 1 | 4STY12CL | 12 | 47418250 |  | Under Procurement | 0% | 0% | 0% | Awaiting on the Approved Authority to Demolished to be issued by the LGU | [10 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
K10 | NCR | Caloocan City | 136606 | Grace Park ES (Main) | Caloocan City | 2 | 1 | 4STY20CL | 20 | 50947050 |  | Under Procurement | 0% | 0% | 0% | Awaiting on the Approved Authority to Demolished to be issued by the LGU | [10 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
SHS | NCR | Caloocan City | 305388 | Caloocan HS | Caloocan City | 2 | 1 | 4STY8CL | 8 | 24060000 |  | Under Procurement | 0% | 0% | 0% | Awaiting on the Approved Authority to Demolished to be issued by the LGU | [10 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | NCR | Malabon City | 136850 | Tinajeros ES | CITY OF MALABON | 0 | 1 | 4STY8CL | 8 | 30877000 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
SHS | NCR | Malabon City | 305450 | Panghulo NHS | CITY OF MALABON | 0 | 1 | 4STY16CL | 16 | 76671200 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
SHS | NCR | Manila | 500566 | T. Paez Integrated School (Elem.) | CITY OF MANILA | 1 | 1 | 4STY20CL | 20 | 68370500 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
K10 | NCR | Manila | 136437 | Manuel L. Quezon Elementary School | CITY OF MANILA | 1 | 1 | 4STY20CL | 20 | 68370500 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
K10 | NCR | Manila | 136437 | Manuel L. Quezon Elementary School | CITY OF MANILA | 1 |  | 2UNITS 4STY12CL | 24 | 99448000 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0
K10 | NCR | Manila | 136439 | I. Delos Reyes ES | CITY OF MANILA | 1 | 1 | 4STY16CL | 32 | 57443250 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0
K10 | NCR | Manila | 136456 | P. Guevara Elementary School | CITY OF MANILA | 3 | 1 | 4STY12CL | 12 | 42907000 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
K10 | NCR | Manila | 136452 | P. Gomez ES | CITY OF MANILA | 3 | 1 | 4STY12CL | 12 | 52337464.7685 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
SHS | NCR | Manila | 305302 | Jose Abad Santos High School | CITY OF MANILA | 3 | 1 | 4STY16CL | 16 | 83876040.8241 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
K10 | NCR | Manila | 305300 | Cayetano Arellano High School | CITY OF MANILA | 3 | 1 | 4STY12CL | 12 | 66203184.4932 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
K10 | NCR | Manila | 136446 | Andres Bonifacio Elementary School | CITY OF MANILA | 3 | 1 | 4STY12CL | 12 | 54417594.5245 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
K10 | NCR | Manila | 136460 | G. Lopez Jaena Elementary School | CITY OF MANILA | 4 | 1 | 4STY20CL (SPECIAL DESIGN) | 20 | 56541000 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
K10 | NCR | Manila | 136472 | Pio del Pilar Elementary School | CITY OF MANILA | 5 | 1 | 4STY8CL | 8 | 29573750 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | NCR | Manila | 136482 | Bagong Diwa Elementary School | CITY OF MANILA | 6 | 1 | 4STY24CL | 24 | 49724000 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0
K10 | NCR | Manila | 136471 | Bacood Elementary School | CITY OF MANILA | 5 | 1 | 4STY16CL | 16 | 50726500 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
K10 | NCR | Muntinlupa City | 136911 | Buli ES | CITY OF MUNTINLUPA | 0 | 1 | 4STY8CL | 8 | 28070000 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | NCR | Muntinlupa City | 136908 | Alabang ES (Main) | CITY OF MUNTINLUPA | 0 | 1 | 4STY20CL | 20 | 49122500 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
K10 | NCR | Navotas | 136868 | Tangos I Elementary School | CITY OF NAVOTAS | 0 | 1 | 4STY8CL | 8 | 38335600 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | NCR | Navotas | 136864 | San Rafael Vill. Elementary School | CITY OF NAVOTAS | 0 | 1 | 4STY8CL | 8 | 38335600 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | NCR | Quezon City | 136492 | Ramon Magsaysay ES | QUEZON CITY | 1 | 1 | 4STY24CL | 24 | 62756500 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0
K10 | NCR | Quezon City | 136492 | Ramon Magsaysay ES | QUEZON CITY | 1 |  | 4STY20CL | 20 | 54185125 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
K10 | NCR | Quezon City | 136491 | Demetrio Tuazon ES | QUEZON CITY | 1 | 1 | 4STY8CL | 8 | 22516150 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | NCR | Quezon City | 136507 | Bagong Pag-Asa Elementary School | QUEZON CITY | 1 | 1 | 4STY20CL | 20 | 54185125 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
K10 | NCR | Quezon City | 136507 | Bagong Pag-Asa Elementary School | QUEZON CITY | 1 |  | 4STY16CL | 16 | 46611237.5 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
K10 | NCR | Quezon City | 136509 | Project 6 ES | QUEZON CITY | 1 | 1 | 4STY8CL | 8 | 22666525 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | NCR | Quezon City | 136569 | Dona Josefa E. Marcos ES | QUEZON CITY | 3 | 1 | 4STY8CL | 8 | 30375750 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | NCR | Quezon City | 136569 | Dona Josefa E. Marcos ES | QUEZON CITY | 3 |  | 4STY12CL | 12 | 38095000 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
SHS | NCR | Quezon City | 305353 | Krus na Ligas HS | QUEZON CITY | 4 | 1 | 4STY12CL | 12 | 40100000 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
K10 | NCR | Quezon City | 136533 | Kaligayahan ES | QUEZON CITY | 5 | 1 | 4STY8CL | 8 | 24004862.5 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
SHS | NCR | Taguig | 305464 | Tipas National High School | TAGUIG CITY | 1 | 1 | 4STY12CL w/ ROOFDECK | 12 | 56381109.0094 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
SHS | NCR | Valenzuela City | 320407 | Wawangpulo National High School | CITY OF VALENZUELA | 1 | 1 | 4STY8CL | 8 | 16040000 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | NCR | Valenzuela City | 136807 | Pio Valenzuela ES | CITY OF VALENZUELA | 1 | 1 | 4STY12CL | 12 | 48440800 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
SHS | NCR | Valenzuela City | 305440 | Lawang Bato National High School | CITY OF VALENZUELA | 1 | 1 | 4STY20CL | 20 | 51648489.1147 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
SHS | NCR | Valenzuela City | 305440 | Lawang Bato National High School | CITY OF VALENZUELA | 1 |  | 4STY16CL | 16 | 45893588.7322 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
SHS | NCR | Valenzuela City | 305440 | Lawang Bato National High School | CITY OF VALENZUELA | 1 |  | 4STY8CL | 8 | 22502549.9446 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | NCR | Valenzuela City | 320406 | Canumay East National High School | CITY OF VALENZUELA | 1 | 1 | 2UNITS 4STY8CL | 16 | 45120136.644 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
K10 | NCR | Valenzuela City | 136825 | Marulas Central School | CITY OF VALENZUELA | 2 | 1 | 4STY8CL | 8 | 22697871.3705 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
SHS | NCR | Valenzuela City | 305445 | Caruhatan National High School | CITY OF VALENZUELA | 2 | 1 | 4STY20CL | 20 | 47655164.2386 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
K10 | Region I | Batac city | 100079 | Magnuang ES | Batac City | 2 | 1 | 1STY2CL | 2 | 3797075.3659 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region I | Candon City | 100433 | Calaoa-an Elementary School | Candon City | 2 | 1 | 2STY4CL | 4 | 11111557.9107 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Candon City | 1004388 | Felomino G. Gagarin ES | CITY OF CANDON | 2 | 1 | 1STY2CL | 2 | 3755459.4455 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region I | Dagupan City | 102154 | Bacayao Sur ES | DAGUPAN CITY | 4 | 1 | 3STY9CL | 9 | 30578805.7434 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0
SHS | Region I | Dagupan City | 500053 | East Central IS | DAGUPAN CITY | 4 | 1 | 3STY9CL | 9 | 26610436.6411 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0
K10 | Region I | Dagupan City | 102149 | Juan L. Siapno ES | Dagupan City | 4 | 1 | 3STY9CL | 9 | 25472507.7231 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0
K10 | Region I | Dagupan City | 102181 | Juan P. Guadiz ES | DAGUPAN CITY | 4 | 1 | 3STY9CL | 9 | 26651925.5948 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0
K10 | Region I | Dagupan City | 102179 | Salapingao ES | DAGUPAN CITY | 4 | 1 | 3STY9CL | 9 | 26651925.5948 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0
K10 | Region I | Dagupan City | 102152 | West Central ES I | DAGUPAN CITY | 4 | 1 | 3STY9CL | 9 | 26651925.5948 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0
K10 | Region I | Ilocos Norte | 100198 | Dadaeman Elementary School | Pasuquin | 1 | 1 | 1STY2CL | 2 | 3797075.3659 |  | Ongoing | 0% | 0% | 0% | needs buffer fund due to updated DUPA | [10 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region I | Ilocos Norte | 100204 | Nagabungan ES | Pasuquin | 1 | 1 | 1STY2CL | 2 | 3797075.3659 |  | Ongoing | 0% | 0% | 0% | needs buffer fund due to updated DUPA | [10 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
SHS | Region I | Ilocos Norte | 300029 | Sarrat National High School | SARRAT | 1 | 1 | 4STY20CL | 20 | 48270375 |  | Ongoing | 0% | 0% | 0% | needs buffer fund due to updated DUPA | [10 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
K10 | Region I | Ilocos Norte | 100214 | Tabungao PS | Pasuquin | 1 | 1 | 1STY3CL | 3 | 5695613.0538 |  | Ongoing | 0% | 0% | 0% | needs buffer fund due to updated DUPA | [10 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region I | Ilocos Norte | 100185 | Nagbacalan ES | PAOAY | 2 | 1 | 1STY3CL | 3 | 5858371.6957 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
SHS | Region I | Ilocos Sur | 300043 | Cabugao NHS | CABUGAO | 1 | 1 | 2STY4CL | 4 | 9589937.5763 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Ilocos Sur | 100513 | Ambulogan ES | NARVACAN | 2 | 1 | 1STY3CL | 3 | 5073993.8412 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region I | Ilocos Sur | 100514 | Anteng PS | NARVACAN | 2 | 1 | 1STY3CL | 3 | 5073993.8412 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region I | Ilocos Sur | 100702 | Babal-lasioan ES | SANTA MARIA | 2 | 1 | 2STY6CL | 6 | 17866914.0053 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region I | Ilocos Sur | 100516 | Banglayan Elementary School | NARVACAN | 2 | 1 | 2STY4CL | 4 | 10096781.8719 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Ilocos Sur | 100517 | Bulanos ES | NARVACAN | 2 | 1 | 1STY3CL | 3 | 5073993.8412 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region I | Ilocos Sur | 100536 | Cagayungan ES | NARVACAN | 2 | 1 | 1STY3CL | 3 | 5073993.8412 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region I | Ilocos Sur | 100537 | Codoog ES | NARVACAN | 2 | 1 | 1STY3CL | 3 | 5073993.8412 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region I | Ilocos Sur | 100521 | Kakaldingan ES | NARVACAN | 2 | 1 | 1STY3CL | 3 | 5073993.8412 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region I | Ilocos Sur | 100393 | Macaoayan Comm. Sch. | BURGOS | 2 | 1 | 2STY4CL | 4 | 10096781.8719 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Ilocos Sur | 100395 | Padayao ES | BURGOS | 2 | 1 | 2STY4CL | 4 | 8995845.54 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Ilocos Sur | 100527 | Parparia Elementary School | NARVACAN | 2 | 1 | 1STY3CL | 3 | 5073993.8412 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region I | La Union | 101085 | Santol Central School | SANTOL | 1 | 1 | 2STY4CL | 4 | 9822142.12 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
SHS | Region I | La Union | 300141 | Santol Voc'l. HS - Liguay Annex | SANTOL | 1 | 1 | 1STY2CL | 2 | 4110250 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region I | La Union | 100940 | Caba CES | CABA | 2 | 1 | 2STY4CL | 4 | 9822142.12 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | La Union | 101002 | San Luis ES | PUGO | 2 | 1 | 2STY8CL | 8 | 20116843.8429 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region I | Laoag City | 102210 | Lagui-Sail Elementary School | Laoag City | 1 | 1 | 1STY2CL | 2 | 3797075.3659 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101136 | Baruan ES | Agno | 1 | 1 | 2STY4CL | 4 | 11111557.9107 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101214 | Mal-ong ES | Anda | 1 | 1 | 2STY4CL | 4 | 10096781.8671 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101391 | Laguit Centro ES | Bugallon I | 2 | 1 | 2STY6CL | 6 | 16242649.0993 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101337 | Tombor ES | Binmaley | 2 | 1 | 3STY6CL | 6 | 15834261.5566 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101299 | Paragos ES | BAYAMBANG | 3 | 1 | 1STY4CL | 4 | 7811162.2676 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101557 | Biba ES | Malasiqui | 3 | 1 | 1STY2CL | 2 | 3797075.3659 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101565 | J.C. Macaranas ES | Malasiqui | 3 | 1 | 1STY5CL | 5 | 9492688.4197 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101338 | Arnedo ES | BOLINAO | 1 | 1 | 2STY6CL | 6 | 13088808.4401 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
SHS | Region I | Pangasinan I, Lingayen | 300161 | Balingasay NHS | BOLINAO | 1 | 1 | 4STY8CL | 8 | 20916395.4873 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
SHS | Region I | Pangasinan I, Lingayen | 500370 | Bolinao Integrated School | BOLINAO | 1 | 1 | 4STY8CL | 8 | 20916395.4873 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101401 | Burgos Central School | BURGOS | 1 | 1 | 1STY2CL | 2 | 3196070.25 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101402 | Cabaruan ES | BURGOS | 1 | 1 | 1STY2CL | 2 | 3196070.25 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101343 | Cabuyao Elementary School | BOLINAO | 1 | 1 | 2STY4CL | 4 | 9970766.5144 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101349 | Estanza ES | BOLINAO | 1 | 1 | 2STY4CL | 4 | 9970766.5144 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101370 | Yabyaban Elementary School | BOLINAO | 1 | 1 | 2STY4CL | 4 | 9970766.5144 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101408 | Ilio-Ilio ES | BURGOS | 1 | 1 | 1STY3CL | 3 | 5858371.6957 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101352 | Ilog-Malino ES | BOLINAO | 1 | 1 | 2STY4CL | 4 | 9970766.5144 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
SHS | Region I | Pangasinan I, Lingayen | 300207 | ILOG-MALINO NATIONAL HIGH SCHOOL | BOLINAO | 1 | 1 | 2STY8CL | 8 | 19082377.2357 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
SHS | Region I | Pangasinan I, Lingayen | 300239 | Jose Rivera Bonsay NHS (Pogoruac NHS) | BURGOS | 1 | 1 | 1STY2CL | 2 | 3196070.25 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101353 | Lambes ES | BOLINAO | 1 | 1 | 2STY4CL | 4 | 9970766.5144 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101409 | Papallasen ES | BURGOS | 1 | 1 | 1STY2CL | 2 | 3196070.25 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101410 | Poguruac ES | BURGOS | 1 | 1 | 1STY2CL | 2 | 3196070.25 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101411 | San Miguel ES | BURGOS | 1 | 1 | 1STY2CL | 2 | 3196070.25 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
SHS | Region I | Pangasinan I, Lingayen | 500620 | Sapa Grande Integrated School | BURGOS | 1 | 1 | 1STY2CL | 2 | 3196070.25 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101413 | Sapa Pequeña ES | BURGOS | 1 | 1 | 1STY2CL | 2 | 3905581.1338 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101414 | Tambacan ES | BURGOS | 1 | 1 | 1STY2CL | 2 | 3196070.25 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101406 | Don Antonio Bonilla Mem. ES | BURGOS | 1 | 1 | 1STY2CL | 2 | 3196070.25 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101420 | Bued ES | CALASIAO | 3 | 1 | 2STY4CL | 4 | 10096781.8671 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101416 | Balani-Parongking ES | CALASIAO | 3 | 1 | 2STY4CL | 4 | 10096781.8671 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101629 | Balingueo Elementary School | SANTA BARBARA | 3 | 1 | 2STY6CL | 6 | 16242649.0993 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101403 | Cabongaoan ES | BURGOS | 1 | 1 | 2STY4CL | 4 | 10096781.8671 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
SHS | Region I | Pangasinan I, Lingayen | 300163 | Banaoang NHS | SANTA BARBARA | 3 | 1 | 4STY8CL | 8 | 18925955.3261 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101536 | Barang ES | MALASIQUI | 3 | 1 | 2STY4CL | 4 | 11373998.1852 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
SHS | Region I | Pangasinan I, Lingayen | 300178 | Buenlag NHS | CALASIAO | 3 | 1 | 4STY8CL | 8 | 18925955.316 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101421 | Cabilocaan ES | CALASIAO | 3 | 1 | 2STY4CL | 4 | 10096781.8671 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101630 | Dalongue ES | SANTA BARBARA | 3 | 1 | 2STY4CL | 4 | 10297281.8671 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
SHS | Region I | Pangasinan I, Lingayen | 300193 | Daniel Maramba NHS | SANTA BARBARA | 3 | 1 | 3STY9CL | 9 | 23718244.5821 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101432 | Doyong Malabago ES | CALASIAO | 3 | 1 | 2STY6CL | 6 | 16242649.0993 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101645 | Leet Elementary School | SANTA BARBARA | 3 | 1 | 2STY4CL | 4 | 10096781.8671 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101434 | Longos Elementary School | CALASIAO | 3 | 1 | 2STY6CL | 6 | 16342899.0993 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101437 | Mancup ES | CALASIAO | 3 | 1 | 2STY4CL | 4 | 10297281.8671 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101634 | Maronong ES | SANTA BARBARA | 3 | 1 | 2STY4CL | 4 | 10096781.8671 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101407 | Don Matias ES | BURGOS | 1 | 1 | 2STY4CL | 4 | 10096781.8671 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
SHS | Region I | Pangasinan I, Lingayen | 300179 | Burgos NHS | BURGOS | 1 | 1 | 3STY9CL | 9 | 24529217.8493 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101438 | Nagsaing Elementary School | CALASIAO | 3 | 1 | 2STY6CL | 6 | 16242649.0993 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101424 | Nalsian Bacayao ES | CALASIAO | 3 | 1 | 2STY4CL | 4 | 10297281.8671 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101651 | Payas ES | SANTA BARBARA | 3 | 1 | 2STY6CL | 6 | 16242649.0993 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region I | Pangasinan I, Lingayen | 101440 | Talibaew ES | CALASIAO | 3 | 1 | 3STY9CL | 9 | 24018994.5821 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 101904 | Bigbiga ES | SAN FABIAN | 4 | 1 | 2STY8CL | 8 | 18686460.442 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 101925 | Jose N. Juguilon ES | SAN FABIAN | 4 | 1 | 2STY4CL | 4 | 10270104.5533 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 101928 | Longos ES | SAN FABIAN | 4 | 1 | 2STY8CL | 8 | 18047852.303 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 101929 | Longos Proper ES | SAN FABIAN | 4 | 1 | 2STY8CL | 8 | 18047852.303 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 101913 | Rabon ES | SAN FABIAN | 4 | 1 | 2STY4CL | 4 | 10310723.4373 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 101915 | Sanitas ES | SAN FABIAN | 4 | 1 | 2STY8CL | 8 | 18706769.879 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
SHS | Region I | Pangasinan II, Binalonan | 300295 | Cabilaoan Agro-Industrial HS | LAOAC | 5 | 1 | 2STY6CL | 6 | 14562524.0714 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
SHS | Region I | Pangasinan II, Binalonan | 300319 | Laoac NHS | LAOAC | 5 | 1 | 2STY6CL | 6 | 14562524.0714 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 101786 | Lebueg ES | LAOAC | 5 | 1 | 2STY6CL | 6 | 14562524.0714 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
SHS | Region I | Pangasinan II, Binalonan | 500376 | Macayo IS | ALCALA | 5 | 1 | 3STY6CL | 6 | 17506985.097 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 101873 | Palacpalac ES | POZORRUBIO | 5 | 1 | 2STY4CL | 4 | 11373998.1852 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 102037 | Pinmilapil ES | SISON | 5 | 1 | 2STY4CL | 4 | 11373998.1852 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 102125 | Puelay ES | VILLASIS | 5 | 1 | 2STY6CL | 6 | 23551696.2296 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
SHS | Region I | Pangasinan II, Binalonan | 321203 | San Antonio NHS | SANTO TOMAS | 5 | 1 | 3STY6CL | 6 | 17641149.7321 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 102060 | San Jose ES | SANTO TOMAS | 5 | 1 | 3STY6CL | 6 | 20584781.9809 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 101706 | San Pedro Ili ES | ALCALA | 5 | 1 | 2STY6CL | 6 | 13514273.7508 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
SHS | Region I | Pangasinan II, Binalonan | 300307 | Juan G. Macaraeg NHS | BINALONAN | 5 | 1 | 4STY12CL | 12 | 39640816.8649 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 101768 | Vacante ES | BINALONAN | 5 | 1 | 2STY6CL | 6 | 14562524.0714 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 152004 | Yatyat Annex Elementary School | LAOAC | 5 | 1 | 2STY4CL | 4 | 11373998.1852 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 102044 | Dalayap ES | SANTA MARIA | 6 | 1 | 2STY4CL | 4 | 11719416.1868 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 101895 | Rizal Elementary School | ROSALES | 6 | 1 | 2STY4CL | 4 | 11719416.1868 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 101972 | Salpad ES | SAN NICOLAS | 6 | 1 | 2STY4CL | 4 | 11848318.3786 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 101842 | San Macario Norte Elementary School | NATIVIDAD | 6 | 1 | 2STY4CL | 4 | 11719416.1868 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 101999 | Teofilo C. Quintin ES | SAN QUINTIN | 6 | 1 | 2STY4CL | 4 | 11719416.1868 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | Pangasinan II, Binalonan | 102077 | Zamora ES | TAYUG | 6 | 1 | 2STY4CL | 4 | 11719416.1868 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region I | San Carlos City | 102250 | TALANG CENTRAL SCHOOL | San Carlos City | 3 | 1 | 2STY4CL | 4 | 10025000 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
SHS | Region I | San Fernando City | 500602 | South Central IS | San Fernando City | 1 | 1 | 2STY6CL | 6 | 21672302.0811 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region I | Urdaneta City | 102289 | Camantiles ES | Urdaneta City | 5 | 1 | 1STY2CL | 2 | 4711750 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
SHS | Region I | Vigan City | 300052 | Ilocos Sur NHS | Vigan City | 1 | 1 | 2STY4CL | 4 | 11111557.9107 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
SHS | Region II | Batanes | 300415 | Ivana NHS | IVANA | 0 | 1 | 1STY2CL | 2 | 9563320.0284 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region II | Cagayan | 102766 | Malinta ES | LASAM | 2 | 1 | 1STY2CL | 2 | 5147025.5752 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region II | Cagayan | 102352 | Sta. Rosa Elementary School | ABULUG | 2 | 1 | 1STY2CL | 2 | 4100860.3745 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region II | Cauayan City | 103241 | Sillawit ES | CITY OF CAUAYAN | 3 | 1 | 1STY2CL W/ TOILET | 2 | 5471868.1866 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region II | City of Ilagan | 103393 | Cabeceria 3 Elementary School | ILAGAN CITY (CAPITAL) | 1 | 1 | 1STY2CL W/ TOILET | 2 | 4692585.0872 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region II | Isabela | 103888 | Antagan 1st ES - Sitio Magoli Annex | TUMAUINI | 1 | 1 | 1STY3CL W/ TOILET | 3 | 6345794.7847 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region II | Isabela |  | SANTA ES - SITIO MINABANG ANNEX | TUMAUINI | 1 | 1 | 1STY2CL W/ TOILET | 2 | 4300378.7566 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region II | Isabela | 103098 | Andabuen Elementary School - Main | BENITO SOLIVEN | 2 | 1 | 1STY3CL W/ TOILET | 3 | 6753370.6333 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
SHS | Region II | Isabela | 300580 | Lanting Region National High School | ROXAS | 2 | 1 | 2STY10CL | 10 | 20085370.5158 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
SHS | Region II | Isabela | 300562 | Munoz High School | ROXAS | 2 | 1 | 2STY10CL | 10 | 20085370.5158 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
K10 | Region II | Isabela | 103636 | Roxas Central School | ROXAS | 2 | 1 | 2STY10CL | 10 | 20085370.5158 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
SHS | Region II | Isabela | 300579 | Roxas National High School | ROXAS | 2 | 1 | 2STY10CL | 10 | 20085370.5158 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
K10 | Region II | Isabela | 103643 | Roxas West Central School | ROXAS | 2 | 1 | 2STY10CL | 10 | 20085370.5158 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
K10 | Region II | Isabela | 103648 | Sinamar Elementary School | ROXAS | 2 | 1 | 1STY3CL W/ TOILET | 3 | 6774472.2357 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region II | Isabela | 102990 | Burgos Elementary School | ALICIA | 3 | 1 | 1STY2CL | 2 | 5932062.3529 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region II | Isabela | 103174 | Namnama Elementary School | CABATUAN | 3 | 1 | 1STY2CL | 2 | 5932062.3529 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region II | Nueva Vizcaya | 104166 | Bascaran ES | SOLANO | 0 | 1 | 1STY2CL | 2 | 5233050 |  | Ongoing | 5% | 5% | 0% | Project did not statst due to the late release of Permit to Demolish | [10 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region II | Nueva Vizcaya | 104021 | DIADI CENTRAL SCHOOL | DIADI | 0 | 1 | 1STY2CL | 2 | 5333300 |  | Ongoing | 18% | 18% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region II | Nueva Vizcaya | 300525 | Tiblac High School | AMBAGUIO | 0 | 1 | 1STY2CL | 2 | 5513750 |  | Ongoing | 4% | 4% | 0% | Location of school building is re-positioned to adapt orientation in the Site Development Plan | [10 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region II | Quirino | 156517 | Agta Community P/S | MADDELA | 0 | 1 | 1STY2CL W/ TOILET | 2 | 6873140 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region II | Santiago City | 103839 | San Jose ES | CITY OF SANTIAGO | 4 | 1 | 1STY2CL W/ TOILET | 2 | 4417965.4101 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region II | Tuguegarao City | 104397 | Carig Norte Elementary School | TUGUEGARAO CITY(Capital) | 3 | 1 | 1STY2CL W/ TOILET | 2 | 4035321.3756 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region III | Angeles City | 107035 | Salapungan ES | ANGELES CITY | 1 | 1 | 2STY4CL | 4 | 11408450 |  | Ongoing | 40% | 40% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Angeles City | 107056 | Leoncia Village ES | ANGELES CITY | 1 | 1 | 2STY4CL | 4 | 11278125 |  | Ongoing | 40% | 40% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Angeles City | 107052 | Apung Guidang Nepomuceno Elementary School | ANGELES CITY | 1 | 1 | 2STY4CL | 4 | 11408450 |  | Ongoing | 30% | 30% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
SHS | Region III | Angeles City | 500131 | Amsic IS | ANGELES CITY | 1 | 1 | 4STY16CL | 16 | 37243614.8049 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
K10 | Region III | Angeles City | 107031 | Jose P. Dizon ES | Angeles City | 1 | 1 | 4STY16CL | 16 | 41966940.1711 |  | Ongoing | 40% | 40% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
K10 | Region III | Aurora | 104415 | Reserva ES | BALER (Capital) | 0 | 1 | 2UNITS 2STY8CL | 16 | 39380767.8737 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
K10 | Region III | Aurora | 104479 | Puangi ES | DIPACULAO | 0 | 1 | 1STY3CL | 3 | 5276161.2293 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region III | Aurora | 305397 | Mijares National High School | DIPACULAO | 0 | 1 | 2STY6CL | 6 | 20683422.828 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region III | Aurora | 104412 | Diego T. Ortiz ES | Baler | 0 | 1 | 2STY4CL | 4 | 12222713.7028 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Aurora | 157516 | Diamanen PS | Dipaculao | 0 | 1 | 1STY2CL | 2 | 4895701.3716 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region III | Aurora | 104463 | Bayabas ES | DIPACULAO | 0 | 1 | 1STY3CL | 3 | 5276161.2293 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region III | BALANGA CITY | 104552 | Balanga Elementary School | Balanga City | 2 | 1 | 2STY4CL | 4 | 12222713.7028 |  | Ongoing | 30% | 30% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Bataan | 104603 | Tucop ES | DINALUPIHAN | 1 | 1 | 2STY6CL | 6 | 16560095.396 |  | Ongoing | 30% | 30% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region III | Bataan | 104539 | T. Pinpin MES | ABUCAY | 1 | 1 | 2STY10CL | 10 | 27568749.1779 |  | Ongoing | 30% | 30% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0
K10 | Region III | Bataan | 104600 | Sta. Isabel ES | DINALUPIHAN | 1 | 1 | 2STY4CL | 4 | 16103622.5998 |  | Ongoing | 30% | 30% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Bataan | 104538 | Salian ES | ABUCAY | 1 | 1 | 2STY10CL | 10 | 27568749.1779 |  | Ongoing | 30% | 30% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0
K10 | Region III | Bataan | 104610 | Hermosa ES | HERMOSA | 1 | 1 | 2STY6CL | 6 | 19492200.0677 |  | Ongoing | 30% | 30% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region III | Bataan | 104576 | Happy Valley ES | DINALUPIHAN | 1 | 1 | 2STY4CL | 4 | 15642467.7778 |  | Ongoing | 30% | 30% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Bataan | 104702 | F.C. Del Rosario ES | SAMAL | 1 | 1 | 2STY4CL | 4 | 15423968.6823 |  | Ongoing | 20% | 20% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Bataan | 104575 | Dinalupihan ES | DINALUPIHAN | 1 | 1 | 2UNITS 2STY4CL | 8 | 27752809.5514 |  | Ongoing | 20% | 20% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region III | Bataan | 104573 | Daang Bago ES | DINALUPIHAN | 1 | 1 | 2STY4CL | 4 | 16054978.7635 |  | Ongoing | 20% | 20% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Bataan | 104531 | Bangkal ES | ABUCAY | 1 | 1 | 2STY4CL | 4 | 15423968.6823 |  | Ongoing | 25% | 25% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Bataan | 104531 | Bangkal ES | ABUCAY | 1 |  | 2STY4CL | 4 | 15642467.7778 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
SHS | Region III | Bataan | 300701 | Balsik NHS | HERMOSA | 1 | 1 | 2STY6CL | 6 | 19492200.0677 |  | Ongoing | 20% | 20% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region III | Bataan | 104687 | Sto. Domingo ES | ORION | 2 | 1 | 2STY8CL | 8 | 20852000 |  | Ongoing | 30% | 30% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region III | Bataan | 300700 | Saysain NHS | BAGAC | 2 | 1 | 2STY6CL | 6 | 17875114.9064 |  | Ongoing | 20% | 20% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
SHS | Region III | Bataan | 306618 | Mariveles NHS - Camaya Campus | MARIVELES | 2 | 1 | 4STY20CL | 20 | 47217750 |  | Ongoing | 20% | 20% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
K10 | Region III | Bataan | 104631 | Lamao ES | LIMAY | 2 | 1 | 2STY4CL | 4 | 10726750 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Bataan | 104643 | Ipag ES | MARIVELES | 2 | 1 | 2STY8CL | 8 | 20852000 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region III | Bataan | 104636 | Alasasin ES | MARIVELES | 2 | 1 | 2STY6CL | 6 | 15238000 |  | Ongoing | 30% | 30% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
SHS | Region III | Bulacan | 300776 | Sta. Cruz NHS | PAOMBONG | 1 | 1 | 1STY4CL | 4 | 7077921.6775 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
SHS | Region III | Bulacan | 300754 | Ramona S. Trillana HS (Mayor Ramon Trillana Mem. HS (Iba NHS)) | HAGONOY | 1 | 1 | 4STY12CL | 12 | 41966940.1711 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
K10 | Region III | Bulacan | 104825 | Malis ES | GUIGUINTO | 2 | 1 | 4STY20CL | 20 | 55217179.6022 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
K10 | Region III | Bulacan | 104959 | T.P. Policarpio ES (Minuyan ES) | NORZAGARAY | 3 | 1 | 2STY10CL | 10 | 27748075.9569 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0
K10 | Region III | Bulacan | 104726 | Sulucan ES | ANGAT | 3 | 1 | 2STY8CL | 8 | 21968818.8043 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region III | Bulacan | 104726 | Sulucan ES | ANGAT | 3 |  | 2STY6CL | 6 | 16974423.8741 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region III | Bulacan | 105087 | Sibul Elementary School | SAN MIGUEL | 3 | 1 | 2STY6CL | 6 | 18949613.6243 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region III | Bulacan | 105099 | Dr. Juan F. Pascual MS (formerly Silangan ES) | SAN MIGUEL | 3 | 1 | 2STY8CL | 8 | 24551364.3976 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region III | Bulacan | 158502 | San Vicente ES | SAN MIGUEL | 3 | 1 | 3STY9CL | 9 | 30349438.9063 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0
SHS | Region III | Bulacan | 300773 | San Rafael Nat'l Trade School | SAN RAFAEL | 3 | 1 | 4STY20CL | 20 | 63323606.8917 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
K10 | Region III | Bulacan | 104957 | San Mateo Elementary School | NORZAGARAY | 3 | 1 | 2STY8CL | 8 | 20315938.1274 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region III | Bulacan | 104952 | Norzagaray ES | NORZAGARAY | 3 | 1 | 2STY10CL | 10 | 27088174.5775 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0
K10 | Region III | Bulacan | 104950 | Matictic Elementary School | NORZAGARAY | 3 | 1 | 2STY4CL | 4 | 10416182.5877 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Bulacan | 105055 | Malipampang ES | SAN ILDEFONSO | 3 | 1 | 3STY9CL | 9 | 26024144.5962 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0
K10 | Region III | Bulacan | 105120 | Maguinao Elementary School | SAN RAFAEL | 3 | 1 | 4STY12CL | 12 | 33955115.4584 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
K10 | Region III | Bulacan | 105036 | Lapnit Elementary School | SAN ILDEFONSO | 3 | 1 | 2STY4CL | 4 | 11553268.6939 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Bulacan | 105115 | Caingin ES | SAN RAFAEL | 3 | 1 | 2STY10CL | 10 | 27229215.4605 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0
K10 | Region III | Bulacan | 104966 | Panghulo Elementary School | OBANDO | 4 | 1 | 3STY6CL | 6 | 23523321.5798 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region III | Bulacan | 105153 | Kaylawig ES | SANTA MARIA | 4 | 1 | 4STY8CL | 8 | 23131517.7528 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region III | Bulacan | 105147 | Cay Pombo ES | SANTA MARIA | 4 | 1 | 3STY15CL | 15 | 37857022.5601 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0
K10 | Region III | Cabanatuan City | 107115 | San Josef ES | Cabanatuan City | 3 | 1 | 2STY4CL | 4 | 12222713.7028 |  | Ongoing | 1% | 1% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
SHS | Region III | Gapan City | 300849 | San Nicolas NHS | CITY OF GAPAN | 4 | 1 | 2STY4CL | 4 | 8968266.5144 |  | Ongoing | 2% | 2% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
TVL | Region III | Gapan City | 300849 | San Nicolas NHS | CITY OF GAPAN | 4 |  | 4STY8WS | 4 | 39937576.1029 |  | Ongoing | 4% | 4% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Gapan City | 105339 | San Nicolas Central School | CITY OF GAPAN | 4 | 1 | 2STY8CL | 8 | 21654000 |  | Ongoing | 2% | 2% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region III | Gapan City | 105325 | Mahipon ES | Gapan City | 4 | 1 | 2STY4CL | 4 | 12222713.7028 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Gapan City | 105334 | Gapan South CS | CITY OF GAPAN | 4 | 1 | 3STY12CL | 12 | 28571250 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
K10 | Region III | Mabalacat City | 300900 | Mauaque HS (Res) | MABALACAT CITY | 1 | 1 | 4STY16CL | 16 | 37003014.8049 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
K10 | Region III | Mabalacat City | 106079 | Gasdam ES | MABALACAT CITY | 1 | 1 | 4STY8CL | 8 | 20462528.75 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region III | Mabalacat City | 106063 | Calapi Negrito ES | MABALACAT CITY | 1 | 1 | 2STY4CL | 4 | 12472607.5795 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Malolos City | 104877 | Santor ES | CITY OF MALOLOS (Capital) | 1 | 1 | 2STY4CL | 4 | 12472607.5795 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Meycauayan City | 265001 | Caingin Bayanihan ES | CITY OF MEYCAUAYAN | 4 | 1 | 4STY8CL | 8 | 20298212.6843 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region III | Munoz Science City | 105561 | Sapang Cawayan ES | SCIENCE CITY OF MUÑOZ | 2 | 1 | 1STY3CL | 3 | 5695613.0538 |  | Ongoing | 20% | 20% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region III | Munoz Science City | 500395 | Gabaldon IS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 1STY3CL | 3 | 5695613.0538 |  | Ongoing | 20% | 20% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
SHS | Region III | Nueva Ecija | 300860 | Vicente R. Bumanlag, Sr. National HS | ALIAGA | 1 | 1 | 3STY15CL | 15 | 41015159.2928 |  | Ongoing | 35% | 35% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0
K10 | Region III | Nueva Ecija | 105807 | Talavera North Elementary School | TALAVERA | 1 | 1 | 2STY4CL | 4 | 14502998.6188 |  | Ongoing | 3% | 3% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
SHS | Region III | Nueva Ecija | 300864 | TALAVERA NATIONAL HIGH SCHOOL | TALAVERA | 1 | 1 | 4STY20CL | 20 | 44303156.9782 |  | Ongoing | 40% | 40% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
K10 | Region III | Nueva Ecija | 105806 | Talavera CS | TALAVERA | 1 | 1 | 4STY20CL | 20 | 47655164.2386 |  | Ongoing | 40% | 40% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
K10 | Region III | Nueva Ecija | 105829 | San Miguel Na Munti ES | TALAVERA | 1 | 1 | 2STY4CL | 4 | 14502998.6188 |  | Ongoing | 70% | 70% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
SHS | Region III | Nueva Ecija | 306807 | San Carlos High School | ALIAGA | 1 | 1 | 4STY12CL | 12 | 36017544.4027 |  | Ongoing | 40% | 40% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
K10 | Region III | Nueva Ecija | 105181 | San Carlos ES | ALIAGA | 1 | 1 | 3STY12CL | 12 | 33508110.2923 |  | Ongoing | 40% | 40% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
K10 | Region III | Nueva Ecija | 105828 | PULA ES | TALAVERA | 1 | 1 | 2STY4CL | 4 | 14502998.6188 |  | Ongoing | 3% | 3% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Nueva Ecija | 105827 | Paludpod ES | TALAVERA | 1 | 1 | 2STY4CL | 4 | 14502998.6188 |  | Ongoing | 20% | 20% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Nueva Ecija | 105823 | LA TORRE ES | TALAVERA | 1 | 1 | 2STY4CL | 4 | 14502998.6188 |  | Ongoing | 20% | 20% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Nueva Ecija | 105813 | CABUBULAUNAN ELEMENTARY SCHOOL | TALAVERA | 1 | 1 | 2STY4CL | 4 | 14502998.6188 |  | Ongoing | 3% | 3% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Nueva Ecija | 105792 | Bakal III ES | TALAVERA | 1 | 1 | 3STY15CL | 15 | 38782535.0613 |  | Ongoing | 3% | 3% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0
K10 | Region III | Nueva Ecija | 105523 | NAMULANDAYAN ES | LUPAO | 2 | 1 | 2STY4CL | 4 | 14502998.6188 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Nueva Ecija | 105502 | LLANERA CS | LLANERA | 2 | 1 | 2STY6CL | 6 | 17905789.7924 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region III | Nueva Ecija | 105519 | BURGOS ES | LUPAO | 2 | 1 | 2STY4CL | 4 | 14502998.6188 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Nueva Ecija | 105765 | SANTA ROSA CENTRAL SCHOOL | STA. ROSA | 3 | 1 | 2STY4CL | 4 | 14502998.6188 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Nueva Ecija | 105687 | SAN ISIDRO CS | SAN ISIDRO | 4 | 1 | 2STY4CL | 4 | 14502998.6188 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Nueva Ecija | 105588 | PALALE ES | GEN. TINIO | 4 | 1 | 2STY6CL | 6 | 17905789.7924 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region III | Olongapo City | 107118 | BANGAL ES | Olongapo City | 1 | 1 | 2STY4CL | 4 | 12222713.7028 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Pampanga | 106123 | Magalang CS | MAGALANG | 1 | 1 | 2STY4CL | 4 | 12222713.7028 |  | Ongoing | 20% | 20% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Pampanga | 106117 | Ayala ES | MAGALANG | 1 | 1 | 2STY4CL | 4 | 11278125 |  | Ongoing | 40% | 40% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Pampanga | 106122 | Escaler ES | MAGALANG | 1 | 1 | 2STY4CL | 4 | 11408450 |  | Ongoing | 20% | 20% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Pampanga | 106135 | San Vicente ES | MAGALANG | 1 | 1 | 2STY4CL | 4 | 11278125 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Pampanga | 106050 | Remedios Elementary School | LUBAO | 2 | 1 | 2STY4CL | 4 | 12222713.7028 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Pampanga | 105997 | Guagua ES | GUAGUA | 2 | 1 | 2STY4CL | 4 | 12222713.7028 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Pampanga | 102292 | Francisco Henson Elementary School | PORAC | 2 | 1 | 2STY4CL | 4 | 12222713.7028 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Pampanga |  | San Juan Bano HS | ARAYAT | 3 | 1 | 2STY4CL | 4 | 12222713.7028 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
SHS | Region III | Pampanga | 300896 | Malino NHS | MEXICO | 3 | 1 | 2STY4CL | 4 | 12222713.7028 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | San Fernando City | 107198 | San Pedro ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 2STY4CL | 4 | 8968266.5144 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | San Fernando City | 500978 | Pulung Bulu ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 2STY4CL | 4 | 8968266.5144 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | San Fernando City | 107167 | Bulaon ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 2STY4CL | 4 | 12222713.7028 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region III | San Jose City | 105725 | San Jose West Central School | SAN JOSE CITY | 2 | 1 | 2STY4CL | 4 | 12222713.7028 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
SHS | Region III | San Jose del Monte City | 301062 | SAPANG PALAY NHS | San Jose del Monte City | 0 | 1 | 2STY4CL | 4 | 12222713.7028 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region III | San Jose del Monte City | 107145 | BAGONG BUHAY F ES | San Jose del Monte City | 0 | 1 | 4STY12CL | 12 | 32653646.4899 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
K10 | Region III | Tarlac | 305562 | San Manuel National High School | SAN MANUEL | 1 | 1 | 4STY16CL | 16 | 50514232.4746 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
K10 | Region III | Tarlac | 106611 | SAN JUAN ES | RAMOS | 1 | 1 | 2STY4CL | 4 | 12222713.7028 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Tarlac | 106548 | CAMPOSANTO ES | MONCADA | 1 | 1 | 2STY6CL | 6 | 17875114.9064 |  | Ongoing | 30% | 30% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region III | Tarlac | 106575 | BRILLANTE ES | PANIQUI | 1 | 1 | 2STY4CL | 4 | 12222713.7028 |  | Ongoing | 20% | 20% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
SHS | Region III | Tarlac | 301000 | Victoria National High School | VICTORIA | 2 | 1 | 2UNITS 4STY16CL | 32 | 105486115.2641 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0
K10 | Region III | Tarlac | 106647 | Sula ES | SAN JOSE | 2 | 1 | 2STY4CL | 4 | 13186902.634 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Tarlac | 106642 | Pisapungan ES | SAN JOSE | 2 | 1 | 1STY2CL W/ TOILET | 2 | 4882388.1917 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region III | Tarlac | 106642 | Pisapungan ES | SAN JOSE | 2 |  | 2STY6CL | 6 | 18604294.75 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region III | Tarlac | 106793 | Palacpalac ES | VICTORIA | 2 | 1 | 1STY2CL W/TOILET | 2 | 4381118.8133 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
TVL | Region III | Tarlac | 106640 | Moriones ES | SAN JOSE | 2 | 1 | 1 UNIQUE WORKSHOP | 1 | 3054354.3538 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
K10 | Region III | Tarlac | 106633 | Labney ES | SAN JOSE | 2 | 1 | 2STY6CL | 6 | 16931222.5 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region III | Tarlac | 106451 | Gerona North CES | GERONA | 2 | 1 | 2STY18CL L-TYPE SCHOOL BLDG. | 18 | 56282867.3276 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0
K10 | Region III | Tarlac | 106631 | E.V.A. Abelling PS | SAN JOSE | 2 | 1 | 2STY6CL | 6 | 17875114.9064 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region III | Tarlac | 106775 | Bangar Elementary | VICTORIA | 2 | 1 | 1STY2CL | 2 | 3797075.3659 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region III | Tarlac | 106324 | San Pedro ES | BAMBAN | 3 | 1 | 2STY4CL | 4 | 10808983.6815 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Tarlac | 106411 | SAN JOSE ES | CONCEPCION | 3 | 1 | 2STY10CL | 10 | 26571116.7465 |  | Ongoing | 35% | 35% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0
K10 | Region III | Tarlac | 106432 | Ligaya ES | CONCEPCION | 3 | 1 | 1STY2CL W/ TOILET ATTACHED | 2 | 4999651.9199 |  | Ongoing | 60% | 60% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region III | Tarlac | 106315 | Dapdap Resettlement ES | BAMBAN | 3 | 1 | 2STY8CL | 8 | 21382823.75 |  | Ongoing | 25% | 25% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region III | Tarlac | 106388 | Cristo Rey Central E/S | CAPAS | 3 | 1 | 2STY4CL | 4 | 10840341.9717 |  | Ongoing | 25% | 25% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Tarlac | 106388 | Cristo Rey Central E/S | CAPAS | 3 |  | 2STY6CL | 6 | 13842988.2577 |  | Ongoing | 25% | 25% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region III | Tarlac | 106388 | Cristo Rey Central E/S | CAPAS | 3 |  | 2STY8CL | 8 | 20162722.0925 |  | Ongoing | 25% | 25% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region III | Tarlac | 106421 | Concepcion South ES | CONCEPCION | 3 | 1 | 2STY6CL | 6 | 14155226.1659 |  | Ongoing | 40% | 40% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region III | Tarlac | 106419 | Balutu ES | CONCEPCION | 3 | 1 | 2STY4CL | 4 | 11172148.6799 |  | Ongoing | 25% | 25% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
SHS | Region III | Tarlac | 500124 | Aranguren Integrated School | CAPAS | 3 | 1 | 4STY12CL | 12 | 41072853.8595 |  | Ongoing | 35% | 35% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
K10 | Region III | Tarlac City | 106722 | Sinait ES | Tarlac City | 2 | 1 | 2STY6CL | 6 | 14951254.7045 |  | Ongoing | 35% | 35% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region III | Tarlac City | 106695 | San Sebastian ES | CITY OF TARLAC (Capital) | 2 | 1 | 2STY8CL | 8 | 19055159.491 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region III | Tarlac City | 106706 | San Pascual ES | CITY OF TARLAC (Capital) | 2 | 1 | 2STY4CL | 4 | 11213725.1619 |  | Ongoing | 45% | 45% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Tarlac City | 106694 | San Nicolas ES | CITY OF TARLAC (Capital) | 2 | 1 | 4STY8CL | 8 | 18611233.7743 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region III | Tarlac City | 106702 | Maliwalo Central ES | CITY OF TARLAC (Capital) | 2 | 1 | 4STY20CL | 20 | 51654096.7388 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
K10 | Region III | Tarlac City | 106698 | Balingcanaway Centro ES | CITY OF TARLAC (Capital) | 2 | 1 | 2STY4CL | 4 | 11988052.2722 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region III | Zambales | 106858 | KANAYNAYAN COMMUNITY SCHOOL | CASTILLEJOS | 1 | 1 | 1STY2CL | 2 | 3797075.3659 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region III | Zambales | 160512 | Mapalad Elementary School | STA CRUZ | 2 | 1 | 1STY2CL | 2 | 3797075.3659 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region III | Zambales | 106934 | Maloma Community Elementary School | SAN FELIPE | 2 | 1 | 2STY6CL | 6 | 17875114.9064 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region III | Zambales | 101782 | Alao Elementary School | BOTOLAN | 2 | 1 | 1STY3CL | 3 | 5695613.0538 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
SHS | Region IV-A | Antipolo City | 321505 | Dela Paz NHS | CITY OF ANTIPOLO | 1 | 1 | 3STY3CL | 3 | 12888626.6035 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region IV-A | Bacoor City | 107886 | Molino Elementary School | BACOOR | 2 | 1 | 4STY8CL | 8 | 24636588.7371 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region IV-A | Batangas | 107725 | Butong Elementary School | TAAL | 1 | 1 | 2STY12CL | 12 | 30482344.8225 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
K10 | Region IV-A | Batangas | 107511 | Nasugbu East Central School | NASUGBU | 1 | 1 | 3STY9CL | 9 | 26827497.49 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0
K10 | Region IV-A | Batangas | 307702 | Banoyo National High School | SAN LUIS | 2 | 1 | 4STY8CL | 8 | 23842206.875 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region IV-A | Batangas | 107432 | Calo Elementary School | LOBO | 2 | 1 | 2STY6CL | 6 | 21343926.75 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region IV-A | Batangas | 107433 | Calumpit Elementary School | LOBO | 2 | 1 | 1STY2CL | 2 | 5675803.6238 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region IV-A | Batangas | 107645 | Calumpang Elementary School | SAN LUIS | 2 | 1 | 2STY6CL | 6 | 18205600.5 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region IV-A | Batangas | 107435 | Lagadlarin/Olo-Olo Elementary School | LOBO | 2 | 1 | 2STY6CL | 6 | 19219629.25 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region IV-A | Batangas | 107647 | Locloc Elementary School | SAN LUIS | 2 | 1 | 2STY4CL & 1STY2CL | 6 | 18266652.75 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region IV-A | Batangas | 107649 | Mahabang Parang Primary School | SAN LUIS | 2 | 1 | 1STY2CL | 2 | 5002575.25 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region IV-A | Batangas | 107439 | Malapad Na Parang Elementary School | LOBO | 2 | 1 | 1STY2CL | 2 | 5230142.75 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region IV-A | Batangas | 107442 | Nagtoctoc Elementary School | LOBO | 2 | 1 | 1STY2CL | 2 | 5704325.25 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region IV-A | Batangas | 107447 | Sawang Elementary School | LOBO | 2 | 1 | 1STY2CL | 2 | 5311345.25 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
SHS | Region IV-A | Batangas | 342199 | Tingloy Senior High School | TINGLOY | 2 | 1 | 4STY16CL | 16 | 38368419.8049 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
K10 | Region IV-A | Batangas | 107657 | Tungal Elementary School | SAN LUIS | 2 | 1 | 4STY8CL | 8 | 23453236.875 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region IV-A | Batangas | 107426 | Apar Elementary School | LOBO | 2 | 1 | 2STY6CL | 6 | 21197561.75 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
SHS | Region IV-A | Batangas | 342216 | Agoncillo SHS | AGONCILLO | 3 | 1 | 4STY8CL | 8 | 17202469.5967 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region IV-A | Batangas | 107707 | Doña Tiburcia Carpio Malvar Elementary School | SANTO TOMAS | 3 | 1 | 2STY4CL | 4 | 8923425.1806 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region IV-A | Batangas | 107741 | Jorge B. Vargas MES | TALISAY | 3 | 1 | 2STY4CL | 4 | 9018391.5144 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region IV-A | Batangas | 107585 | Bagong Pook Elementary School | SAN JOSE | 4 | 1 | 2STY4CL | 4 | 10261088.75 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region IV-A | Batangas | 107603 | Barualte Elementary School | San Juan | 4 | 1 | 2STY2CL | 2 | 7035043.75 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region IV-A | Batangas | 107590 | Dagatan Elementary School | San Jose | 4 | 1 | 2STY4CL | 4 | 10261088.75 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region IV-A | Batangas | 107614 | Imelda Elementary School | San Juan | 4 | 1 | 2STY4CL | 4 | 10311213.75 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region IV-A | Batangas | 107561 | Masaya Elementary School | Rosario | 4 | 1 | 3STY3CL | 3 | 11035018.75 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region IV-A | Batangas | 107622 | Palahanan ES | San Juan | 4 | 1 | 2STY2CL | 2 | 7080156.25 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region IV-A | Batangas | 107629 | Quipot ES | San Juan | 4 | 1 | 2STY2CL | 2 | 7095193.75 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region IV-A | Batangas City | 301472 | Batangas National High School | BATANGAS CITY (Capital) | 5 | 1 | 4STY16CL | 16 | 56173976.73 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
K10 | Region IV-A | Batangas City | 109620 | Piit ES | BATANGAS CITY (Capital) | 5 | 1 | 2STY2CL | 2 | 6857108.5513 |  | Ongoing | 7% | 7% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
SHS | Region IV-A | Batangas City | 301481 | Tabangao Senior High School | BATANGAS CITY (Capital) | 5 | 1 | 4STY8CL | 8 | 17503219.5967 |  | Ongoing | 8% | 8% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region IV-A | Binan City | 108219 | Dr. Marcelino Z. Batista Memorial Elementary School | CITY OF BIÑAN | 1 | 1 | 4STY12CL | 12 | 42478752.05 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
K10 | Region IV-A | Calamba City | 109861 | San Ramon Elementary School | CITY OF CALAMBA | 2 | 1 | 4STY8CL | 8 | 24287667.75 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region IV-A | Cavite | 108016 | Aguinaldo ES | KAWIT | 1 | 1 | 4STY20CL | 20 | 62433177.8804 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
K10 | Region IV-A | Cavite | 108083 | San Antonio ES | Noveleta | 1 | 1 | 4STY8CL | 8 | 26793468.6341 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region IV-A | Cavite | 108026 | Wakas ES | KAWIT | 1 | 1 | 4STY8CL | 8 | 26736887.3997 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region IV-A | Cavite | 108096 | Balubad ES | SILANG | 5 | 1 | 4STY20CL | 20 | 53412970.9288 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
K10 | Region IV-A | Cavite | 107892 | Bancal ES | CARMONA | 5 | 1 | 4STY16CL | 16 | 46774716.3279 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
K10 | Region IV-A | Cavite | 108118 | Carmen ES | SILANG | 5 | 1 | 2STY6CL | 6 | 28410465.7718 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region IV-A | Cavite | 108124 | Lalaan CS | SILANG | 5 | 1 | 4STY20CL | 20 | 54928314.7209 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
K10 | Region IV-A | Cavite | 107942 | San Gabriel III ES | GEN. MARIANO ALVAREZ | 5 | 1 | 4STY16CL | 16 | 47026140.1299 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
K10 | Region IV-A | Cavite | 108111 | Silang West ES | Silang | 5 | 1 | 4STY20CL | 20 | 53616691.4399 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
SHS | Region IV-A | Cavite |  | Tagaytay City NHS Annex (Senior HS) | Cavite | 7 | 1 | 4STY100CL (Phase 2) | 36 | 91182387.5 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36 | 0
K10 | Region IV-A | Cavite City | 109634 | Bagumbuhay ES | Cavite City | 1 | 1 | 2STY4CL | 4 | 14918543.5806 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region IV-A | Dasmarinas City | 107903 | Humayao ES | CITY OF DASMARIÑAS | 4 | 1 | 4STY8CL | 8 | 21480347.5415 |  | Under Procurement | 0% | 0% | 0% | Requested for additional fund / Proposed start is on April 2019 due to issue in access | [10 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
SHS | Region IV-A | Gen. Trias City |  | Luis Y. Ferrer Jr. SHS-Sta. Clara Annex | City of Gen. Trias | 6 | 1 | 2UNITS 4STY20CL | 40 | 121379917.551 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0
K10 | Region IV-A | Imus City | 107986 | Malagasang I Elementary School | IMUS | 3 | 1 | 4STY8CL | 8 | 26873446.9772 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region IV-A | Imus City | 107978 | Pasong Santol Elementary School | IMUS | 3 | 1 | 4STY12CL (L-Type) | 12 | 42578127.1582 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
SHS | Region IV-A | Laguna | 301240 | Famy National High School | FAMY | 4 | 1 | 4STY8CL | 8 | 18378632 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region IV-A | Laguna | 108314 | Tadlac Elementary School | LOS BAÑOS | 2 | 1 | 4STY8CL | 8 | 24445651.725 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region IV-A | Laguna | 108294 | Calumpang ES | LILIW | 3 | 1 | 2STY4CL | 4 | 10113782.192 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region IV-A | Laguna | 108442 | Pagsawitan ES | SANTA CRUZ (Capital) | 4 | 1 | 4STY12CL | 12 | 32754192.6685 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
K10 | Region IV-A | Laguna | 108281 | Talaongan East ES | CAVINTI | 4 | 1 | 4STY12CL | 12 | 31964133.7969 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
K10 | Region IV-A | Lipa City | 500889 | Sen. Claro M. Recto Memorial Integrated School | LIPA CITY | 6 | 1 | 4STY12CL | 12 | 41663900 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
K10 | Region IV-A | Lipa City | 500889 | Sen. Claro M. Recto Memorial Integrated School | LIPA CITY | 6 |  | 4STY8CL | 8 | 24125162.5 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region IV-A | Lipa City | 109641 | Jose K. Obando MES (Antipolo ES) | LIPA CITY | 6 | 1 | 4STY8CL | 8 | 24210375 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region IV-A | Lipa City | 109653 | San Jose ES | LIPA CITY | 6 | 1 | 4STY12CL | 12 | 42245350 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
K10 | Region IV-A | Lipa City | 500781 | Gaudencio B. Lontok Memorial Integrated School | LIPA CITY | 6 | 1 | 4STY8CL | 8 | 24240450 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
SHS | Region IV-A | Lucena City | 308505 | Lucena City NHS - Mayao Parada Extension | LUCENA CITY (Capital) | 2 | 1 | 2STY4CL | 4 | 11759459.8362 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region IV-A | Quezon | 109021 | Balungay ES | PANUKULAN | 1 | 1 | 2STY6CL | 6 | 18892313 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region IV-A | Quezon | 108701 | Batangan ES | General Nakar | 1 | 1 | 2STY4CL | 4 | 13616957.5 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region IV-A | Quezon | 109022 | Bato ES | PANUKULAN | 1 | 1 | 2STY6CL | 6 | 18892313 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region IV-A | Quezon | 108559 | Bongliw ES | Burdeos | 1 | 1 | 2STY6CL | 6 | 20964592.369 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region IV-A | Quezon | 108561 | Burdeos CS | Burdeos | 1 | 1 | 2STY10CL | 10 | 31101560 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
K10 | Region IV-A | Quezon | 109028 | Calasumanga ES | PANUKULAN | 1 | 1 | 2STY6CL | 6 | 18892313 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region IV-A | Quezon | 108706 | Dadyangaw ES | GENERAL NAKAR | 1 | 1 | 1STY4CL | 4 | 10305900.5 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region IV-A | Quezon | 109034 | Libo ES | PANUKULAN | 1 | 1 | 2STY6CL | 6 | 18892313 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
TVL | Region IV-A | Quezon | 308036 | Quezon Science High School | CITY OF TAYABAS | 1 | 1 | 3STY LABORATORY | 3 | 27284941.2275 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region IV-A | Quezon | 108680 | Don Severo Filismino ES | DOLORES | 2 | 1 | 2STY6CL | 6 | 14518089.6223 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region IV-A | Quezon | 109181 | Lutgarda Causapin ES | SARIAYA | 2 | 1 | 2STY6CL | 6 | 14360232.3031 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region IV-A | Quezon | 109191 | San Roque ES | SARIAYA | 2 | 1 | 2STY6CL | 6 | 14729340.4924 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region IV-A | Quezon | 109003 | Dulong Bayan ES | PITOGO | 3 | 1 | 2STY6CL | 6 | 17042488.6116 |  | Ongoing | 20% | 20% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region IV-A | Quezon | 108951 | Ilayang Kinagunan ES | AGDANGAN | 3 | 1 | 2STY4CL | 4 | 12130250 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region IV-A | Quezon | 109127 | Mabunga ES | SAN FRANCISCO (AURORA) | 3 | 1 | 2STY4CL | 4 | 12531250 |  | Ongoing | 18% | 18% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region IV-A | Quezon | 108655 | Macpac ES | CATANAUAN | 3 | 1 | 2STY4CL | 4 | 12531250 |  | Ongoing | 30% | 30% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region IV-A | Quezon | 108658 | Navitas ES | CATANAUAN | 3 | 1 | 2STY4CL | 4 | 12531250 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region IV-A | Quezon | 108659 | San Isidro ES | CATANAUAN | 3 | 1 | 2STY6CL | 6 | 14530824.5602 |  | Ongoing | 20% | 20% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
SHS | Region IV-A | Quezon | 308010 | San Vicente Kanluran NHS | Catanauan | 3 | 1 | 2STY4CL | 4 | 12531250 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region IV-A | Quezon | 108664 | San Vicente Silangan ES | CATANAUAN | 3 | 1 | 2STY4CL | 4 | 12531250 |  | Ongoing | 35% | 35% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region IV-A | Quezon | 108511 | Atimonan Central School Annex | ATIMONAN | 4 | 1 | 4STY16CL | 16 | 43703997.0237 |  | Ongoing | 65% | 65% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
K10 | Region IV-A | Quezon | 108816 | Samat ES | LOPEZ | 4 | 1 | 1STY2CL | 2 | 3808567.685 |  | Ongoing | 55% | 55% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region IV-A | Quezon | 109205 | Kinatakutan ES | TAGKAWAYAN | 4 | 1 | 2STY6CL | 6 | 14272803.3258 |  | Ongoing | 30% | 30% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region IV-A | Quezon | 108607 | Sabang ES | CALAUAG | 4 | 1 | 2STY8CL & 2STY4CL | 12 | 31719803.1334 |  | Ongoing | 25% | 25% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
K10 | Region IV-A | Quezon | 108824 | Vergaña ES | LOPEZ | 4 | 1 | 2STY6CL | 6 | 14272803.3258 |  | Ongoing | 7% | 7% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region IV-A | Rizal | 109396 | Cainta Elementary School | CAINTA | 1 | 1 | 4STY8CL | 8 | 22003064.4549 |  | Ongoing | 5% | 10% | 5% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region IV-A | Rizal | 109372 | Tatala ES | BINANGONAN | 1 | 1 | 4STY8CL | 8 | 21627885.4966 |  | Ongoing | 5% | 10% | 5% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
SHS | Region IV-A | Rizal | 308103 | Abuyod NHS | TERESA | 2 | 1 | 3STY6CL | 6 | 18279860.3166 |  | Ongoing | 5% | 30% | 25% |  |  | 19 DO 0110 | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region IV-A | Rizal | 109472 | Mascap ES | RODRIGUEZ (MONTALBAN) | 2 | 1 | 2STY6CL | 6 | 19795085.2023 |  | Ongoing | 5% | 30% | 25% |  |  | 19 DO 0111 | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region IV-A | Rizal | 301449 | Mascap NHS | RODRIGUEZ (MONTALBAN) | 2 | 1 | 2STY6CL | 6 | 20330429.3751 |  | Ongoing | 5% | 30% | 25% |  |  | 19 DO 0112 | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
SHS | Region IV-A | Rizal | 301452 | Morong National High School - SHS | MORONG | 2 | 1 | 4STY16CL | 16 | 49890715.5996 |  | Ongoing | 5% | 10% | 5% |  |  | 19 DO 0113 | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
K10 | Region IV-A | San Pablo City | 109776 | Sta. Maria Magdalena Elementary School | SAN PABLO CITY | 3 | 1 | 3STY6CL | 6 | 15618970.7217 |  | Ongoing | 25% | 25% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region IV-A | Sta. Rosa City | 108473 | Dita Elementary School | CITY OF SANTA ROSA | 1 | 1 | 4STY8CL | 8 | 25594099.685 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
SHS | Region IV-A | Tanauan City | 321601 | Tanauan City NHS | CITY OF TANAUAN | 3 | 1 | 1STY3CL | 3 | 4511250 |  | Ongoing | 85% | 85% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region IV-A | Tayabas City | 109257 | Malao-Calantas Elementary School | CITY OF TAYABAS | 1 | 1 | 2STY4CL | 4 | 13466582.5 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region IV-B | CALAPAN CITY | 111572 | Sta. Rita ES (Bungahan ES) | CITY OF CALAPAN (Capital) | 1 | 1 | 1STY3CL | 3 | 6175822.0926 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region IV-B | Marinduque | 109895 | Cawit ES | BOAC (Capital) | 0 | 1 | 2STY4CL | 4 | 27211617.786 |  | Under Procurement | 0% | 0% | 0% |  | P00370413LZ | 19EA0103 | 2019-04-09 | 2019-11-09 | 9/23/2019 | [5 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
TVL | Region IV-B | Marinduque | 301557 | Mogpog National Comprehensive High School | MOGPOG | 0 | 1 | 2STY 4 LAB (2 SCI & 2 ICT LAB) | 8 | 37636918.6725 |  | Under Procurement | 0% | 0% | 0% |  | P00370414LZ | 19EA0104 | 2019-04-09 | 2019-11-09 | 9/23/2019 | [5 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region IV-B | Marinduque | 109995 | Santa Cruz North CS (Landy ES) | SANTA CRUZ | 0 | 1 | 2STY4CL | 4 | 27283081.2591 |  | Under Procurement | 0% | 0% | 0% |  | P00370415LZ | 19EA0105 | 2019-04-09 | 2019-11-09 | 9/23/2019 | [5 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
SHS | Region IV-B | Marinduque | 301562 | Sibuyao NHS | TORRIJOS | 0 | 1 | 3STY6CL | 6 | 14743773.6654 |  | Under Procurement | 0% | 0% | 0% |  | P00370616LZ | 19EA0106 | 2019-04-09 | 2019-11-09 | 9/23/2019 | [5 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region IV-B | Occidental Mindoro | 110046 | Hebron Min. Sch. | ABRA DE ILOG | 0 | 1 | 1STY5CL | 5 | 10293036.821 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
K10 | Region IV-B | Oriental Mindoro | 110465 | Cabuyao PS | MANSALAY | 2 | 1 | 1STY4CL | 4 | 8234429.4568 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region IV-B | Oriental Mindoro | 110561 | Natividad De Joya MS (Guinhawa) | PINAMALAYAN | 2 | 1 | 1STY2CL | 2 | 4117214.7284 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region IV-B | Oriental Mindoro | 110580 | Pambisan Munti ES | PINAMALAYAN | 2 | 1 | 1STY3CL | 3 | 4141496.9125 |  | Ongoing | 3% | 3% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region IV-B | Oriental Mindoro | 110477 | Sta. Brigida ES | MANSALAY | 2 | 1 | 1STY2CL | 2 | 4117214.7284 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region IV-B | Puerto Princesa City | 111483 | Labtay ES - Pagasa Ext. * | Puerto Princesa City | 3 | 1 | 1STY3CL | 3 | 6175822.0926 |  | Ongoing | 25% | 25% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
SHS | Region IV-B | Romblon | 301747 | Alcantara NHS | ALCANTARA | 0 | 1 | 2STY4CL | 4 | 13616957.5 |  | Ongoing | 0% | 30% | 30% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region IX | Dapitan City | 125960 | Sicayab ES | DAPITAN CITY | 1 | 1 | 2STY4CL | 4 | 13616957.5 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region IX | Dipolog City | 125976 | Sta. Filomena ES | Dipolog City | 2 | 1 | 3STY9CL | 9 | 25203542.1561 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
TVL | Region IX | Isabela City | 198004 | Ajibon ES | CITY OF ISABELA (Capital) | 0 | 1 | 2STY2LAB | 2 | 4117214.7284 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region IX | Pagadian City | 126056 | Tulawas ES | PAGADIAN CITY (Capital) | 1 | 1 | 2STY6CL | 6 | 16242649.0993 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region IX | Zamboanga City | 126145 | Pamucutan ES | ZAMBOANGA CITY | 1 | 1 | 2STY4CL | 4 | 11445595.9032 |  | Ongoing | 95% | 95% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region IX | Zamboanga City | 126223 | Arena Blanco East ES | ZAMBOANGA CITY | 2 | 1 | 3STY6CL | 6 | 14743773.6654 |  | Ongoing | 70% | 70% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region IX | Zamboanga City | 126197 | Boalan ES | ZAMBOANGA CITY | 2 | 1 | 2UNITS 2STY10CL | 20 | 55532309.5926 |  | Ongoing | 50% | 50% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
K10 | Region IX | Zamboanga City | 126189 | Mercedes CS | ZAMBOANGA CITY | 2 | 1 | 4STY20CL | 20 | 52046376.9036 |  | Ongoing | 50% | 50% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0
K10 | Region IX | Zamboanga City | 126169 | Poso ES | ZAMBOANGA CITY | 2 | 1 | 2STY6CL | 6 | 16242649.0993 |  | Ongoing | 50% | 50% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region IX | Zamboanga del Norte | 124575 | Lingasad ES | POLANCO | 1 | 1 | 2STY4CL | 4 | 13616957.5 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region IX | Zamboanga del Norte | 124531 | San Antonio ES | MANUKAN | 2 | 1 | 1STY2CL | 2 | 4117214.7284 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region IX | Zamboanga del Sur | 314254 | Baclay Ext. TTVHS | TUKURAN | 1 | 1 | 1STY2CL | 2 | 4117214.7284 |  | Ongoing | 45% | 60% | 15% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region IX | Zamboanga del Sur | 124893 | Commonwealth CS with SPED Classes | AURORA | 1 | 1 | 2STY10CL | 10 | 24144478.3893 |  | Ongoing | 37% | 47% | 10% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0
K10 | Region IX | Zamboanga del Sur | 124895 | La Victoria PS | AURORA | 1 | 1 | 1STY2CL | 2 | 4117214.7284 |  | Ongoing | 40% | 90% | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region IX | Zamboanga del Sur |  | Lower Bayao ES | TUKURAN | 1 | 1 | 1STY2CL | 2 | 4117214.7284 |  | Ongoing | 45% | 95% | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region IX | Zamboanga del Sur |  | Tagulo ES | TUKURAN | 1 | 1 | 1STY2CL | 2 | 4117214.7284 |  | Ongoing | 35% | 60% | 25% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region IX | Zamboanga del Sur | 124978 | Proper Dimaya ES | DINAS | 2 | 1 | 2STY4CL | 4 | 10674931.3765 |  | Ongoing | 30% | 30% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region IX | Zamboanga del Sur | 314251 | San Pablo NHS - Sacbulan Extension | SAN PABLO | 2 | 1 | 1STY2CL W/ TOILET | 2 | 3384182.2472 |  | Ongoing | 28% | 28% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region IX | Zamboanga del Sur | 125173 | Tabon ES | LAPUYAN | 2 | 1 | 1STY2CL W/ TOILET | 2 | 3222137.666 |  | Ongoing | 33% | 33% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
SHS | Region IX | Zamboanga Sibugay | 303829 | Buug National High School | BUUG | 1 | 1 | 2STY4CL | 4 | 13616957.5 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
SHS | Region IX | Zamboanga Sibugay | 303828 | Diplahan National High School | DIPLAHAN | 1 | 1 | 2STY4CL | 4 | 13616957.5 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region IX | Zamboanga Sibugay | 125654 | Sanghanan ES | KABASALAN | 2 | 1 | 1STY4CL | 4 | 8234429.4568 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
SHS | Region IX | Zamboanga Sibugay | 303854 | Zamboanga Sibugay NHS | IPIL | 2 | 1 | 2STY4CL | 4 | 13616957.5 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region V | Albay | 111585 | Basud Elementary School | BACACAY | 1 | 1 | 1STY2CL | 2 | 2781949.0488 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region V | Albay | 111603 | Bayandong Elementary School | BACACAY | 1 | 1 | 1STY3CL | 3 | 4223610.5146 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region V | Albay | 111680 | Anislag Elementary School | Daraga (Locsin) | 2 | 1 | 3STY12CL | 12 | 45408618.45 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
K10 | Region V | Albay | 111662 | Binitayan Elementary School | Daraga (Locsin) | 2 | 1 | 3STY9CL | 9 | 42544988.2275 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
SHS | Region V | Albay | 301846 | Cawayan High School | MANITO | 2 | 1 | 2STY4CL | 4 | 16913981.505 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
SHS | Region V | Albay | 301822 | Cotmon National High School | CAMALIG | 2 | 1 | 4STY12CL | 12 | 46078597.22 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
SHS | Region V | Albay | 301825 | Daraga National High School | DARAGA (LOCSIN) | 2 | 1 | 4STY12CL | 12 | 62409892.6425 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
K10 | Region V | Albay | 111667 | Daraga North Central School | DARAGA (LOCSIN) | 2 | 1 | 4STY16CL | 16 | 69938443.0825 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
SHS | Region V | Albay | 301823 | Ilawod National High School | CAMALIG | 2 | 1 | 4STY20CL | 20 | 55948459.3425 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
SHS | Region V | Albay | 309518 | Kilicao High School | Daraga (Locsin) | 2 | 1 | 4STY20CL | 20 | 59339411.5825 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
K10 | Region V | Albay | 112036 | Mancao Elementary School | RAPURAPU | 2 | 1 | 2STY4CL | 4 | 14350841.9358 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region V | Legaspi City | 114475 | Bitano Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 2STY4CL ATTACHED | 4 | 11002039.8584 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
SHS | Region V | Albay | 301845 | Manito National High School | MANITO | 2 | 1 | 4STY20CL | 20 | 61255829.68 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
K10 | Region V | Legaspi City | 114463 | Mariawa Elementary School | LEGAZPI CITY | 2 | 1 | 1STY2CL | 2 | 4998265.1216 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
TVL | Region V | Albay | 301839 | Malapay High School | PIO DURAN | 3 | 1 | 2STY4CL (2reg ws) | 2 | 13048441.5144 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
TVL | Region V | Albay | 301864 | Pio Duran National High School | PIO DURAN | 3 | 1 | 4STY8CL (6sci,4shs) | 6 | 22806444.5967 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region V | Camarines Norte | 112216 | Malatap ES | LABO | 1 | 1 | 2STY4CL | 4 | 15555779.6279 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region V | Camarines Norte | 112260 | Tugos ES | PARACALE | 1 | 1 | 2STY4CL | 4 | 13819427.1719 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region V | Camarines Norte | 112307 | Juanita Balon ES | VINZONS | 2 | 1 | 2STY4CL | 4 | 13344394.6923 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
TVL | Region V | Camarines Sur | 301942 | Barcelonita Fisheries School | CABUSAO | 1 | 1 | 3storey - 2 Regular, 2 science lab, 2 ICT | 6 | 53084410.3657 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region V | Camarines Sur | 112789 | Antipolo ES | MINALABAC | 2 | 1 | 1STY2CL | 2 | 2640396.6002 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region V | Camarines Sur | 112790 | Bagolatao ES | MINALABAC | 2 | 1 | 1STY2CL | 2 | 2752705.011 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region V | Camarines Sur | 112868 | Cagbunga ES | PAMPLONA | 2 | 1 | 1STY2CL | 2 | 2845576.5509 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region V | Camarines Sur | 112877 | San Vicente ES | PAMPLONA | 2 | 1 | 1STY2CL | 2 | 2659833.4712 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
SHS | Region V | Camarines Sur | 301952 | Calabanga NHS | CALABANGA | 3 | 1 | 4STY24CL | 24 | 62537498.8825 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0
K10 | Region V | Camarines Sur | 112770 | Sta. Lucia ES | MAGARAO | 3 | 1 | 3STY9CL | 9 | 43216033.036 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
K10 | Region V | Camarines Sur | 112986 | Odiongan ES | SAGÑAY | 4 | 1 | 2STY4CL | 4 | 11792333.1947 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region V | Camarines Sur | 113028 | San Jose CS | SAN JOSE | 4 | 1 | 2STY6CL | 6 | 15582864.3609 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region V | Camarines Sur | 113045 | Siruma Central School | SIRUMA | 4 | 1 | 2STY4CL | 4 | 11782308.1947 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region V | Camarines Sur | 113150 | Tierra Nevada Elementary School | TINAMBAC | 4 | 1 | 2STY4CL | 4 | 11891951.6197 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
TVL | Region V | Iriga City | 302251 | Rinconada National Technical Vocational School | IRIGA CITY | 5 | 1 | 1unit 3sty (1Reg, 1Science & 1ICT Lab) | 3 | 14388219.0555 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region V | Legaspi City | 114466 | Bagumbayan Central School | LEGAZPI CITY (Capital) | 2 | 1 | 4STY16CL | 16 | 68681760.21 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
K10 | Region V | Legaspi City | 114477 | Cabagnan ES | LEGAZPI CITY (Capital) | 2 | 1 | 4STY12CL | 12 | 59439248.5525 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
K10 | Region V | Legaspi City | 114478 | Dapdap Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 2STY8CL | 8 | 23197709.65 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
SHS | Region V | Legaspi City | 310202 | Legazpi City Science High School | LEGAZPI CITY (Capital) | 2 | 1 | 4STY12CL | 12 | 57993386.9125 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
SHS | Region V | Legaspi City | 302263 | Pawa High School | LEGAZPI CITY (Capital) | 2 | 1 | 3STY12CL | 12 | 49187041.9525 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
SHS | Region V | Legaspi City | 500169 | Taysan Resettlement Integrated School | LEGAZPI CITY (Capital) | 2 | 1 | 4STY12CL | 12 | 46428990.0175 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
TVL | Region V | Ligao City | 301820 | Deogracias P. Princesa Memorial HS | CITY OF LIGAO | 3 | 1 | 2STY4CL (2units sci) | 2 | 11815366.5144 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
SHS | Region V | Masbate | 302176 | Verdida-Sabrido NHS | PLACER | 3 | 1 | 2STY8CL | 8 | 26685440.2325 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
SHS | Region V | Sorsogon | 302186 | Biriran NHS | JUBAN | 2 | 1 | 2STY8CL | 8 | 25062500 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
TVL | Region V | Sorsogon | 302211 | Gabao NHS | IROSIN | 2 | 1 | 3STY12CL (2reg,2sci,2ict) | 6 | 36974934.1784 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
TVL | Region V | Sorsogon | 302214 | Gubat National High School | GUBAT | 2 | 1 | 2STY8CL (2sci,2ict) | 4 | 23733306.3626 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
SHS | Region V | Sorsogon | 302214 | Gubat National High School | GUBAT | 2 |  | 4STY16CL | 16 | 45590437.5542 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0
TVL | Region V | Sorsogon | 302237 | San Francisco NHS | BULAN | 2 | 1 | 2STY6CL (1reg,1sci,2shs) | 4 | 16627787.8952 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
SHS | Region V | Sorsogon | 302242 | San Roque NHS | BULUSAN | 2 | 1 | 3STY12CL | 12 | 45408618.45 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
K10 | Region V | Sorsogon City | 114554 | Bibincahan Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 2STY6CL | 6 | 20350750 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region V | Sorsogon City | 114582 | Ticol Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3STY6CL | 6 | 18046901.7024 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region V | Tabaco City | 114597 | Quinastillojan ES | CITY OF TABACO | 1 | 1 | 1STY3CL | 3 | 3999565.2181 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
SHS | Region VI | Antique | 310707 | Gov. Evelio B. Javier MNHS | SAN REMIGIO | 0 | 1 | 2UNITS 1STY2CL W/ TOILET | 4 | 10627207.2136 |  | Under Procurement | 0% | 0% | 0% | 1st Bidding Failed. For Re-bidding | [10 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VI | Antique | 114943 | Igpalge ES | ANINI-Y | 0 | 1 | 3UNITS 1STY3CL | 9 | 11624773.44 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0
K10 | Region VI | Antique | 178517 | Ilaures Elementary School | BUGASONG | 0 | 1 | 1STY3CL W/ TOILET | 3 | 7293455.8492 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region VI | Bago City | 117511 | Alianza Elementary School | BAGO CITY | 4 | 1 | 1STY2CL | 2 | 4950531.9261 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VI | Capiz | 115611 | Agbalo ES | PANAY | 1 | 1 | 2STY4CL | 4 | 13553595.2093 |  | Ongoing | 35% | 35% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region VI | Capiz | 115642 | Agloway PS | PANITAN | 1 | 1 | 2STY8CL | 8 | 21773965.2051 |  | Ongoing | 35% | 35% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region VI | Capiz | 115642 | Agloway PS | PANITAN | 1 |  | 2STY6CL | 6 | 17493355.7085 |  | Ongoing | 25% | 25% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region VI | Capiz | 115640 | Antonio Belo Memorial ES | PANITAN | 1 | 1 | 2STY4CL | 4 | 13348083.7118 |  | Ongoing | 35% | 35% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region VI | Capiz | 115761 | Matangcong PS | SIGMA | 2 | 1 | 2STY4CL | 4 | 13325737.676 |  | Ongoing | 35% | 35% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region VI | Capiz | 115745 | Sapian Elementary School | SAPI-AN | 2 | 1 | 3STY15CL | 15 | 42004466.9341 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0
K10 | Region VI | Capiz | 115819 | Tapaz CES | TAPAZ | 2 | 1 | 2STY4CL | 4 | 11312057.9107 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region VI | Capiz | 115819 | Tapaz CES | TAPAZ | 2 |  | 2STY6CL | 6 | 18075614.8964 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region VI | Capiz | 115412 | Angub Elementary School | CUARTERO | 2 | 1 | 2STY6CL | 6 | 18075614.8964 |  | Ongoing | 20% | 20% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
SHS | Region VI | Escalante City | 311106 | Escalante NHS - Dr. Floro T. Bongco Mem. Ext. | CITY OF ESCALANTE | 1 | 1 | 2STY8CL | 8 | 21271534.0395 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region VI | Iloilo | 116721 | Balbino Seron Elementary School | SAN JOAQUIN | 1 | 1 | 1STY4CL | 4 | 10002793.8932 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VI | Iloilo | 116721 | Balbino Seron Elementary School | SAN JOAQUIN | 1 |  | 1STY4CL | 4 | 10002793.8932 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
SHS | Region VI | Iloilo | 302508 | Igtalongon NHS | IGBARAS | 1 | 1 | 1STY3CL | 3 | 7408102.892 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
SHS | Region VI | Iloilo | 311011 | Adriano Cabardo NHS | ALIMODIAN | 2 | 1 | 1STY2CL | 2 | 4345082.9283 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VI | Iloilo | 116444 | Bagongbong ES | LAMBUNAO | 3 | 1 | 1STY2CL | 2 | 2992159.745 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VI | Iloilo | 116142 | Guibuangan Elementary School | CABATUAN | 3 | 1 | 1STY3CL | 3 | 4295943.075 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
SHS | Region VI | Iloilo | 302534 | Mostro NHS | ANILAO | 4 | 1 | 2STY4CL | 4 | 8882732.4525 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VI | Iloilo | 116092 | Batad CES | BATAD | 5 | 1 | 2STY6CL | 6 | 12300321.7892 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
TVL | Region VI | Iloilo City | 302744 | Jaro National High School | ILOILO CITY (Capital) | 0 | 1 | 3STY REG. WORKSHOP | 3 | 24920145 |  | Ongoing | 0% | 20% | 20% | Suspended as of September 27, 2019 (Pending issuance of building Permit | [10 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region VI | La Carlota City | 117635 | Ferlou ES | LA CARLOTA CITY | 4 | 1 | 1STY2CL | 2 | 4975662.145 |  | Ongoing | 55% | 55% | 0% | AVAILABILITY OF MATERIALS IN THE MARKET ACCORDING TO THE DPWH AND CONTRACTOR FOR THE TRUSS MEMBERS AND OTHER MATERIALS |  | 19GN0097 | 2019-07-31 | 2019-08-07 | 2019-08-19 |  | 2019-09-12 | SBK CONTRUCTION SUPPLIES AND SERVICES | 2019-12-05 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
SHS | Region VI | Negros Occidental | 302658 | Labilabi NHS | TOBOSO | 1 | 1 | 1STY2CL | 2 | 5058147.5443 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VI | Negros Occidental | 117418 | Toboso CS | TOBOSO | 1 | 1 | 2STY10CL | 10 | 20085370.5058 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
K10 | Region VI | Negros Occidental | 117017 | Alacaygan ES | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 1STY2CL W/ TOILET | 2 | 3344836.3377 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
SHS | Region VI | Negros Occidental | 302588 | Barangay Alegria NHS | MURCIA | 3 | 1 | 2STY6CL with Water System | 6 | 14656760.545 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region VI | Negros Occidental | 117025 | E. B. Magalona ES | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 2STY10CL | 10 | 20085370.3153 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
K10 | Region VI | Negros Occidental | 117028 | Jose M. Consing Memorial School | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 2STY4CL with Water System | 4 | 15748290.9761 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VI | Negros Occidental | 117031 | Nanca Elementary School | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 2STY10CL | 10 | 20085370.5058 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
K10 | Region VI | Negros Occidental | 117299 | Cambarus ES | PONTEVEDRA | 4 | 1 | 1STY2CL W/ TOILET | 2 | 4958511.2247 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VI | Negros Occidental | 117341 | Don Vicente Lopez ES | SAN ENRIQUE | 4 | 1 | 2STY10CL | 10 | 20085370.3153 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
K10 | Region VI | Negros Occidental | 117305 | Recreo ES | PONTEVEDRA | 4 | 1 | 2STY10CL | 10 | 20085370.5158 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
K10 | Region VI | Negros Occidental | 117232 | Don Felix Robles ES | LA CASTELLANA | 5 | 1 | 1STY4CL | 4 | 5571588.235 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VI | Passi City | 117898 | Bagacay Elementary School | CITY OF PASSI | 4 | 1 | 1STY3CL W/ TOILET | 3 | 6270144.27 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
SHS | Region VI | Roxas City | 500195 | Sofronio A. Cordovero Integrated School | ROXAS CITY (Capital) | 1 | 1 | 2STY4CL | 4 | 13192696.2118 |  | Under Procurement | 0% | 0% | 0% |  |  | 19GD0098 |  | 2019-07-31 | 2019-08-14 | [5 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VI | Sagay City | 117717 | Hautea Elementary School | SAGAY CITY | 2 | 1 | 1STY3CL | 3 | 5223570.1395 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region VI | Silay City | 117801 | Don Eustaquio Hofilena Mem.Elem. School | SILAY CITY | 3 | 1 | 1STY2CL | 2 | 3244586.3377 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VII | Bayawan City | 120121 | Bahian E/S | CITY OF BAYAWAN (TULONG) | 3 | 1 | 1STY2CL W/ TOILET ATTACHED | 2 | 2509551.1824 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
TVL | Region VII | Bayawan City | 303217 | Basay National High School | BASAY | 3 | 1 | 4STY8LAB (4 Reg. Workshop, 2 SCI LAB, 2 ICT) | 8 | 39416104.9561 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region VII | Bayawan City | 120128 | Dawis Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2STY6CL | 6 | 15901486.5599 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region VII | Bayawan City | 120153 | Hag-um Primary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 1STY2CL | 2 | 4362400.1032 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
SHS | Region VII | Bogo City | 500408 | Don Celestino Martinez Sr. Taytayan IS | CITY OF BOGO | 4 | 1 | 2STY4CL | 4 | 9791535.6045 |  | Ongoing | 55% | 55% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region VII | Bohol | 118696 | Abucay ES | SIKATUNA | 1 | 1 | 1STY3CL | 3 | 7200957.5 |  | Ongoing | 50% | 50% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region VII | Bohol | 118555 | Bolod ES | PANGLAO | 1 | 1 | 1STY3CL | 3 | 7164667 |  | Ongoing | 35% | 35% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region VII | Bohol | 118560 | Lourdes ES | PANGLAO | 1 | 1 | 1STY3CL | 3 | 7118351.5 |  | Ongoing | 35% | 35% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region VII | Bohol | 118562 | Panglao Central ES | PANGLAO | 1 | 1 | 2STY4CL | 4 | 10454982.275 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region VII | Bohol | 118564 | Tawala ES | PANGLAO | 1 | 1 | 1STY2CL | 2 | 5112810.15 |  | Ongoing | 35% | 35% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VII | Bohol | 118039 | Sagasa ES | BIEN UNIDO | 2 | 1 | 1STY2CL | 2 | 2988873.4698 |  | Ongoing | 35% | 35% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VII | Bohol | 118723 | San Agustin Elementary School | TALIBON | 2 | 1 | 1STY2CL | 2 | 2817025 |  | Ongoing | 75% | 75% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VII | Bohol | 118723 | San Agustin Elementary School | TALIBON | 2 |  | 1STY2CL | 2 | 3402827.855 |  | Ongoing | 80% | 80% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VII | Bohol | 118277 | Lapsaon ES | DIMIAO | 3 | 1 | 1STY2CL | 2 | 4272098.9634 |  | Ongoing | 50% | 50% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VII | Bohol | 118858 | Omjon ES | VALENCIA | 3 | 1 | 1STY2CL | 2 | 4390167.0976 |  | Ongoing | 55% | 55% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VII | Bohol | 186501 | Pagahat ES | ALICIA | 3 | 1 | 1STY2CL | 2 | 4096105.3566 |  | Ongoing | 18% | 18% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VII | Bohol | 118023 | Quirino PS | BATUAN | 3 | 1 | 1STY2CL | 2 | 4390167.0976 |  | Ongoing | 18% | 18% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VII | Bohol | 117964 | Talisay PS | ANDA | 3 | 1 | 1STY4CL | 4 | 7422886.8899 |  | Ongoing | 40% | 40% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region VII | Carcar City | 500726 | Puesto Integrated School | CITY OF CARCAR | 1 | 1 | 2STY4CL | 4 | 12899852.9694 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region VII | Cebu | 119472 | Bacay ES | MINGLANILLA | 1 | 1 | 4STY12CL | 12 | 42401040.6961 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
K10 | Region VII | Cebu | 118917 | Argao I Central ES | ARGAO | 2 | 1 | 2STY8CL | 8 | 22343418.2475 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region VII | Cebu | 119316 | Casay ES | DALAGUETE | 2 | 1 | 2STY4CL | 4 | 13627365.455 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VII | Cebu | 119303 | Libo PS | DALAGUETE | 2 | 1 | 2STY4CL | 4 | 12542361.5095 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VII | Cebu | 119322 | Malones Elementary School | DALAGUETE | 2 | 1 | 2STY4CL | 4 | 12391986.5095 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VII | Cebu | 119561 | Lamac ES | PINAMUNGAHAN | 3 | 1 | 4STY12CL | 12 | 39448812.1602 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
SHS | Region VII | Cebu | 302963 | Paypay NHS | DAANBANTAYAN | 4 | 1 | 3STY10CL | 10 | 30567091.6612 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
K10 | Region VII | Cebu | 119409 | Ernesto V. Veloso ES (Cabadiangan ES) | LILOAN | 5 | 1 | 2STY4CL | 4 | 9552777.9489 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VII | Cebu | 119862 | Secante Bag-o PS | TUDELA | 5 | 1 | 2STY6CL | 6 | 12238899.9275 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region VII | Cebu | 119422 | Tiltilon ES | LILOAN | 5 | 1 | 4STY12CL | 12 | 33384584.508 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
K10 | Region VII | Cebu | 119247 | Polog ES | CONSOLACION | 6 | 1 | 1STY2CL | 2 | 4178445.8144 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VII | Cebu | 118998 | Basiao PS | BADIAN | 7 | 1 | 1STY2CL | 2 | 4106081.3042 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VII | Cebu | 118998 | Basiao PS | BADIAN | 7 |  | 1STY2CL | 2 | 4106081.3042 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VII | Cebu City | 119872 | Cambinocot ES | CEBU CITY (Capital) | 1 | 1 | 4STY8CL | 8 | 24130195.2605 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region VII | Cebu City | 119869 | Sinsin ES | CEBU CITY (Capital) | 2 | 1 | 3STY6CL | 6 | 20265495.2246 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region VII | City of Naga, Cebu | 302929 | Balirong National High School | CITY OF NAGA | 1 | 1 | 2STY4CL | 4 | 13311193.1654 |  | Ongoing | 35% | 70% | 35% |  |  | 19-HE-0103 | JULY 26-AUGUST 14, 2019 | 2019-08-02 | 2019-08-14 | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
SHS | Region VII | Danao City | 322001 | Ubaldo Iway Memo. NHS | DANAO CITY | 5 | 1 | 2STY6CL | 6 | 11656095.169 |  | Ongoing | 0% | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region VII | Guihulngan City |  | Binobohan HS | CITY OF GUIHULNGAN | 1 | 1 | 2STY6CL | 6 | 16295464.2279 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region VII | Guihulngan City | 120271 | Kapudlusan PS | CITY OF GUIHULNGAN | 1 | 1 | 1STY3CL W/ TOILET | 3 | 5293200 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region VII | Guihulngan City | 189509 | Mandi-i ES | CITY OF GUIHULNGAN | 1 | 1 | 1STY2CL | 2 | 4411000 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
SHS | Region VII | Mandaue City | 303194 | Cabancalan NHS | MANDAUE CITY | 6 | 1 | 4STY8CL | 8 | 18426169.347 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region VII | Negros Oriental | 120320 | La Libertad CES | LA LIBERTAD | 1 | 1 | 4STY16CL | 16 | 43641963.9779 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
K10 | Region VII | Negros Oriental | 120049 | Mabato ES | Ayungon | 1 | 1 | 1STY3CL W/ TOILET | 3 | 5293200 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region VII | Negros Oriental | 120052 | Nabhang ES | AYUNGON | 1 | 1 | 1STY2CL W/ TOILET | 2 | 4451100 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VII | Negros Oriental | 120592 | Nabilog Elementary School | TAYASAN | 1 | 1 | 3UNITS 1STY3CL | 9 | 15047108.9224 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
K10 | Region VII | Negros Oriental | 120341 | BANBAN ELEMENTARY SCHOOL | MABINAY | 2 | 1 | 1STY2CL | 2 | 3428791.6827 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VII | Negros Oriental | 120342 | Barang-barang Primary School | MABINAY | 2 | 1 | 1STY3CL | 3 | 5301439.4573 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
TVL | Region VII | Negros Oriental | 303224 | Apolinar B. Macias Memorial High School | DAUIN | 3 | 1 | 4STY4 lab (2 sci-lab, 2 ICT) | 4 | 17734607.173 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VII | Negros Oriental | 120507 | Cawitan Elementary School | SANTA CATALINA | 3 | 1 | 1STY2CL W/ TOILET | 2 | 3905461.305 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
TVL | Region VII | Negros Oriental | 303263 | Don Emilio Macias MNHS (San Francisco NHS) | SANTA CATALINA | 3 | 1 | 4STY4 lab (2 reg workshop, 1 sci-lab, 1 ICT) | 4 | 17630490.1095 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VII | Negros Oriental | 120459 | Felipe Tayko MCES | SIATON | 3 | 1 | 2STY6CL | 6 | 11785558.4401 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region VII | Negros Oriental | 120461 | Inalad Elementary School | SIATON | 3 | 1 | 2STY6CL | 6 | 14329571.9133 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
TVL | Region VII | Negros Oriental | 303267 | Ong Che Tee - Bacong HS | BACONG | 3 | 1 | 4STY4 lab (4 reg workshop, 2 ICT) | 4 | 17603469.5967 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
TVL | Region VII | Negros Oriental | 361077 | Pulangbato National Senior High School | VALENCIA (LUZURRIAGA) | 3 | 1 | 4STY6 lab (2 reg workshop, 2 sci-lab, 2 ICT, 4CL) | 10 | 38548062.7924 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
TVL | Region VII | Siquijor | 303303 | BASAC NATIONAL HIGH SCHOOL | LARENA | 0 | 1 | 1 unit, 2 Sty, Science Lab. Bldg | 2 | 14028697.4128 |  | Ongoing | 5% | 5% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
SHS | Region VII | Siquijor | 500232 | Cabulihan Integrated School | LARENA | 0 | 1 | 1STY2CL | 2 | 3090863.2083 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VII | Siquijor | 120698 | Cantabon Elementary School | SIQUIJOR (Capital) | 0 | 1 | 2STY6CL | 6 | 14950657.5252 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region VII | Siquijor | 120662 | New Corregidor Elementary School | LARENA | 0 | 1 | 1STY2CL | 2 | 3030349.5013 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
SHS | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1 | 1 | 1STY2CL | 2 | 4535390.6511 |  | Ongoing | 6% | 6% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VII | Toledo City | 120745 | Ibo Elementary School | TOLEDO CITY | 3 | 1 | 3STY9CL | 9 | 28260329.3067 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
K10 | Region VIII | Baybay | 121097 | Biasong Elementary School | Baybay | 5 | 1 | 1STY2CL | 2 | 4678614.7284 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Biliran | 120860 | Naval CS | NAVAL (Capital) | 0 | 1 | 1STY2CL | 2 | 3125637.6075 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Biliran | 120862 | Sabang ES | NAVAL (Capital) | 0 | 1 | 1STY2CL | 2 | 2957938.5454 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Borongan City | 122368 | Amantacop ES | CITY OF BORONGAN (Capital) | 0 | 1 | 1STY2CL | 2 | 4551350 |  | Ongoing | 90% | 90% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VIII | Calbayog City | 500749 | Tomaligues Integrated School | CALBAYOG CITY | 1 | 1 | 2STY4CL | 4 | 12107757.0579 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VIII | Catbalogan City | 123415 | Majaba Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | 1STY2CL | 2 | 4438678.2932 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Eastern Samar | 122634 | Bantayan Elementary School | ORAS | 0 | 1 | 1STY2CL | 2 | 4513255 |  | Ongoing | 87% | 87% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VIII | Eastern Samar | 122659 | Buntay Elementary School | ORAS | 0 | 1 | 1STY2CL | 2 | 4957362.5 |  | completed | 100% | 100% | 0% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2
K10 | Region VIII | Eastern Samar | 122738 | Cajagwayan Elementary School | SAN POLICARPO | 0 | 1 | 1STY2CL | 2 | 4483180 |  | Ongoing | 82% | 82% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VIII | Eastern Samar | 122415 | Cansangaya Elementary School | CAN-AVID | 0 | 1 | 1STY2CL | 2 | 4729795 |  | Ongoing | 79% | 79% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VIII | Eastern Samar | 192508 | Dacul Primary School | TAFT | 0 | 1 | 1STY2CL | 2 | 4419020 |  | Ongoing | 84% | 84% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VIII | Eastern Samar | 122451 | Dapdap Central Elementary School | DOLORES | 0 | 1 | 1STY2CL | 2 | 4801975 |  | Ongoing | 77% | 77% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VIII | Eastern Samar | 122431 | Del Pilar Elementary School | DOLORES | 0 | 1 | 1STY2CL | 2 | 5195957.5 |  | Ongoing | 69% | 69% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VIII | Eastern Samar | 122510 | Giporlos Central School | GIPORLOS | 0 | 1 | 1STY2CL | 2 | 4773905 |  | Ongoing | 76% | 76% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VIII | Eastern Samar | 122739 | Japunan Elementary School | SAN POLICARPO | 0 | 1 | 1STY3CL | 3 | 6178407.5 |  | Ongoing | 79% | 79% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region VIII | Eastern Samar | 313512 | Quinapundan National High School- Anislag Annex | QUINAPONDAN | 0 | 1 | 1STY2CL | 2 | 4709745 |  | Ongoing | 59% | 59% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VIII | Eastern Samar | 122742 | San Policarpo Central Elementary School | SAN POLICARPO | 0 | 1 | 1STY3CL | 3 | 6168382.5 |  | Ongoing | 68% | 68% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region VIII | Leyte | 120978 | San Francisco West Elementary School | ALANGALANG | 1 | 1 | 1STY3CL | 3 | 6360225.8123 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region VIII | Leyte | 120982 | Santol Elementary School | ALANGALANG | 1 | 1 | 1STY2CL | 2 | 4109000.2634 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Leyte | 121311 | Calutan Primary School | DAGAMI | 2 | 1 | 1STY2CL | 2 | 3550855 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Leyte | 191529 | Gen. Luna Elementary School | MACARTHUR | 2 | 1 | 1STY2CL | 2 | 3395467.5 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Leyte | 121245 | Manloy Elementary School | CAPOOCAN | 2 | 1 | 1STY2CL | 2 | 3884888 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Leyte | 121611 | Tinocdugan Elementary School | LEYTE | 3 | 1 | 1STY2CL | 2 | 2650780.3949 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Leyte | 121788 | Cangcosme Elementary School | PALOMPON | 4 | 1 | 1STY2CL | 2 | 3929800 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Leyte | 121633 | Higmamara ES | MAHAPLAG | 5 | 1 | 1STY2CL | 2 | 4548289.7284 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Leyte | 121390 | Pontod ES | HILONGOS | 5 | 1 | 2STY8CL | 8 | 22933822.8081 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region VIII | Leyte | 121075 | Tabunuk ES | BATO | 5 | 1 | 1STY3CL | 3 | 6525694.5926 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region VIII | Maasin City | 122172 | San Agustin MGS | CITY OF MAASIN (Capital) | 0 | 1 | 1STY3CL | 3 | 8820121.6258 |  | Ongoing | 20% | 20% | 0% |  |  | 19IL0085 |  |  | 2019-08-27 |  |  | CEAN CONSTRUCTION | 2020-01-04 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region VIII | Northern Samar | 122872 | Nazareno ES | CATARMAN (CAPITAL) | 1 | 1 | 1STY3CL | 3 | 7103644.5142 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region VIII | Northern Samar | 122852 | Trangue ES | CATARMAN (CAPITAL) | 1 | 1 | 1STY3CL | 3 | 7302812.1216 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region VIII | Northern Samar | 123142 | Binay ES | PALAPAG | 2 | 1 | 1STY3CL | 3 | 6484613.1952 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region VIII | Northern Samar | 123010 | Dapdap ES | LAS NAVAS | 2 | 1 | 1STY3CL | 3 | 6546371.4157 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region VIII | Northern Samar | 123238 | Ginagdanan ES | SAN ROQUE | 2 | 1 | 1STY3CL | 3 | 6791667.5468 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region VIII | Northern Samar | 122984 | Palmera ES | LAOANG | 2 | 1 | 1STY4CL | 4 | 9057872.4005 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VIII | Northern Samar | 123177 | Pambujan II CS | PAMBUJAN | 2 | 1 | 1STY4CL | 4 | 8975528.2034 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VIII | Ormoc City | 124202 | Cabintan Elementary School | ORMOC CITY | 4 | 1 | 1STY2CL | 2 | 3929800 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Ormoc City | 124163 | Maglahug Elementary School | ORMOC CITY | 4 | 1 | 1STY2CL | 2 | 3879675 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123285 | Almagro CS | ALMAGRO | 1 | 1 | 2STY4CL | 4 | 8968266.5144 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123831 | Bahay ES | TARANGNAN | 1 | 1 | 1STY2CL | 2 | 4518214.7284 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123831 | Bahay ES | TARANGNAN | 1 |  | 1STY1CL | 1 | 2309232.3642 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 313737 | Apolonia Integrated School | PARANAS (WRIGHT) | 2 | 1 | 2STY6CL | 6 | 20303988.7183 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123440 | Arawane ES | DARAM | 2 | 1 | 1STY2CL | 2 | 4382062.0255 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123357 | Bacyaran Elementary School | CALBIGA | 2 | 1 | 2STY4CL | 4 | 12681391.1669 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123359 | Beri Elementary School | CALBIGA | 2 | 1 | 1STY3CL | 3 | 6672169.8676 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123361 | Borong ES | CALBIGA | 2 | 1 | 1STY2CL | 2 | 4382062.0255 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123761 | Cadaragan ES | SANTA RITA | 2 | 1 | 2STY4CL | 4 | 12642605.4744 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123368 | Canbagtic ES | CALBIGA | 2 | 1 | 1STY3CL | 3 | 4382062.0255 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123916 | Cantao-an ES | PARANAS (WRIGHT) | 2 | 1 | 1STY2CL | 2 | 4458872.4326 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123315 | Guirang ES | BASEY | 2 | 1 | 2STY4CL | 4 | 12617542.9744 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123380 | Otoc ES | CALBIGA | 2 | 1 | 1STY2CL | 2 | 4382062.0255 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123322 | Rawis ES | BASEY | 2 | 1 | 2STY4CL | 4 | 12617542.9744 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 313715 | San Fernando NHS | BASEY | 2 | 1 | 2STY4CL | 4 | 12617542.9744 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123386 | San Mauricio Elementary School | CALBIGA | 2 | 1 | 1STY2CL | 2 | 4382062.0255 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123465 | San Vicente ES | DARAM | 2 | 1 | 2STY4CL | 4 | 12657642.9744 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123325 | Serum ES | BASEY | 2 | 1 | 2STY4CL | 4 | 12617542.9744 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123387 | Sinalangtan ES | CALBIGA | 2 | 1 | 1STY2CL | 2 | 4382062.0255 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123580 | Tabay Elementary School | HINABANGAN | 2 | 1 | 1STY2CL | 2 | 4382062.0255 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123355 | Tingib ES | BASEY | 2 | 1 | 4STY20CL | 20 | 51248921.7975 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 123931 | Tula ES | PARANAS (WRIGHT) | 2 | 1 | 2STY4CL | 4 | 12617542.9744 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region VIII | Samar (Western Samar) | 193519 | Upper Minata Elementary School | CALBIGA | 2 | 1 | 1STY2CL | 2 | 4458872.4326 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region VIII | Southern Leyte | 122200 | Aurora Elementary School | MALITBOG | 0 | 1 | 1STY2CL | 2 | 6650338.9965 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
SHS | Region VIII | Southern Leyte | 303463 | Libas NHS | SOGOD | 0 | 1 | 1STY3CL | 3 | 9499462.0616 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region VIII | Southern Leyte | 122036 | Lumbog Elementary School | HINUNANGAN | 0 | 1 | 1STY2CL | 2 | 6333313.4692 |  | Ongoing | 10% | 10% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region VIII | Tacloban City | 124224 | Caibaan ES | TACLOBAN CITY (Capital) | 1 | 1 | 2STY4CL | 4 | 14139835.2846 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region X | Bukidnon | 126810 | Lirongan ES | TALAKAG | 1 | 1 | 1STY4CL | 4 | 10825793.9925 |  | Under Procurement | 0% | 0% | 0% |  |  | 19KC0098 |  |  | 2019-06-11 | [5 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region X | Bukidnon | 501153 | Capt. Juan IS | ANTAPAN | 2 | 1 | 1STY2CL | 2 | 4986594.207 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
SHS | Region X | Bukidnon |  | Impasug-Ong Stand Alone SHS | IMPASUG-ONG | 2 | 1 | 2STY4CL | 4 | 12076243.7711 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region X | Bukidnon | 126768 | Nakabuklad ES | SAN FERNANDO | 2 | 1 | 1STY2CL | 2 | 5146012.8397 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region X | Bukidnon | 126776 | Tigua ES | SAN FERNANDO | 2 | 1 | 1STY3CL | 3 | 7064432.8094 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region X | Bukidnon | 126710 | Kipaypayon ES | QUEZON | 3 | 1 | 2UNITS 1STY3CL | 6 | 18476720.9809 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region X | Bukidnon | 126712 | Lumintao ES | QUEZON | 3 | 1 | 1STY5CL | 5 | 13468044.5961 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
K10 | Region X | Bukidnon | 126719 | Quezon CES | QUEZON | 3 | 1 | 3STY9CL | 9 | 31814538 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
K10 | Region X | Bukidnon | 126720 | Salaysay ES | QUEZON | 3 | 1 | 1STY4CL | 4 | 10612291.6878 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region X | Bukidnon | 126685 | Kimanait ES | PANGANTUCAN | 4 | 1 | 1STY4CL | 4 | 10785693.9925 |  | Under Procurement | 0% | 0% | 0% |  |  | 19KC0099 |  |  | 2019-06-11 | [5 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region X | Cagayan de Oro City | 127979 | Mambuaya Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 1STY2CL | 2 | 5588066.117 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region X | Cagayan de Oro City | 127948 | Balubal Elementary School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 1STY2CL | 2 | 6516250 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region X | Camiguin | 126932 | Liong ES | Guinsiliban | 0 | 1 | 2STY4CL | 4 | 14003117.9737 |  | Ongoing | 0% | 15% | 15% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region X | El Salvador | 127674 | Kalabaylabay ES | CITY OF EL SALVADOR | 2 | 1 | 3STY9CL | 9 | 25973630.8969 |  | Ongoing | 0% | 55% | 55% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0
K10 | Region X | Gingoog City | 128051 | Esik Campilan Elementary School | GINGOOG CITY | 1 | 1 | 2STY4CL | 4 | 12151927.4405 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region X | Gingoog City | 128058 | Roy Vizcara Elementary School | GINGOOG CITY | 1 | 1 | 2STY4CL | 4 | 12299615.0467 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region X | Iligan City | 128154 | Estenzo Comendador MES (Upper Tominobo ES) | ILIGAN CITY | 0 | 1 | 2STY4CL | 4 | 12903925.6156 |  | Ongoing | 0% | 10% | 10% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
SHS | Region X | Lanao del Norte | 304000 | Binuni-Demologan NHS | BACOLOD | 1 | 1 | 2STY4CL | 4 | 12647285.6156 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
SHS | Region X | Lanao del Norte | 304013 | Diego H. Patigayon NHS (Mukas NHS) | KOLAMBUGAN | 1 | 1 | 2STY4CL | 4 | 14316448.1156 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region X | Lanao del Norte | 127186 | Padianan ES | SALVADOR | 2 | 1 | 2STY6CL | 6 | 16667013.625 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region X | Malaybalay City | 103629 | Pighalugan ES | CITY MALAYBALAY (Capital) | 2 | 1 | 1STY5CL | 5 | 10844681.2529 |  | Ongoing | 0% | 60% | 60% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0
K10 | Region X | Misamis Occidental | 127500 | Mangidkid Elementary School | PLARIDEL | 1 | 1 | 1STY3CL W/ TOILET ATTACHED | 3 | 6949731.9724 |  | Ongoing | 0% | 25% | 25% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region X | Misamis Occidental | 127370 | San Francisco ES | CONCEPCION | 1 | 1 | 1STY2CL W/ TOILET ATTACHED | 2 | 7441920.9965 |  | Ongoing | 0% | 20% | 20% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region X | Misamis Occidental | 127270 | Tugaya ES | ALORAN | 1 | 1 | 1STY2CL W/ TOILET ATTACHED | 2 | 5099053.6946 |  | Ongoing | 0% | 25% | 25% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region X | Misamis Occidental | 127384 | Petianan ES | DON VICTORIANO CHIONGBIAN | 2 | 1 | 2STY6CL | 6 | 22179300.6968 |  | Ongoing | 0% | 40% | 40% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region X | Misamis Occidental | 127359 | Tinaclaan ES | CLARIN | 2 | 1 | 2STY4CL | 4 | 19582366.2511 |  | Ongoing | 0% | 35% | 35% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region X | Misamis Oriental | 500250 | Alipuaton IS | SALAY | 1 | 1 | 2STY4CL | 4 | 12969790.9784 |  | Ongoing | 0% | 15% | 15% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region X | Misamis Oriental | 500250 | Alipuaton IS | SALAY | 1 |  | 2STY6CL | 6 | 16976587.7603 |  | Ongoing | 0% | 27% | 27% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
K10 | Region X | Misamis Oriental | 127927 | Talacogon ES | LUGAIT | 2 | 1 | 2STY10CL | 10 | 25173868.8679 |  | Ongoing | 0% | 57% | 57% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0
K10 | Region X | Oroquieta City | 127468 | Sarancial Mialen ES | OROQUIETA CITY (Capital) | 1 | 1 | 1STY2CL W/ TOILET ATTACHED | 2 | 5023607.1386 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region X | Ozamis City | 128165 | Bacolod Elementary School | OZAMIS CITY | 2 | 1 | 2STY6CL | 6 | 17114579.8703 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region X | Ozamis City | 128162 | Baybay Central School | OZAMIS CITY | 2 | 1 | 3STY6CL | 6 | 28992806.1522 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region X | Ozamis City | 128170 | Gango Elementary School | OZAMIS CITY | 2 | 1 | 3STY9CL | 9 | 34647658.1575 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
K10 | Region X | Ozamis City | 500701 | Misamis Annex Integrated School | OZAMIS CITY | 2 | 1 | 3STY6CL | 6 | 25076720.2219 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region X | Tangub City | 128237 | Villaba ES | TANGUB CITY | 2 | 1 | 2STY4CL | 4 | 13251768.2235 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region X | Valencia City | 126873 | Laligan Central School | CITY OF VALENCIA | 4 | 1 | 1STY3CL | 3 | 7017500 |  | Ongoing | 0% | 55% | 55% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region XI | Compostela Valley | 128460 | Banglasan ES | MONTEVISTA | 1 | 1 | 1STY3CL W/ TOILET ATTACHED | 3 | 6866122.5 |  | Ongoing | 30% | 70% | 40% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region XI | Compostela Valley | 204019 | Cabanggatan ES | MONTEVISTA | 1 | 1 | 1STY4CL W/ TOILET ATTACHED | 4 | 9477434.5 |  | Ongoing | 30% | 70% | 40% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region XI | Compostela Valley | 128433 | Inambatan ES | MONKAYO | 1 | 1 | 1STY3CL W/ TOILET ATTACHED | 3 | 7030532.5 |  | Ongoing | 43% | 76% | 33% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region XI | Compostela Valley | 128526 | Pongpong ES | NEW BATAAN | 1 | 1 | 1STY2CL W/ TOILET ATTACHED | 2 | 5745828.75 |  | Ongoing | 35% | 50% | 15% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region XI | Compostela Valley | 128295 | Doña Josefa ES | LAAK (SAN VICENTE) | 2 | 1 | 1STY2CL W/ TOILET ATTACHED | 2 | 5481670 |  | Ongoing | 70% | 80% | 10% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region XI | Compostela Valley | 128408 | Guisok ES | MAWAB | 2 | 1 | 1STY2CL W/ TOILET ATTACHED | 2 | 4743328.75 |  | Ongoing | 75% | 79% | 4% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region XI | Compostela Valley | 128543 | Gumayan ES | PANTUKAN | 2 | 1 | 1STY3CL W/ TOILET ATTACHED | 3 | 7557897.625 |  | Ongoing | 20% | 36% | 16% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region XI | Compostela Valley | 128302 | Kapatagan ES | LAAK (SAN VICENTE) | 2 | 1 | 2STY10CL | 10 | 35203697.2988 |  | Ongoing | 25% | 42% | 17% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0
K10 | Region XI | Compostela Valley | 128370 | Manipongol ES | MACO | 2 | 1 | 1STY3CL W/ TOILET ATTACHED | 3 | 6625238.8927 |  | Ongoing | 60% | 64% | 4% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
K10 | Region XI | Compostela Valley | 128373 | New Leyte ES | MACO | 2 | 1 | 1STY2CL W/ TOILET ATTACHED | 2 | 4743328.75 |  | Ongoing | 35% | 43% | 8% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region XI | Compostela Valley | 128555 | Pantukan ES | PANTUKAN | 2 | 1 | 2STY12CL | 12 | 42243345 |  | Ongoing | 25% | 28% | 3% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
SHS | Region XI | Compostela Valley | 304208 | Pantukan NHS | PANTUKAN | 2 | 1 | 2STY12CL | 12 | 42243345 |  | Ongoing | 35% | 36% | 1% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0
K10 | Region XI | Compostela Valley | 128417 | San Vicente PS | MAWAB | 2 | 1 | 1STY2CL W/ TOILET ATTACHED | 2 | 5244578.75 |  | Ongoing | 35% | 44% | 9% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region XI | Davao City | 129703 | Agdao Elementary School | DAVAO CITY | 1 | 1 | 4STY8CL | 8 | 25580055.6625 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
SHS | Region XI | Davao City | 304365 | Erico T. Nograles NHS | DAVAO CITY | 1 | 1 | 4STY24CL | 24 | 79423837.4325 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0
K10 | Region XI | Davao City | 129662 | Kiman-Anao ES | DAVAO CITY | 2 | 1 | 1STY3CL | 3 | 8021061.6475 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region XI | Davao City | 129678 | Tibungol ES | DAVAO CITY | 2 | 1 | 1STY3CL | 3 | 8001011.6475 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
K10 | Region XI | Davao City | 8888 | Cabagaayan ES | DAVAO CITY | 3 | 1 | 2UNITS 1STY3CL | 6 | 14337537.3573 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region XI | Davao City | 129571 | Masicampo ES | DAVAO CITY | 3 | 1 | 2STY6CL | 6 | 21808019.288 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
K10 | Region XI | Davao del Norte | 204501 | Camansa Lower Elementary School | ASUNCION (SAUG) | 1 | 1 | 1STY2CL W/TOILET | 2 | 4292705 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region XI | Davao del Norte | 204533 | Dr. Vislumino Y. Tamondong Elementary School | KAPALONG | 1 | 1 | 1STY3CL W/ TOILET | 3 | 6427027.5 |  | Under Procurement | 0% | 0% | 0% |  |  |  | 2019-08-02 | [7 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
SHS | Region XI | Davao del Norte | 315906 | Pinamuno National High School | SAN ISIDRO | 1 | 1 | 2STY4CL | 4 | 13784295.8025 |  | Under Procurement | 0% | 0% | 0% |  |  |  | 2019-08-02 | [7 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region XI | Davao del Norte | 128643 | Tubod ES | CARMEN | 2 | 1 | 1STY5CL W/ TOILET ATTACHED | 5 | 10251615.125 |  | Under Procurement | 0% | 0% | 0% |  |  |  | 2019-08-02 | [7 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
K10 | Region XI | Davao del Sur | 316015 | Manuel Francisco C. Ramos Sr., National High School | SANTA CRUZ | 1 | 1 | 2STY4CL | 4 | 16853626.2832 |  | Ongoing | 8% | 75% | 67% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region XI | Davao del Sur | 316016 | Maria Cleta R. Delos Cientos National High School | PADADA | 1 | 1 | 1STY3CL W/ TOILET ATTACHED | 3 | 7819148.2528 |  | Completed | 10% | 100% | 90% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3
K10 | Region XI | Davao Occidental | 129002 | Mana CES | MALITA | 0 | 1 | 2STY4CL | 4 | 13019847.4475 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region XI | Davao Occidental | 129129 | Tanglad ES | SANTA MARIA | 0 | 1 | 1STY2CL | 2 | 4936198.7225 |  | Ongoing | 15% | 15% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region XI | Davao Oriental | 129198 | Cabasagan ES | BOSTON | 1 | 1 | 2STY8CL | 8 | 26063498.6961 |  | Ongoing | 15% | 55% | 40% | Requesting for Additional Funds | [10 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0
K10 | Region XI | Digos City | 302004 | Dawis National High School | CITY OF DIGOS (Capital) | 1 | 1 | 1STY2CL | 2 | 5105488.2409 |  | Completed | 33% | 100% | 67% |  | P00370721MN | 19LD0128 | July19-Aug 8, 2019 | July 26, 2019 | August 8, 2019 |  | August 21-22, 2019 | NLC Const & Supply | Nov. 14, 2019 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2
K10 | Region XI | Island Garden City of Samal | 500443 | San Isidro Integrated School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2STY4CL | 4 | 12786796.2725 |  | Ongoing | 10% | 50% | 40% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region XI | Mati City | 129413 | Dawan Central ES | CITY OF MATI (Capital) | 2 | 1 | 2STY4CL | 4 | 17164351.2885 |  | Ongoing | 15% | 60% | 45% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
SHS | Region XI | Mati City | 304313 | Dawan NHS | CITY OF MATI (Capital) | 2 | 1 | 2STY4CL | 4 | 17239860.571 |  | Ongoing | 7% | 50% | 43% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region XI | Panabo City | 129790 | P. Changco ES | CITY OF PANABO | 2 | 1 | 1STY2CL W/ TOILET ATTACHED | 2 | 4192672.5425 |  | Ongoing | 29% | 29% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0
K10 | Region XI | Tagum City | 128783 | SAN AGUSTIN ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 3STY9CL | 9 | 29716706.5 |  | Under Procurement | 0% | 0% | 0% | For Additional Fund | [10 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
K10 | Region XII | General Santos City | 131284 | Irineo Santiago ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2STY4CL | 4 | 10143273.8472 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region XII | Koronadal City | 131388 | Chua Elementary School | CITY OF KORONADAL (Capital) | 2 | 1 | 2STY4CL | 4 | 10848034.2645 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
SHS | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2 | 1 | 2STY8CL | 8 | 22466024.4687 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
K10 | Region XII | North Cotabato | 316545 | Yanson High School | ALAMADA | 1 | 1 | 1STY4CL | 4 | 9763900.9502 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
K10 | Region XII | North Cotabato | 304697 | Bongolanon High School | MAGPET | 2 | 1 | 2STY8CL | 8 | 22372395.3997 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
SHS | Region XII | North Cotabato | 304420 | Banisilan NHS | BANISILAN | 3 | 1 | 3STY15CL | 15 | 52124547.1519 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
K10 | Region XII | Sarangani | 500710 | James Alfred Strong Integrated School | MAITUM | 0 | 1 | 2STY4CL | 4 | 9327655.6466 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
SHS | Region XII | Sarangani | 304525 | Glan-Padidu NHS | GLAN | 0 | 1 | 4STY16CL | 16 | 35354981.5363 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
K10 | Region XII | Sarangani | 500835 | Dakok Tamulon Integrated School | MALUNGON | 0 | 1 | 2STY4CL | 4 | 9357498.2671 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
SHS | Region XII | Sarangani | 304521 | Baliton NHS | GLAN | 0 | 1 | 3STY12CL | 12 | 29432665.4181 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
TVL | Region XII | South Cotabato | 304544 | Bentung Sulit NHS | POLOMOLOK | 1 | 1 | 2STY4CL (2REG WS) | 2 | 10239355.8833 |  | Under Procurement | 0% | 0% | 0% | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
K10 | Region XII | South Cotabato | 130660 | Blit ES | LAKE SEBU | 2 | 1 | 2UNITS 1STY2CL | 4 | 7442573.634 |  | Ongoing | 4.16% | 4.16% | 0% |  | P00370738MN | 19MG0166 |  |  |  |  | 2019-10-21 | Migo Construction | 2020-05-26 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0
K10 | Region XII | South Cotabato | 130810 | Demamis ES | T'BOLI | 2 | 1 | 1STY3CL | 3 | 5671732.7219 |  | Ongoing | 8.47% | 8.47% | 0% |  | P00370739MN | 19MG0167 |  |  |  |  | 2019-10-21 | Janmarie Const. Services | 2020-04-24 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0
SHS | Region XII | South Cotabato | 304547 | Edwards NHS | T'BOLI | 2 | 1 | 2STY6CL | 6 | 15389838.4094 |  | Ongoing | 1.28% | 1.28% | 0% |  | P00370739MN | 19MG0168 |  |  |  |  | 2019-10-21 | Migo Construction | 2020-04-19 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0
| Grand Total | [7 empty] | 14 | 29306534.5072 | [16 empty] | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 14 | 0
Note on E47: Sherwin-Lennovo: Original List - Caloocan North ES
Note on I61: Sherwin-Lennovo: changed to 4STY12CL original scope is 4sty8cl. Subject to submission of documents/validation
Note on E68: Sherwin-Lennovo: Original List - Justo Lukban Elementary School
Note on E70: Sherwin-Lennovo: Changed to Buli ES 4STY8CL, original school was Poblacion ES
Note on I71: Sherwin-Lennovo: Changed to 4STY20CL 51,730,000.00 original scope is 4STY8CL 19,925,000.00
Note on E72: Sherwin-Lennovo: Replaced_Tangos_ES_1_4STY8CL from Tanza ES
Note on E84: Sherwin-Lennovo: From RP Cruz ES due to NBS
Note on I227: Sherwin Bagagunio: From 4STY12CL changed to 4STY16CL
Note on D399: Sherwin Bagagunio: from Anabu I ES - NBS
Note on E401: Sherwin Bagagunio: from Southville 3A ES - NBS

## Summary
REPUBLIC OF THE PHILIPPINES
DEPARTMENT OF EDUCATION
CY 2019 BASIC EDUCATIONAL FACILITIES FUND
As of February 25, 2019
Region | Sum of Total Project Cost | Sum of Total No. of Classrooms | Sum of No. of CL Completed | Sum of No. of CL ongoing | Sum of No. of CL Under Procurement | Sum of No. of CL Not yet started | Sum of No. of CL Reverted
CAR | 188847278.9954 | 66 | 0 | 66 | 0 | 0 | 0
CARAGA | 314482896.8656 | 121 | 0 | 49 | 72 | 0 | 0
NCR | 2035951968.6643 | 632 | 0 | 464 | 168 | 0 | 0
Region I | 1366528118.8145 | 534 | 0 | 88 | 446 | 0 | 0
Region II | 196847179.7325 | 87 | 0 | 6 | 81 | 0 | 0
Region III | 2665517856.8101 | 929 | 0 | 891 | 38 | 0 | 0
Region IV-A | 2203333589.3435 | 743 | 0 | 531 | 212 | 0 | 0
Region IV-B | 163747385.7153 | 48 | 0 | 14 | 34 | 0 | 0
Region IX | 333905131.4257 | 125 | 0 | 98 | 27 | 0 | 0
Region V | 1390167291.5605 | 375 | 0 | 50 | 325 | 0 | 0
Region VI | 492551716.4097 | 198 | 0 | 74 | 124 | 0 | 0
Region VII | 776987723.9468 | 278 | 0 | 79 | 199 | 0 | 0
Region VIII | 488877168.6891 | 194 | 2 | 34 | 158 | 0 | 0
Region X | 516665589.5587 | 164 | 0 | 62 | 102 | 0 | 0
Region XI | 530031709.5969 | 170 | 5 | 92 | 73 | 0 | 0
Region XII | 249934477.599 | 94 | 0 | 13 | 81 | 0 | 0
Grand Total | 13914377083.7277 | 4758 | 7 | 2611 | 2140 | 0 | 0