## summary
Column Labels
| Sum of NO. OF SITES |  |  |  | Sum of ALLOCATION |  |  |  | Total Sum of NO. OF SITES | Total Sum of ALLOCATION
Row Labels | ELECTRIFICATION OF SCHOOLS ON-GRID | SOLAR PANEL | UPGRADING | (blank) | ELECTRIFICATION OF SCHOOLS ON-GRID | SOLAR PANEL | UPGRADING | (blank)
CAR | 1 |  | 81 |  | 1351919.59 |  | 109996811.43 |  | 82 | 111348731.02
Abra |  |  | 11 |  |  |  | 11674528 |  | 11 | 11674528
Apayao |  |  | 10 |  |  |  | 9798196.19 |  | 10 | 9798196.19
Baguio City |  |  | 1 |  |  |  | 5343246.78 |  | 1 | 5343246.78
Benguet |  |  | 17 |  |  |  | 19145226.02 |  | 17 | 19145226.02
Ifugao |  |  | 6 |  |  |  | 11264300.81 |  | 6 | 11264300.81
Kalinga |  |  | 11 |  |  |  | 15551115.36 |  | 11 | 15551115.36
Mt. Province | 1 |  | 21 |  | 1351919.59 |  | 28239444.21 |  | 22 | 29591363.8
Tabuk City |  |  | 4 |  |  |  | 8980754.06 |  | 4 | 8980754.06
CARAGA |  |  | 27 |  |  |  | 44434190.4 |  | 27 | 44434190.4
Dinagat Island |  |  | 6 |  |  |  | 13575190.9 |  | 6 | 13575190.9
Siargao |  |  | 3 |  |  |  | 7976924.5 |  | 3 | 7976924.5
Surigao del Norte |  |  | 18 |  |  |  | 22882075 |  | 18 | 22882075
NCR |  |  | 8 |  |  |  | 26849144.57 |  | 8 | 26849144.57
Caloocan City |  |  | 1 |  |  |  | 1957934.42 |  | 1 | 1957934.42
Quezon City |  |  | 7 |  |  |  | 24891210.15 |  | 7 | 24891210.15
Region I | 63 |  | 2 |  | 61724146.67 |  | 599425.36 |  | 65 | 62323572.03
Candon City | 3 |  |  |  | 2550104.89 |  |  |  | 3 | 2550104.89
Dagupan City | 2 |  |  |  | 2637123.83 |  |  |  | 2 | 2637123.83
Ilocos Norte | 3 |  |  |  | 3100048.77 |  |  |  | 3 | 3100048.77
Ilocos Sur | 10 |  | 1 |  | 7808721.55 |  | 379200.22 |  | 11 | 8187921.77
La Union | 11 |  |  |  | 13473946.16 |  |  |  | 11 | 13473946.16
Pangasinan I, Lingayen | 15 |  |  |  | 15025152.53 |  |  |  | 15 | 15025152.53
Pangasinan II, Binalonan | 12 |  |  |  | 10002749.19 |  |  |  | 12 | 10002749.19
San Carlos City | 3 |  |  |  | 2980902.35 |  |  |  | 3 | 2980902.35
Urdaneta City | 2 |  |  |  | 1853910.56 |  |  |  | 2 | 1853910.56
Vigan City | 2 |  | 1 |  | 2291486.84 |  | 220225.14 |  | 3 | 2511711.98
Region II |  | 15 | 130 |  |  | 20825552.88 | 145268632.08 |  | 145 | 166094184.96
Batanes |  |  | 3 |  |  |  | 3317035.98 |  | 3 | 3317035.98
Cagayan |  | 11 | 45 |  |  | 11147852.23 | 37224662.84 |  | 56 | 48372515.07
Cauayan City |  |  | 6 |  |  |  | 7175073.54 |  | 6 | 7175073.54
City of Ilagan |  |  | 3 |  |  |  | 5821383.32 |  | 3 | 5821383.32
Isabela |  | 1 | 45 |  |  | 2206445.44 | 57651245.95 |  | 46 | 59857691.39
Nueva Vizcaya |  | 2 | 6 |  |  | 4817943.45 | 18458248.36 |  | 8 | 23276191.81
Quirino |  | 1 | 16 |  |  | 2653311.76 | 10944011.47 |  | 17 | 13597323.23
Santiago City |  |  | 2 |  |  |  | 2346431.77 |  | 2 | 2346431.77
Tuguegarao City |  |  | 4 |  |  |  | 2330538.85 |  | 4 | 2330538.85
Region III |  | 9 | 47 |  |  | 8510838.32 | 48685681.92 |  | 56 | 57196520.24
Angeles City |  |  | 2 |  |  |  | 346116.56 |  | 2 | 346116.56
Aurora |  |  | 9 |  |  |  | 15638048.93 |  | 9 | 15638048.93
Bataan |  |  | 3 |  |  |  | 7263823.35 |  | 3 | 7263823.35
Mabalacat City |  |  | 5 |  |  |  | 3066065.34 |  | 5 | 3066065.34
Malolos City |  |  | 1 |  |  |  | 2604906.2 |  | 1 | 2604906.2
Olongapo City |  | 1 |  |  |  | 2077391.62 |  |  | 1 | 2077391.62
Tarlac |  |  | 1 |  |  |  | 2770962.62 |  | 1 | 2770962.62
Zambales |  | 8 | 26 |  |  | 6433446.7 | 16995758.92 |  | 34 | 23429205.62
Region IV-A |  | 2 | 18 |  |  | 2648046.5 | 15742659.6504 |  | 20 | 18390706.1504
Bacoor City |  |  | 1 |  |  |  | 1146067.18 |  | 1 | 1146067.18
Batangas City |  |  | 6 |  |  |  | 4670145.61 |  | 6 | 4670145.61
CITY OF BIÑAN |  |  | 3 |  |  |  | 2758464.02 |  | 3 | 2758464.02
Rizal |  | 2 | 1 |  |  | 2648046.5 | 1995063.29 |  | 3 | 4643109.79
San Pablo City |  |  | 4 |  |  |  | 1991781.5104 |  | 4 | 1991781.5104
TANAUAN CITY |  |  | 2 |  |  |  | 1874395.49 |  | 2 | 1874395.49
TAYABAS CITY |  |  | 1 |  |  |  | 1306742.55 |  | 1 | 1306742.55
Region IV-B | 52 | 25 | 4 |  | 63004255.95 | 50731883.62 | 3801238.11 |  | 81 | 117537377.68
Calapan City | 1 |  | 1 |  | 446113.47 |  | 415231.83 |  | 2 | 861345.3
Marinduque | 3 | 2 |  |  | 1501078.11 | 1794138.92 |  |  | 5 | 3295217.03
Occidental Mindoro | 10 |  |  |  | 7961409.4 |  |  |  | 10 | 7961409.4
Oriental Mindoro | 10 |  | 2 |  | 11515163.63 |  | 1955891.28 |  | 12 | 13471054.91
Palawan | 16 | 23 | 1 |  | 23255050.36 | 48937744.7 | 1430115 |  | 40 | 73622910.06
Romblon | 12 |  |  |  | 18325440.98 |  |  |  | 12 | 18325440.98
Region IX |  |  | 74 |  |  |  | 57702317.09 |  | 74 | 57702317.09
Zamboanga City |  |  | 9 |  |  |  | 9045000 |  | 9 | 9045000
Zamboanga del Norte |  |  | 30 |  |  |  | 19241957.09 |  | 30 | 19241957.09
Zamboanga del Sur |  |  | 35 |  |  |  | 29415360 |  | 35 | 29415360
Region V | 7 |  | 74 | 1 | 9862646.77 |  | 137699469.06 | 6161438.9 | 82 | 153723554.73
Albay |  |  | 10 | 1 |  |  | 15364484.02 | 6161438.9 | 11 | 21525922.92
Camarines Norte |  |  | 9 |  |  |  | 30179190.14 |  | 9 | 30179190.14
Camarines Sur |  |  | 44 |  |  |  | 74464800.2 |  | 44 | 74464800.2
Catanduanes |  |  | 5 |  |  |  | 9003325.55 |  | 5 | 9003325.55
Iriga City |  |  | 1 |  |  |  | 1224536.41 |  | 1 | 1224536.41
Legaspi City |  |  | 1 |  |  |  | 3313445.5 |  | 1 | 3313445.5
Sorsogon | 7 |  |  |  | 9862646.77 |  |  |  | 7 | 9862646.77
Sorsogon City |  |  | 4 |  |  |  | 4149687.24 |  | 4 | 4149687.24
Region VI |  | 21 | 205 |  |  | 24383318.22 | 280481280.6337 |  | 226 | 304864598.8537
Aklan |  | 3 | 29 |  |  | 2025433.87 | 35128143.1462 |  | 32 | 37153577.0162
Antique |  |  | 43 |  |  |  | 57939792.0072 |  | 43 | 57939792.0072
Bacolod City |  |  | 3 |  |  |  | 3625952.67 |  | 3 | 3625952.67
Bago City |  |  | 7 |  |  |  | 6648010.19 |  | 7 | 6648010.19
Cadiz City |  | 1 | 5 |  |  | 1476567.94 | 7311207.62 |  | 6 | 8787775.56
Capiz |  |  | 54 |  |  |  | 37439340.4303 |  | 54 | 37439340.4303
Escalante City |  |  | 1 |  |  |  | 1141365.67 |  | 1 | 1141365.67
Guimaras |  |  | 1 |  |  |  | 3911646.12 |  | 1 | 3911646.12
Iloilo |  |  | 9 |  |  |  | 31823715.68 |  | 9 | 31823715.68
Iloilo City |  |  | 1 |  |  |  | 4475369.9 |  | 1 | 4475369.9
Kabankalan City |  |  | 19 |  |  |  | 22891681.86 |  | 19 | 22891681.86
Negros Occidental |  | 11 | 11 |  |  | 10564742.2 | 43158958.06 |  | 22 | 53723700.26
Passi City |  |  | 1 |  |  |  | 3134244.08 |  | 1 | 3134244.08
Roxas City |  |  | 9 |  |  |  | 5709873.74 |  | 9 | 5709873.74
Sagay City |  |  | 9 |  |  |  | 12013845.53 |  | 9 | 12013845.53
San Carlos City |  | 6 |  |  |  | 10316574.21 |  |  | 6 | 10316574.21
Silay City |  |  | 3 |  |  |  | 4128133.93 |  | 3 | 4128133.93
Region VII |  | 2 | 182 |  |  | 2804191.69 | 285897083.13 |  | 184 | 288701274.82
Bais City |  |  | 4 |  |  |  | 9798916.94 |  | 4 | 9798916.94
Bayawan City |  |  | 34 |  |  |  | 64138639.05 |  | 34 | 64138639.05
Bohol |  |  | 30 |  |  |  | 54116235.47 |  | 30 | 54116235.47
Carcar City |  |  | 7 |  |  |  | 15569447.1 |  | 7 | 15569447.1
Cebu |  |  | 23 |  |  |  | 37670224.21 |  | 23 | 37670224.21
Dumaguete City |  |  | 3 |  |  |  | 3210023.75 |  | 3 | 3210023.75
Guihulngan City |  | 2 | 3 |  |  | 2804191.69 | 5299302.27 |  | 5 | 8103493.96
Lapu-Lapu City |  |  | 3 |  |  |  | 6008911.36 |  | 3 | 6008911.36
Mandaue City |  |  | 3 |  |  |  | 3311550.83 |  | 3 | 3311550.83
Negros Oriental |  |  | 38 |  |  |  | 24364649.22 |  | 38 | 24364649.22
Siquijor |  |  | 13 |  |  |  | 45777326.98 |  | 13 | 45777326.98
Tagbilaran City |  |  | 1 |  |  |  | 1682365.93 |  | 1 | 1682365.93
Talisay City |  |  | 11 |  |  |  | 5229067.61 |  | 11 | 5229067.61
Tanjay City |  |  | 9 |  |  |  | 9720422.41 |  | 9 | 9720422.41
Region VIII | 3 |  | 50 |  | 2851853.13 |  | 101522337.86 |  | 53 | 104374190.99
Borongan City |  |  | 3 |  |  |  | 6530531.33 |  | 3 | 6530531.33
Calbayog City |  |  | 3 |  |  |  | 3659487.52 |  | 3 | 3659487.52
Catbalogan City |  |  | 3 |  |  |  | 2853650.92 |  | 3 | 2853650.92
Eastern Samar |  |  | 5 |  |  |  | 12465783.82 |  | 5 | 12465783.82
Leyte |  |  | 4 |  |  |  | 6684462.92 |  | 4 | 6684462.92
Northern Samar |  |  | 9 |  |  |  | 19626307.19 |  | 9 | 19626307.19
Ormoc City |  |  | 14 |  |  |  | 34409086.12 |  | 14 | 34409086.12
Samar (Western Samar) | 3 |  | 8 |  | 2851853.13 |  | 12024160.05 |  | 11 | 14876013.18
Tacloban City |  |  | 1 |  |  |  | 3268867.99 |  | 1 | 3268867.99
Region X | 1 |  | 42 |  | 395210.89 |  | 134375328.3486 |  | 43 | 134770539.2386
Bukidnon |  |  | 7 |  |  |  | 5278305.25 |  | 7 | 5278305.25
Cagayan de Oro City |  |  | 6 |  |  |  | 15152893.81 |  | 6 | 15152893.81
Camiguin |  |  | 10 |  |  |  | 53139490.47 |  | 10 | 53139490.47
El Salvador |  |  | 1 |  |  |  | 2639714.7 |  | 1 | 2639714.7
Malaybalay City | 1 |  | 7 |  | 395210.89 |  | 11804215.8886 |  | 8 | 12199426.7786
Misamis Oriental |  |  | 9 |  |  |  | 38759949.94 |  | 9 | 38759949.94
Oroquieta City |  |  | 2 |  |  |  | 7600758.29 |  | 2 | 7600758.29
Region XI |  |  | 67 |  |  |  | 133389868.1 |  | 67 | 133389868.1
Compostela Valley |  |  | 23 |  |  |  | 43611881.93 |  | 23 | 43611881.93
Davao del Norte |  |  | 6 |  |  |  | 26381846.82 |  | 6 | 26381846.82
Davao del Sur |  |  | 14 |  |  |  | 23310742.37 |  | 14 | 23310742.37
Davao Occidental |  |  | 11 |  |  |  | 19351025.85 |  | 11 | 19351025.85
Island Garden City of Samal |  |  | 13 |  |  |  | 20734371.13 |  | 13 | 20734371.13
Region XII |  |  | 18 |  |  |  | 36430265.1413 |  | 18 | 36430265.1413
North Cotabato |  |  | 18 |  |  |  | 36430265.1413 |  | 18 | 36430265.1413
Grand Total | 127 | 74 | 1029 | 1 | 139190033 | 109903831.23 | 1562875732.884 | 6161438.9 | 1231 | 1818131036.014

## ELECTRIFICATION LIST ALL
REPUBLIC OF THE PHILIPPINES
DEPARTMENT OF EDUCATION
CY 2018 BASIC EDUCATIONAL FACILITIES FUND
ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1,2,3&4
March 25, 2020 | [16 empty] | As of January 2020 | As of February 2020
REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | # of cl Needs Major Repair | NO. OF SITES | TOTAL PHYSICAL TARGET | BLDG. TYPE | HAULING | REPAIR COST | TOTAL COST | ALLOCATION | SCOPE OF WORK | BATCH | STATUS | Previous Percentage of Completion | Present Percentage of Completion | Target Completion Date | Actual Completion Date | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Contract Amount | No. of Sites Reverted (1) | No. of Sites Not yet started (1) | No. of Sites Under Procurement (1) | No. of Sites On Going(1) | No. of Sites Completed (1) | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed |  | WITH TRANSFOPMER (Y/N)
CAR | Abra | 305075 | Abra HS | BANGUED (Capital) | 0 |  | 1 | [5 empty] | 825727.12 | UPGRADING | 1 | Completed | 15% | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Abra | 305080 | Capitan NHS | DAGUIOMAN | 0 |  | 1 | [5 empty] | 807054.31 | UPGRADING | 1 | Completed | 22% | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Abra | 305105 | Western Abra NHS | DANGLAS | 0 |  | 1 | [5 empty] | 1001258.48 | UPGRADING | 1 | Completed | 34% | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Abra | 318701 | MARC YSRAEL B. BERNOS MEMORIAL NATIONAL HIGH SCHOOL | LA PAZ | 0 |  | 1 | [5 empty] | 1221450.81 | UPGRADING | 1 | Completed | 25% | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Abra | 305081 | Cayapa NHS | LAGANGILANG | 0 |  | 1 | [5 empty] | 1177438.05 | UPGRADING | 1 | Completed | 24% | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Abra | 305102 | Tagodtod NHS | LAGANGILANG | 0 |  | 1 | [5 empty] | 1168924.11 | UPGRADING | 1 | Completed | 22% | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Abra | 305094 | Pulot NHS | LAGAYAN | 0 |  | 1 | [5 empty] | 1162253.81 | UPGRADING | 1 | Completed | 35% | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Abra | 305101 | Suyo National High School | PIDIGAN | 0 |  | 1 | [5 empty] | 1794998.25 | UPGRADING | 1 | Completed | 20% | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Abra | 305074 | Abas NHS | SALLAPADAN | 0 |  | 1 | [5 empty] | 1072964.35 | UPGRADING | 1 | Completed | 21% | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Abra | 305091 | Northern Abra NHS | SAN JUAN | 0 |  | 1 | [5 empty] | 729023.16 | UPGRADING | 1 | Completed | 25% | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Abra | 305099 | San Quintin NHS | SAN QUINTIN | 0 |  | 1 | [5 empty] | 713435.55 | UPGRADING | 1 | Completed | 25% | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Apayao | 318811 | PIO DALIM Memorial SAT-Sta.Filomena | CALANASAN (BAYAG) | 0 |  | 1 | [5 empty] | 886166.84 | UPGRADING | 1 | Completed | 94% | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES | 908090.3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Apayao | 318803 | Conner Central NHS Cupis Annex | CONNER | 0 |  | 1 | [5 empty] | 826570.72 | UPGRADING | 1 | Completed | 94% | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES | 796851.23 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Apayao | 305113 | FLORA NATIONAL HIGH SCHOOL | FLORA | 0 |  | 1 | [5 empty] | 1199958.86 | UPGRADING | 1 | Completed | 94% | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES | 1156657.37 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Apayao | 305121 | Mayor Ricardo de San Jose, Sr. Comp. HS | FLORA | 0 |  | 1 | [5 empty] | 767937.37 | UPGRADING | 1 | Completed | 94% | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES | 988685.78 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Apayao | 318808 | Allig National Agricultural and Trade HS | FLORA | 0 |  | 1 | [5 empty] | 823927.98 | UPGRADING | 1 | Completed | 94% | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES | 895499.5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Apayao | 305115 | Kabugao Agro-Ind'l. HS Main | KABUGAO (Capital) | 0 |  | 1 | [5 empty] | 1026403.1 | UPGRADING | 1 | Completed | 94% | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES | 1074016.92 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Apayao | 305107 | Apayao Science HS | LUNA | 0 |  | 1 | [5 empty] | 929638.03 | UPGRADING | 1 | Completed | 94% | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES | 1239931.36 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Apayao | 305116 | Luna National High School Main | LUNA | 0 |  | 1 | [5 empty] | 933340.55 | UPGRADING | 1 | Completed | 90% | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES | 725415.93 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Apayao | 305123 | Pudtol NHS | PUDTOL | 0 |  | 1 | [5 empty] | 1284282.48 | UPGRADING | 1 | Completed | 90% | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES | 849654 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Apayao | 305120 | Mayor Guillermo Barsalan SAT | SANTA MARCELA | 0 |  | 1 | [5 empty] | 1119970.26 | UPGRADING | 1 | Completed | 90% | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES | 799643.44 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Baguio City | 305269 | Baguio City National High School - Main | BAGUIO CITY | 0 |  | 1 | [5 empty] | 5343246.78 | UPGRADING | 1 | Completed | 100% | 100% | Sept. 8, 2018 |  |  |  | 2018-04-26 | 2018-05-04 | 2018-05-18 | 2018-05-22 | 2018-06-08 | www.construction | 5314182.16 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Benguet | 305129 | Atok NHS | ATOK | 0 |  | 1 | [5 empty] | 1128082.5 | UPGRADING | 1 | ONGOING | 85% | 85% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Benguet | 318913 | Ampusongan NHS - Kayapa Ext. | BAKUN | 0 |  | 1 | [5 empty] | 1036761.41 | UPGRADING | 1 | ONGOING | 85% | 85% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Benguet | 318901 | Bokod NHS - Daclan Extension | BOKOD | 0 |  | 1 | [5 empty] | 1123051.32 | UPGRADING | 1 | Completed | 85% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Benguet | 305134 | Binga NHS | ITOGON | 0 |  | 1 | [5 empty] | 1120443.54 | UPGRADING | 1 | Completed | 85% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Benguet | 305142 | Laurencio Fianza National High School | ITOGON | 0 |  | 1 | [5 empty] | 1184835.64 | UPGRADING | 1 | Completed | 85% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Benguet | 305159 | Fianza Mem'l NHS - Tinongdan | ITOGON | 0 |  | 1 | [5 empty] | 1163516.51 | UPGRADING | 1 | Completed | 85% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Benguet | 305146 | Adaoay National High School | KABAYAN | 0 |  | 1 | [5 empty] | 1183986.61 | UPGRADING | 1 | Completed | 85% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Benguet | 305147 | Kapangan Central NHS (RA8841) | KAPANGAN | 0 |  | 1 | [5 empty] | 1022559.57 | UPGRADING | 1 | Completed | 25% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Benguet | 318908 | Gov. Bado Dangwa Agro-Industrial School Extension - Taba-ao Annex | KAPANGAN | 0 |  | 1 | [5 empty] | 1139374.62 | UPGRADING | 1 | Completed | 50% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Benguet | 305154 | MADAYMEN NATIONAL HIGH SCHOOL | KIBUNGAN | 0 |  | 1 | [5 empty] | 1147876.7 | UPGRADING | 1 | ONGOING | 85% | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Benguet | 305140 | Cordillera Regional Science HS | LA TRINIDAD (Capital) | 0 |  | 1 | [5 empty] | 1004906.3 | UPGRADING | 1 | ONGOING | 25% | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Benguet | 305139 | Cabiten NHS (RA9087) | MANKAYAN | 0 |  | 1 | [5 empty] | 1130157.75 | UPGRADING | 1 | ONGOING | 25% | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Benguet | 305144 | Guinaoang NHS | MANKAYAN | 0 |  | 1 | [5 empty] | 1147228.62 | UPGRADING | 1 | ONGOING | 25% | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Benguet | 305155 | Mankayan National High School | MANKAYAN | 0 |  | 1 | [5 empty] | 1167917.84 | UPGRADING | 1 | ONGOING | 25% | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Benguet | 305156 | Bulalacao NHS | MANKAYAN | 0 |  | 1 | [5 empty] | 1134226.7 | UPGRADING | 1 | ONGOING | 25% | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Benguet | 305157 | Sablan NHS | SABLAN | 0 |  | 1 | [5 empty] | 1162986.61 | UPGRADING | 1 | ONGOING | 25% | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Benguet | 305160 | Tuba NHS (Nangalisan) | TUBA | 0 |  | 1 | [5 empty] | 1147313.78 | UPGRADING | 1 | ONGOING | 25% | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Ifugao | 305171 | Eastern Potia National High School | ALFONSO LISTA (POTIA) | 0 |  | 1 | [5 empty] | 1679924.65 | UPGRADING | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | bid evaluation | Y
CAR | Ifugao | 305187 | Namillangan NHS | ALFONSO LISTA (POTIA) | 0 |  | 1 | [5 empty] | 2203262.26 | UPGRADING | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | bid evaluation | Y
CAR | Ifugao | 305188 | Pinto NHS | ALFONSO LISTA (POTIA) | 0 |  | 1 | [5 empty] | 1552581.28 | UPGRADING | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | bid evaluation | Y
CAR | Ifugao | 305190 | Sta. Maria NHS | ALFONSO LISTA (POTIA) | 0 |  | 1 | [5 empty] | 2725220.35 | UPGRADING | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | bid evaluation | Y
CAR | Ifugao | 305177 | Hapid NHS - Bimpal Annex | LAMUT | 0 |  | 1 | [5 empty] | 1410957.61 | UPGRADING | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | bid evaluation | Y
CAR | Ifugao | 305183 | Lawig NHS | LAMUT | 0 |  | 1 | [5 empty] | 1692354.66 | UPGRADING | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | bid evaluation | Y
CAR | Kalinga | 305199 | Balbalan Agricultural and Industrial School | BALBALAN | 0 |  | 1 | [5 empty] | 2442507.27 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Kalinga | 305223 | Lubuagan National High School | LUBUAGAN | 0 |  | 1 | [5 empty] | 784163.64 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Kalinga | 340131 | SHS - Lubuagan | LUBUAGAN | 0 |  | 1 | [5 empty] | 979846.65 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Kalinga | 305214 | Central Pasil National High School | PASIL | 0 |  | 1 | [5 empty] | 1792826.18 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Kalinga | 305201 | Cal-owan Agricultural Vocational National High School | PINUKPUK | 0 |  | 1 | [5 empty] | 1088979.46 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Kalinga | 305216 | Pinukpuk Vocational School | PINUKPUK | 0 |  | 1 | [5 empty] | 1895776.58 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Kalinga | 305217 | Rizal National School of Arts & Trades | RIZAL (LIWAN) | 0 |  | 1 | [5 empty] | 2016943.01 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Kalinga | 305218 | Macutay-Palao National High School | RIZAL (LIWAN) | 0 |  | 1 | [5 empty] | 1090872.87 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Kalinga | 305211 | Magtoma Pangol NHS-Main | TANUDAN | 0 |  | 1 | [5 empty] | 967916.92 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Kalinga | 305208 | Southern Tinglayan National High School | TINGLAYAN | 0 |  | 1 | [5 empty] | 984873.35 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Kalinga | 305220 | Bangad National High School | TINGLAYAN | 0 |  | 1 | [5 empty] | 1506409.43 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305242 | Eastern Bontoc NAVHS | BARLIG | 0 |  | 1 | [5 empty] | 1559940.28 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305244 | Guinzadan National High School | BAUKO | 0 |  | 1 | [5 empty] | 1722122.63 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305252 | Mt. Data National High School | BAUKO | 0 |  | 1 | [5 empty] | 1255178.1 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305259 | Otucan-Bila National High School | BAUKO | 0 |  | 1 | [5 empty] | 1195926.78 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305237 | Besao National High School | BESAO | 0 |  | 1 | [5 empty] | 703212.95 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305260 | Panabungen School of Arts, trades, and Home Industries | BESAO | 0 |  | 1 | [5 empty] | 1490662.56 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305255 | Mt. Prov. Gen. Comprehensive HS | BONTOC (Capital) | 0 |  | 1 | [5 empty] | 1648360.08 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 340155 | Natonin SHS_Stand Alone | NATONIN | 0 |  | 1 | [5 empty] | 943990.98 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305230 | Bacarri National Trade & Agricultural School | PARACELIS | 0 |  | 1 | [5 empty] | 1297230.2 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305231 | Paracelis Technical & Vocational High School | PARACELIS | 0 |  | 1 | [5 empty] | 1913096.56 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305239 | Butigue National High School | PARACELIS | 0 |  | 1 | [5 empty] | 1396732.14 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305261 | Paracelis National High School | PARACELIS | 0 |  | 1 | [5 empty] | 1637975.75 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 319220 | Anonat National Agricultural and Vocational High School | PARACELIS | 0 |  | 1 | [5 empty] | 1351919.59 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305262 | Pingad National High School | SABANGAN | 0 |  | 1 | [5 empty] | 1121246.16 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305263 | Sabangan National High School | SABANGAN | 0 |  | 1 | [5 empty] | 1691013.04 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305264 | Sadanga National High School | SADANGA | 0 |  | 1 | [5 empty] | 1041709.2 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305265 | Sagada National High School | SAGADA | 0 |  | 1 | [5 empty] | 923929.67 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305266 | Ankileng NHS (Suyo NHS) | SAGADA | 0 |  | 1 | [5 empty] | 1041024.74 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305240 | Cagubatan National High School | TADIAN | 0 |  | 1 | [5 empty] | 1035377.89 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305247 | Lubon National High School | TADIAN | 0 |  | 1 | [5 empty] | 1055606.66 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305251 | Masla National High School | TADIAN | 0 |  | 1 | [5 empty] | 1022374.5 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Mt. Province | 305267 | Tadian School of Arts & Trades | TADIAN | 0 |  | 1 | [5 empty] | 2542733.34 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Tabuk City | 305195 | Agbannawag National High School | CITY OF TABUK (Capital) | 0 |  | 1 | [5 empty] | 1437535.17 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Tabuk City | 305205 | Kalinga National High School | CITY OF TABUK (Capital) | 0 |  | 1 | [5 empty] | 2823729.29 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Tabuk City | 305212 | Nambaran Agro-Industrial National High School | CITY OF TABUK (Capital) | 0 |  | 1 | [5 empty] | 1471209.15 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Tabuk City | 305221 | Tabuk City National High School | CITY OF TABUK (Capital) | 0 |  | 1 | [5 empty] | 3248280.45 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CARAGA | Dinagat Island | 304815 | Cagdianao NHS | CAGDIANAO | 0 |  | 1 | [5 empty] | 2138817.1 | UPGRADING | 1 | Completed | 100% | 100% | NOV. 17, 2018 |  |  | INFRA18-002-02 |  |  |  |  | JULY 11, 2018 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Dinagat Island | 304822 | Dinagat School of Fisheries | DINAGAT | 0 |  | 1 | [5 empty] | 2371554.25 | UPGRADING | 1 | Completed | 100% | 100% | NOV. 17, 2018 |  |  | INFRA18-002-04 |  |  |  |  | JULY 11, 2018 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Dinagat Island | 324406 | Primitivo J. Ebol Memorial National High School | DINAGAT | 0 |  | 1 | [5 empty] | 2001578.36 | UPGRADING | 1 | Completed | 100% | 100% | NOV. 17, 2018 |  |  | INFRA18-002-05 |  |  |  |  | JULY 11, 2018 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Dinagat Island | 304808 | Albor NHS | LIBJO (ALBOR) | 0 |  | 1 | [5 empty] | 2335700.05 | UPGRADING | 1 | Completed | 100% | 100% | NOV. 17, 2018 |  |  | INFRA18-002-01 |  |  |  |  | JULY 11, 2018 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Dinagat Island | 304824 | Don Ruben E. Ecleo Sr. MNHS | SAN JOSE (Capital) | 0 |  | 1 | [5 empty] | 2337098.19 | UPGRADING | 1 | Completed | 100% | 100% | NOV. 17, 2018 |  |  | INFRA18-002-03 |  |  |  |  | JULY 11, 2018 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Dinagat Island | 304854 | Tubajon NHS | TUBAJON | 0 |  | 1 | [5 empty] | 2390442.95 | UPGRADING | 1 | Completed | 100% | 100% | NOV. 17, 2018 |  |  | INFRA18-002-06 |  |  |  |  | JULY 11, 2018 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Siargao | 304774 | Dapa NHS | DAPA | 1 |  | 1 | [5 empty] | 2929746.09 | UPGRADING | 1 | ONGOING | 0% | 80% | 0% |  |  | BEFF-INFRA2018-008 | February 8 ,2018 | February 19, 2018 | March 5, 2018 | May 3, 2018 | May 16, 2018 | Vic B. Borja Construction | 2905000 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CARAGA | Siargao | 304783 | Del Carmen NHS | DEL CARMEN | 1 |  | 1 | [5 empty] | 2271995.06 | UPGRADING | 1 | ONGOING | 0% | 80% | 0% |  |  | BEFF-INFRA2018-009 | February 8 ,2018 | February 19, 2018 | March 5, 2018 | May 3, 2018 | May 16, 2018 | Vic B. Borja Construction | 2250000 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CARAGA | Siargao | 304777 | Gen Luna NHS | GENERAL LUNA | 1 |  | 1 | [5 empty] | 2775183.35 | UPGRADING | 1 | ONGOING | 0% | 80% | 0% |  |  | BEFF-INFRA2018-010 | February 8 ,2018 | February 19, 2018 | March 5, 2018 | May 3, 2018 | May 16, 2018 | Vic B. Borja Construction | 2750000 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CARAGA | Surigao del Norte | 304813 | Bacuag Nat'L Agro-Indust'L Sch. | BACUAG | 2 |  | 1 | [5 empty] | 1168482.85 | UPGRADING | 1 | completed | 100% | 100% | 100% | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 304817 | Campo NHS | BACUAG | 2 |  | 1 | [5 empty] | 1178282.61 | UPGRADING | 1 | awaiting for energization of Elec. Coop | 95% | 95% | 95% | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CARAGA | Surigao del Norte | 317806 | Payapag NHS | BACUAG | 2 |  | 1 | [5 empty] | 1129680.82 | UPGRADING | 1 | awaiting for energization of Elec. Coop | 95% | 95% | 95% | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CARAGA | Surigao del Norte | 304826 | Gigaquit Nat'l. Sch. of Home Industries | GIGAQUIT | 2 |  | 1 | [5 empty] | 1915898.59 | UPGRADING | 1 | awaiting for energization of Elec. Coop | 95% | 95% | 95% | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CARAGA | Surigao del Norte | 304829 | Mainit NHS | MAINIT | 2 |  | 1 | [5 empty] | 1336228.12 | UPGRADING | 1 | awaiting for energization of Elec. Coop | 95% | 95% | 95% | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CARAGA | Surigao del Norte | 304834 | Matin-ao National High School | MAINIT | 2 |  | 1 | [5 empty] | 1284562.4 | UPGRADING | 1 | awaiting for energization of Elec. Coop | 95% | 95% | 95% | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CARAGA | Surigao del Norte | 304835 | Hacienda NHS | MAINIT | 2 |  | 1 | [5 empty] | 1271122.29 | UPGRADING | 1 | Completed | 45% | 100% | 2018-08-29 |  |  | 023-2018 | 2018-04-04 | 2018-05-04 | 2018-05-22 | 2018-05-24 | 2018-06-15 | Maxter Resources, Inc. | 1263572.957 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 317803 | Magpayang NHS | MAINIT | 2 |  | 1 | [5 empty] | 1129680.82 | UPGRADING | 1 | Completed | 75% | 100% | 2018-07-19 |  |  | 020-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. | 1121180.273 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 304837 | Placer NHS | PLACER | 2 |  | 1 | [5 empty] | 1284443.5 | UPGRADING | 1 | Completed | 35% | 100% | 2018-08-05 |  |  | 019-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Digos Constrak Corporation | 1276827.897 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 304845 | Amando A. Fabio MNHS | PLACER | 2 |  | 1 | [5 empty] | 1178282.61 | UPGRADING | 1 | Completed | 35% | 100% | 2018-08-05 |  |  | 019-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Digos Constrak Corporation | 1171195.167 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 304814 | Balite NHS | SAN FRANCISCO (ANAO-AON) | 2 |  | 1 | [5 empty] | 1163382.98 | UPGRADING | 1 | Completed | 75% | 100% | 2018-08-03 |  |  | 016-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. | 1150077.79 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 304843 | San Francisco NHS | SAN FRANCISCO (ANAO-AON) | 2 |  | 1 | [5 empty] | 1129680.82 | UPGRADING | 1 | Completed | 75% | 100% | 2018-08-03 |  |  | 016-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. | 1116543.31 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 304849 | T.S Pantilo, Sr. MNHS | SISON | 2 |  | 1 | [5 empty] | 1141983.51 | UPGRADING | 1 | Completed | 75% | 100% | 2018-07-19 |  |  | 021-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. | 1132847.827 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 317808 | Dakung Patag NHS - Annex (TS PSMHS) | SISON | 2 |  | 1 | [5 empty] | 1129680.82 | UPGRADING | 1 | Completed | 75% | 100% | 2018-07-19 |  |  | 021-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. | 1120606.347 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 304847 | Surigao Del Norte NHS | SURIGAO CITY (Capital) | 2 |  | 1 | [5 empty] | 1900350.59 | UPGRADING | 1 | Completed | 75% | 100% | 2018-08-03 |  |  | 016-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. | 1883378.9 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 304812 | Tagana-an NHS (ASA NHS) | TAGANA-AN | 2 |  | 1 | [5 empty] | 1280970.03 | UPGRADING | 1 | Completed | 45% | 100% | 2018-08-05 |  |  | 019-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Digos Constrak Corporation | 1273371.717 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 304853 | Timamana National High School | TUBOD | 2 |  | 1 | [5 empty] | 1129680.82 | UPGRADING | 1 | Completed | 35% | 100% | 2018-08-29 |  |  | 024-2018 | 2018-04-04 | 2018-05-04 | 2018-05-22 | 2018-05-24 | 2018-06-15 | Maxter Resources, Inc. | 1118994.447 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 304855 | Tubod NHS | TUBOD | 2 |  | 1 | [5 empty] | 1129680.82 | UPGRADING | 1 | Completed | 35% | 100% | 2018-08-29 |  |  | 024-2018 | 2018-04-04 | 2018-05-04 | 2018-05-22 | 2018-05-24 | 2018-06-15 | Maxter Resources, Inc. | 1118994.447 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
NCR | Caloocan City | 500330 | Tandang Sora IS | Caloocan City | 2 |  | 1 | [5 empty] | 1957934.42 | UPGRADING | 1 | Completed | 30% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
NCR | Quezon City | 305320 | Balingasa HS | Quezon City | 1 |  | 1 | [5 empty] | 3168383.07 | UPGRADING | 1 | NOT YET STARTED | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | Y
NCR | Quezon City | 305322 | Eulogio Rodriguez, Jr. HS | Quezon City | 1 |  | 1 | [5 empty] | 3248178.64 | UPGRADING | 1 | Completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
NCR | Quezon City | 305329 | Quezon City Science HS | Quezon City | 1 |  | 1 | [5 empty] | 5943563.39 | UPGRADING | 1 | NOT YET STARTED | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | Y
NCR | Quezon City | 319506 | National Orthopedic Hospital School for Crippled Children | Quezon City | 1 |  | 1 | [5 empty] | 1105837.87 | UPGRADING | 1 | Completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
NCR | Quezon City | 305355 | Carlos L. Albert HS | Quezon City | 4 |  | 1 | [5 empty] | 4917426.49 | UPGRADING | 1 | NOT YET STARTED | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | Y
NCR | Quezon City | 305361 | Manuel A. Roxas HS | Quezon City | 4 |  | 1 | [5 empty] | 3106367.81 | UPGRADING | 1 | NOT YET STARTED | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | Y
NCR | Quezon City | 305333 | Culiat HS | Quezon City | 6 |  | 1 | [5 empty] | 3401452.88 | UPGRADING | 1 | Completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Candon City | 300047 | Candon City High School | CITY OF CANDON | 2 |  | 1 | [5 empty] | 711644.09 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | 2018-11-26 | 2019-02-13 | PB-INFRA-02-2018 |  | 2018-07-07 | 2018-07-17 | 2018-07-17 | 2018-08-20 | 2018-08-28 | MRK SQUARE CONSTRUCTION AND SUPPLY | 705.320.36 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Candon City | 300051 | Dr. Ricardo Gacula Memorial National High School | CITY OF CANDON | 2 |  | 1 | [5 empty] | 958451.44 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | 2018-11-26 | 2019-02-13 | PB-INFRA-02-2018 |  | 2018-07-07 | 2018-07-17 | 2018-07-17 | 2018-08-20 | 2018-08-28 | MRK SQUARE CONSTRUCTION AND SUPPLY | 950712.2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Candon City | 300083 | Sto. Tomas National High School | CITY OF CANDON | 2 |  | 1 | [5 empty] | 880009.36 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | 2018-11-26 | 2019-02-13 | PB-INFRA-02-2018 |  | 2018-07-07 | 2018-07-17 | 2018-07-17 | 2018-08-20 | 2018-08-28 | MRK SQUARE CONSTRUCTION AND SUPPLY | 873967.44 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Dagupan City | 102157 | East Central IS | DAGUPAN CITY | 4 |  | 1 | [5 empty] | 1567287.75 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | July 4, 2018 | July 4, 2018 | [6 empty] | April 6, 2018 | ZOTA TRADING AND CONSTRUCTION | 1554489.25 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Dagupan City | 102178 | Pugaro IS | DAGUPAN CITY | 4 |  | 1 | [5 empty] | 1069836.08 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | July 4, 2018 | July 4, 2018 | [6 empty] | April 6, 2018 | ZOTA TRADING AND CONSTRUCTION | 1059523.39 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Ilocos Norte | 300001 | Adams NHS | ADAMS | 1 |  | 1 | [5 empty] | 825617.42 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 803491.0678 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | with Time Suspension | Y
Region I | Ilocos Norte | 300009 | Carasi NHS | CARASI | 1 |  | 1 | [5 empty] | 1143193.66 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 1119174.8024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | with Time Suspension | Y
Region I | Ilocos Norte | 300017 | Dumalneg NHS | DUMALNEG | 1 |  | 1 | [5 empty] | 1131237.69 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 1107922.4984 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | with Time Suspension | Y
Region I | Ilocos Sur | 100370 | Bantay East CS | BANTAY | 1 |  | 1 | [5 empty] | 593540.61 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | 2018-11-26 | 2018-11-23 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY | 588675.89 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Ilocos Sur | 100371 | Bantay West Central School | BANTAY | 1 |  | 1 | [5 empty] | 618227.78 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | 2018-11-26 | 2018-11-23 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY | 589207.33 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Ilocos Sur | 100372 | Bulag ES | BANTAY | 1 |  | 1 | [5 empty] | 379200.22 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 | 2018-12-03 |  |  | 2018-08-30 |  | 2018-09-06 | 2018-09-07 | 2018-09-10 | RAMSA CONSTRUCTION & SUPPLY | 375489.93 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Ilocos Sur | 300038 | Bantay NHS | BANTAY | 1 |  | 1 | [5 empty] | 686696.24 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | 2018-11-26 | 2018-12-03 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY | 648431.79 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Ilocos Sur | 300045 | Caoayan NHS | CAOAYAN | 1 |  | 1 | [5 empty] | 986746.23 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | 2018-11-26 | 2019-03-21 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY | 979288.47 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Ilocos Sur | 300035 | SAN JUAN NHS | SAN JUAN (LAPOG) | 1 |  | 1 | [5 empty] | 1092784.66 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | 2018-11-26 | 2019-03-29 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY | 1085483.84 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Ilocos Sur | 100617 | San Vicente IS | SAN VICENTE | 1 |  | 1 | [5 empty] | 808567.21 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | 2018-11-26 | 2019-03-21 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY | 803172.25 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Ilocos Sur | 300080 | Sinait NHS | SINAIT | 1 |  | 1 | [5 empty] | 557523.26 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | 2018-11-26 | 2019-03-29 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY | 534791.41 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Ilocos Sur | 300063 | Narvacan Nat'l. Central HS | NARVACAN | 2 |  | 1 | [5 empty] | 629893.44 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | 2018-11-26 | 2019-03-21 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY | 624266.05 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Ilocos Sur | 320901 | Mabilbila IS | SANTA | 2 |  | 1 | [5 empty] | 947353.53 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | 2018-11-26 | 2018-11-23 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY | 940831.52 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Ilocos Sur | 300077 | Santa Maria NHS | SANTA MARIA | 2 |  | 1 | [5 empty] | 887388.59 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | 2018-11-26 |  |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY | 882020.33 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | La Union | 300106 | Balaoan NHS-Castor Concepcion MNHS | BALAOAN | 1 |  | 1 | [5 empty] | 1536816.3 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES | 1362570.53 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | La Union | 300124 | Oanari NHS | LUNA | 1 |  | 1 | [5 empty] | 969820.67 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES | 860218.38 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | La Union | 321018 | LUNA NATIONAL VOCATIONAL HIGH SCHOOL | LUNA | 1 |  | 1 | [5 empty] | 1006982.57 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES | 891632.77 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | La Union | 300097 | Balbalayang NHS | SAN GABRIEL | 1 |  | 1 | [5 empty] | 1092741.59 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES | 968373.08 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | La Union |  | SAN JUAN SENIOR HIGH SCHOOL | SAN JUAN | 1 |  | 1 | [5 empty] | 1011563.33 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES | 894104.76 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | La Union | 300093 | Aringay NHS | ARINGAY | 2 |  | 1 | [5 empty] | 1789981.7 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [9 empty] | NMDC CONSTRUCTION CORPORATION | 1780026.31 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | La Union | 300090 | Eulogio Clarence De Guzman Junior Memorial National Vocational High School | BAUANG | 2 |  | 1 | [5 empty] | 956985.36 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES | 904095.35 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | La Union | 300128 | Paringao NHS | BAUANG | 2 |  | 1 | [5 empty] | 970724.94 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES | 917914.02 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | La Union | 300136 | San Gregorio National High School | CABA | 2 |  | 1 | [5 empty] | 1025780.07 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [9 empty] | NMDC CONSTRUCTION CORPORATION | 1019626.69 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | La Union | 300091 | Amlang-Nagtagaan NHS | ROSARIO | 2 |  | 1 | [5 empty] | 1163070.09 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [9 empty] | NMDC CONSTRUCTION CORPORATION | 1156233.67 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | La Union | 300152 | Tubao National High School | TUBAO | 2 |  | 1 | [5 empty] | 1949479.54 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [9 empty] | NMDC CONSTRUCTION CORPORATION | 1938730.64 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Pangasinan I, Lingayen | 300192 | Dacap Norte NHS | BANI | 1 |  | 1 | [5 empty] | 459052.5 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan I, Lingayen | 500608 | BANI EAST INTEGRATED SCHOOL | BANI | 1 |  | 1 | [5 empty] | 1238583.7 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan I, Lingayen | 300268 | Zaragosa NHS | BOLINAO | 1 |  | 1 | [5 empty] | 1709137.99 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan I, Lingayen | 500441 | Dasol IS | DASOL | 1 |  | 1 | [5 empty] | 1008247.87 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan I, Lingayen | 300255 | Sual National High School | SUAL | 1 |  | 1 | [5 empty] | 1188525.14 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan I, Lingayen | 300267 | Irene Rayos Ombac NHS | BUGALLON | 2 |  | 1 | [5 empty] | 459052.5 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan I, Lingayen | 300233 | Pangasinan NHS | LINGAYEN (Capital) | 2 |  | 1 | [5 empty] | 1301990.03 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan I, Lingayen | 300234 | Pangasinan SAT | LINGAYEN (Capital) | 2 |  | 1 | [5 empty] | 1200219.41 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan I, Lingayen | 300236 | Urbiztondo National High School | URBIZTONDO | 2 |  | 1 | [5 empty] | 923773.32 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan I, Lingayen | 300168 | Bayambang NHS (Bayambang) | BAYAMBANG | 3 |  | 1 | [5 empty] | 1086061.05 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Pangasinan I, Lingayen | 300188 | Moises B. Rebamontan NHS | BAYAMBANG | 3 |  | 1 | [5 empty] | 577242.58 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Pangasinan I, Lingayen | 300259 | Tanolong National High School | BAYAMBANG | 3 |  | 1 | [5 empty] | 654297.57 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Pangasinan I, Lingayen | 300224 | Mapandan National High School | MAPANDAN | 3 |  | 1 | [5 empty] | 1622181.45 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Pangasinan I, Lingayen | 300265 | Torres NHS | MAPANDAN | 3 |  | 1 | [5 empty] | 954894.47 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Pangasinan I, Lingayen | 300237 | Payas NHS | SANTA BARBARA | 3 |  | 1 | [5 empty] | 641892.95 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Pangasinan II, Binalonan | 300294 | Cabanbanan NHS | MANAOAG | 4 |  | 1 | [5 empty] | 815407.48 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 30% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 500383 | Mangaldan IS | MANGALDAN | 4 |  | 1 | [5 empty] | 1560913.55 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 30% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300272 | Ambalangan Dalin NHS | SAN FABIAN | 4 |  | 1 | [5 empty] | 693500.18 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 30% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300274 | Anonang NHS | SAN FABIAN | 4 |  | 1 | [5 empty] | 876203.79 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 30% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 500006 | San Fabian IS | SAN FABIAN | 4 |  | 1 | [5 empty] | 897261.77 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 30% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300321 | Lobong NHS | SAN JACINTO | 4 |  | 1 | [5 empty] | 824735.39 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 30% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300348 | San Jacinto National High School | SAN JACINTO | 4 |  | 1 | [5 empty] | 808925.25 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 30% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300355 | San Pedro Apartado NHS | ALCALA | 5 |  | 1 | [5 empty] | 701069.14 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 30% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300329 | San Pedro Apartado NHS | POZZORUBIO | 5 |  | 1 | [5 empty] | 904428.35 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 30% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300284 | Barangobong NHS | VILLASIS | 5 |  | 1 | [5 empty] | 682758.6 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 30% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 500385 | DUNGON IS | VILLASIS | 5 |  | 1 | [5 empty] | 581796.47 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 30% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300340 | Robert B. Estrella Memorial NHS | ROSALES | 6 |  | 1 | [5 empty] | 655749.22 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 30% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | San Carlos City | 300379 | Cobol NHS | SAN CARLOS CITY | 3 |  | 1 | [5 empty] | 954866.98 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | San Carlos City | 300382 | Libas NHS | SAN CARLOS CITY | 3 |  | 1 | [5 empty] | 1009366.63 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | San Carlos City | 300385 | Malacanang NHS | SAN CARLOS CITY | 3 |  | 1 | [5 empty] | 1016668.74 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Urdaneta City | 300397 | Camabu NHS | CITY OF URDANETA | 5 |  | 1 | [5 empty] | 847104.78 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | 8-16-2018 | 10-15-2018 |  |  | 2018-02-04 | 2018-10-04 | 4-23-2018 | 2018-07-05 | 2018-11-05 | LAV Construction | 783323.06 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Urdaneta City | 300406 | Nancalobasaan NHS | CITY OF URDANETA | 5 |  | 1 | [5 empty] | 1006805.78 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | 8-16-2018 | 10-15-2018 |  |  | 2018-02-04 | 2018-10-04 | 4-23-2018 | 2018-07-05 | 2018-11-05 | LAV Construction | 930663.77 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Vigan City | 100786 | Burgos Memorial School West | CITY OF VIGAN (Capital) | 1 |  | 1 | [5 empty] | 1258735.11 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% |  |  |  |  | 2018-02-12 | 2018-02-26 | 2018-03-12 | 2018-04-17 | 2018-04-23 | ELKAN Engineering Services and General Merchandise | 1218637.93 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Vigan City | 100798 | San Julian ES | CITY OF VIGAN (Capital) | 1 |  | 1 | [5 empty] | 220225.14 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 2018-02-12 | 2018-02-26 | 2018-03-12 | 2018-04-17 | 2018-04-23 | ELKAN Engineering Services and General Merchandise | 219081.49 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Vigan City | 100800 | Vigan CS | CITY OF VIGAN (Capital) | 1 |  | 1 | [5 empty] | 1032751.73 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% |  |  |  |  | 2018-02-12 | 2018-02-26 | 2018-03-12 | 2018-04-17 | 2018-04-23 | ELKAN Engineering Services and General Merchandise | 1024505.51 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region II | Batanes | 300415 | Ivana NHS | IVANA | 0 |  | 1 | [5 empty] | 1126860.32 | UPGRADING | 1 | ONGOING | 25% | 85% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | No interested bidders
Region II | Batanes | 300416 | Mahatao NHS | MAHATAO | 0 |  | 1 | [5 empty] | 1095087.83 | UPGRADING | 1 | ONGOING | 25% | 85% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | No interested bidders
Region II | Batanes | 300417 | Sabtang National School of Fisheries | SABTANG | 0 |  | 1 | [5 empty] | 1095087.83 | UPGRADING | 1 | ONGOING | 25% | 85% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | No interested bidders
Region II | Cagayan | 300420 | Afusing NHS | ALCALA | 1 |  | 1 | [5 empty] | 495971.47 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300421 | Alcala Rural School | ALCALA | 1 |  | 1 | [5 empty] | 518889.44 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300437 | Bukig National Agr'l. and Tech. School | APARRI | 1 |  | 1 | [5 empty] | 730017.81 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300470 | Aparri West National High School | APARRI | 1 |  | 1 | [5 empty] | 567838.55 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300471 | Aparri East National High School | APARRI | 1 |  | 1 | [5 empty] | 699410.46 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 102498 | San Antonio ES | BAGGAO | 1 |  | 1 | [5 empty] | 1753452.5 | SOLAR PANEL | 1 | ONGOING |  | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award | N
Region II | Cagayan | 102503 | Tabugan ES | BAGGAO | 1 |  | 1 | [5 empty] | 559889.96 | SOLAR PANEL | 1 | ONGOING |  | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award | N
Region II | Cagayan | 155053 | Cagurungan Primary School | BAGGAO | 1 |  | 1 | [5 empty] | 559889.96 | SOLAR PANEL | 1 | ONGOING |  | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award | N
Region II | Cagayan | 300429 | Baggao NAS | BAGGAO | 1 |  | 1 | [5 empty] | 643414.67 | UPGRADING | 1 | ONGOING |  | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300430 | Baggao National School of Arts & Trades | BAGGAO | 1 |  | 1 | [5 empty] | 589120.28 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300432 | Hacienda Intal NHS | BAGGAO | 1 |  | 1 | [5 empty] | 571264.33 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300433 | Imurung NHS | BAGGAO | 1 |  | 1 | [5 empty] | 2011343.55 | UPGRADING | 1 | ONGOING | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 306020 | AGAMAN NATIONAL HIGH SCHOOL | BAGGAO | 1 |  | 1 | [5 empty] | 634259.39 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 306426 | Camalaniugan National High School- Catotoran Annex | CAMALANIUGAN | 1 |  | 1 | [5 empty] | 588020.29 | UPGRADING | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Cagayan | 300440 | Calaoagan Dackel NHS | GATTARAN | 1 |  | 1 | [5 empty] | 637964.57 | UPGRADING | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Cagayan | 155051 | Laoc Primary School | GONZAGA | 1 |  | 1 | [5 empty] | 1846756.72 | SOLAR PANEL | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award | N
Region II | Cagayan | 300465 | Ipil National High School | GONZAGA | 1 |  | 1 | [5 empty] | 2263197.02 | UPGRADING | 1 | Completed | 98% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Cagayan | 300482 | Rebecca NHS | GONZAGA | 1 |  | 1 | [5 empty] | 628809.3 | UPGRADING | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Cagayan | 300483 | Gonzaga National High School | GONZAGA | 1 |  | 1 | [5 empty] | 617102.21 | UPGRADING | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Cagayan | 300469 | LAL-LO NATIONAL HIGH SCHOOL | LAL-LO | 1 |  | 1 | [5 empty] | 709465.42 | UPGRADING | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Cagayan | 306004 | Magapit NHS | LAL-LO | 1 |  | 1 | [5 empty] | 515742.71 | UPGRADING | 1 | Completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | SANTA ANA | 1 |  | 1 | [5 empty] | 841324.37 | UPGRADING | 1 | Completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Cagayan | 300490 | Sta. Teresita NHS | SANTA TERESITA | 1 |  | 1 | [5 empty] | 602505.52 | UPGRADING | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Cagayan | 300473 | Libertad NHS | ABULUG | 2 |  | 1 | [5 empty] | 1233921.78 | UPGRADING | 1 | ONGOING | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300424 | Allacapan VHS | ALLACAPAN | 2 |  | 1 | [5 empty] | 740050.2 | UPGRADING | 1 | ONGOING | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 500065 | Mapurao Integ. Learning School | ALLACAPAN | 2 |  | 1 | [5 empty] | 671431.74 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300434 | Ballesteros NHS | BALLESTEROS | 2 |  | 1 | [5 empty] | 740050.2 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 102586 | Caniwalan ES | CALAYAN | 2 |  | 1 | [5 empty] | 1586151.2 | SOLAR PANEL | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award | N
Region II | Cagayan | 102587 | Dadao ES | CALAYAN | 2 |  | 1 | [5 empty] | 1688631.96 | UPGRADING | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Cagayan | 102593 | Morol ES | CALAYAN | 2 |  | 1 | [5 empty] | 930135.8 | SOLAR PANEL | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award | N
Region II | Cagayan | 155040 | Bibigsan PS | CALAYAN | 2 |  | 1 | [5 empty] | 663729.76 | SOLAR PANEL | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award | N
Region II | Cagayan | 300441 | Calayan HS | CALAYAN | 2 |  | 1 | [5 empty] | 1478886.29 | SOLAR PANEL | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award | N
Region II | Cagayan | 300450 | Claveria RVS | CLAVERIA | 2 |  | 1 | [5 empty] | 501909.48 | UPGRADING | 1 | ONGOING | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300451 | Claveria SAT | CLAVERIA | 2 |  | 1 | [5 empty] | 501909.48 | UPGRADING | 1 | ONGOING | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300438 | Cabatacan National High School | LASAM | 2 |  | 1 | [5 empty] | 2131509.18 | UPGRADING | 1 | ONGOING | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300439 | Nabannagan National High School | LASAM | 2 |  | 1 | [5 empty] | 1915584.2 | UPGRADING | 1 | ONGOING | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300497 | Western Cagayan SAT | LASAM | 2 |  | 1 | [5 empty] | 1118621.25 | UPGRADING | 1 | ONGOING | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300481 | Piat National HS | PIAT | 2 |  | 1 | [5 empty] | 964556.11 | UPGRADING | 1 | ONGOING | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 102854 | Kittag ES | SANCHEZ-MIRA | 2 |  | 1 | [5 empty] | 527749.68 | SOLAR PANEL | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | No guildelines for Solar Panel | N
Region II | Cagayan | 102862 | Santiago Elementary School | SANCHEZ-MIRA | 2 |  | 1 | [5 empty] | 734565.68 | SOLAR PANEL | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | No guildelines for Solar Panel | N
Region II | Cagayan | 155046 | Pureg Elementary School | SANCHEZ-MIRA | 2 |  | 1 | [5 empty] | 506644.68 | SOLAR PANEL | 1 | Completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | No guildelines for Solar Panel | N
Region II | Cagayan | 300486 | Sanchez Mira SAT | SANCHEZ-MIRA | 2 |  | 1 | [5 empty] | 740050.2 | UPGRADING | 1 | ONGOING | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300489 | Sta. Praxedes HS | SANTA PRAXEDES | 2 |  | 1 | [5 empty] | 570762.04 | UPGRADING | 1 | ONGOING | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 306017 | Amulung NHS - Dadda Ext. | AMULUNG | 3 |  | 1 | [5 empty] | 1146918.75 | UPGRADING | 1 | ONGOING | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300458 | Enrile Vocational High School | ENRILE | 3 |  | 1 | [5 empty] | 668475.19 | UPGRADING | 1 | Completed | 98% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Cagayan | 300459 | Western Enrile Vocational High School | ENRILE | 3 |  | 1 | [5 empty] | 824448.52 | UPGRADING | 1 | Completed | 98% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Cagayan | 300472 | Lemu NHS | ENRILE | 3 |  | 1 | [5 empty] | 579730.22 | UPGRADING | 1 | ONGOING | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 306421 | CARIDAD B. TRINIDAD NHS | IGUIG | 3 |  | 1 | [5 empty] | 612469.14 | UPGRADING | 1 | ONGOING | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300445 | Penablanca National High School | PEÑABLANCA | 3 |  | 1 | [5 empty] | 620842.75 | UPGRADING | 1 | ONGOING | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300446 | Cabbo NHS | PEÑABLANCA | 3 |  | 1 | [5 empty] | 599373.57 | UPGRADING | 1 | Completed | 98% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Cagayan | 300457 | Penablanca East NHS | PEÑABLANCA | 3 |  | 1 | [5 empty] | 730602.29 | UPGRADING | 1 | ONGOING | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300467 | Itawes National High School | TUAO | 3 |  | 1 | [5 empty] | 730602.29 | UPGRADING | 1 | ONGOING | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300468 | Itawes Nat'l.l Agr'l. & Tech'l. School - Bagumbayan Annex | TUAO | 3 |  | 1 | [5 empty] | 538676.19 | UPGRADING | 1 | ONGOING | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300492 | Tuao Voc'l. and Tech'l. School | TUAO | 3 |  | 1 | [5 empty] | 750245.64 | UPGRADING | 1 | ONGOING | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cagayan | 300493 | Tuao Voc'l. and Tech'l. School - Culung Annex | TUAO | 3 |  | 1 | [5 empty] | 532184.83 | UPGRADING | 1 | Completed | 98% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Cagayan | 306019 | Tuao Voc'l. and Tech'l. School - Malummin Annex | TUAO | 3 |  | 1 | [5 empty] | 505444.28 | UPGRADING | 1 | ONGOING | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | For award
Region II | Cauayan City | 103215 | Faustino ES | CITY OF CAUAYAN | 3 |  | 1 | [5 empty] | 1416994.55 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Cauayan City | 103241 | Sillawit ES | CITY OF CAUAYAN | 3 |  | 1 | [5 empty] | 2061137.84 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Cauayan City | 300614 | Villaluna NHS | CITY OF CAUAYAN | 3 |  | 1 | [5 empty] | 618992.18 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Cauayan City | 306107 | WEST TABACAL REGION NATIONAL HIGH SCHOOL | CITY OF CAUAYAN | 3 |  | 1 | [5 empty] | 2160530.55 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Cauayan City | 323901 | Cauayan City NHS - Research Annex | CITY OF CAUAYAN | 3 |  | 1 | [5 empty] | 569092.68 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Cauayan City | 323903 | Villa Concepcion HS - Rogus Ext. | CITY OF CAUAYAN | 3 |  | 1 | [5 empty] | 348325.74 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | City of Ilagan | 300542 | Isabela NHS - Main | ILAGAN (Capital) | 1 |  | 1 | [5 empty] | 1452300.94 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | City of Ilagan | 300583 | San Antonio Nat'l. Agro-Ind'l. & Voc'l. HS | ILAGAN (Capital) | 1 |  | 1 | [5 empty] | 679654.89 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | City of Ilagan | 306105 | ISAT-Main | ILAGAN (Capital) | 1 |  | 1 | [5 empty] | 3689427.49 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 300520 | Delfin Albano HS-Main | CABAGAN | 1 |  | 1 | [5 empty] | 1897430.9 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300521 | Alfreda Albano NHS - Magassi, Cabagan | CABAGAN | 1 |  | 1 | [5 empty] | 1800665.03 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300522 | Delfin Albano HS - San Juan Annex | CABAGAN | 1 |  | 1 | [5 empty] | 1406343.79 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300585 | San Antonio NHS | DELFIN ALBANO (MAGSAYSAY) | 1 |  | 1 | [5 empty] | 2827752.29 | UPGRADING | 1 | Completed | 80% | 1100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300554 | Isabela SF | PALANAN | 1 |  | 1 | [5 empty] | 2206445.44 | SOLAR PANEL | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award | N
Region II | Isabela | 300601 | St. Paul Voc'l. & Ind'l. HS-Main | SAN PABLO | 1 |  | 1 | [5 empty] | 1323322.14 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300603 | Santa Maria High School | SANTA MARIA | 1 |  | 1 | [5 empty] | 1646981.65 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300606 | Sto Tomas NHS | SANTO TOMAS | 1 |  | 1 | [5 empty] | 1649011.33 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300609 | Tumauini NHS | TUMAUINI | 1 |  | 1 | [5 empty] | 1628465.08 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 306153 | Cumabao IS | TUMAUINI | 1 |  | 1 | [5 empty] | 1451220.68 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300503 | Benito Soliven NHS | BENITO SOLIVEN | 2 |  | 1 | [5 empty] | 1176226.66 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300509 | BURGOS NHS (formerly Caliguian NHS-Main) | BURGOS | 2 |  | 1 | [5 empty] | 1414778.54 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300511 | San Antonino NHS | BURGOS | 2 |  | 1 | [5 empty] | 1273274.55 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300561 | Mallig NHS (formerly Mallig NHS - Main) | MALLIG | 2 |  | 1 | [5 empty] | 1148985.74 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 306110 | San Jose NHS (formerly Mallig HS -San Jose Norte Annex) | MALLIG | 2 |  | 1 | [5 empty] | 1190682.84 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300568 | Quezon HS - Main | QUEZON | 2 |  | 1 | [5 empty] | 1181729.01 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300562 | Munoz HS | ROXAS | 2 |  | 1 | [5 empty] | 1173740.73 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300579 | Roxas NHS-Main | ROXAS | 2 |  | 1 | [5 empty] | 1999770.49 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 306111 | Monico Rarama NHS (Munoz HS -San Pedro Extension) | ROXAS | 2 |  | 1 | [5 empty] | 1252371.25 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 500094 | Simimbaan Integrated School | ROXAS | 2 |  | 1 | [5 empty] | 1218106.74 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300512 | Callang NHS - Main | SAN MANUEL | 2 |  | 1 | [5 empty] | 1744759.24 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300514 | Sandiat NHS | SAN MANUEL | 2 |  | 1 | [5 empty] | 1547898.63 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300565 | Palayan Region HS | ALICIA | 3 |  | 1 | [5 empty] | 1186861.71 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300576 | Rizal Region NHS , Alicia, Isabela | ALICIA | 3 |  | 1 | [5 empty] | 1075486.31 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300506 | Cadaloria HS | ANGADANAN | 3 |  | 1 | [5 empty] | 1049158.75 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300504 | Cabatuan National High School | CABATUAN | 3 |  | 1 | [5 empty] | 1929966.85 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300558 | Luna NHS | LUNA | 3 |  | 1 | [5 empty] | 1195227.54 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300575 | Reina Mercedes Vocational and Industrial School | REINA MERCEDES | 3 |  | 1 | [5 empty] | 1432514.77 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 306116 | Reina Mercedes Vocational High School | REINA MERCEDES | 3 |  | 1 | [5 empty] | 1116614.51 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300590 | San Guillermo Voc'l & Ind'l High Sch. | SAN GUILLERMO | 3 |  | 1 | [5 empty] | 1074656.19 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300581 | Salinungan NHS | SAN MATEO | 3 |  | 1 | [5 empty] | 1245397.84 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300508 | CAGASAT NHS | CORDON | 4 |  | 1 | [5 empty] | 790744.56 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300523 | Diadi Region HS | CORDON | 4 |  | 1 | [5 empty] | 885270.95 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300532 | Dona Josefa E. Marcos HS | CORDON | 4 |  | 1 | [5 empty] | 834063 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 306143 | Cagasat HS-Magsasay Annex | CORDON | 4 |  | 1 | [5 empty] | 813316.04 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300526 | Dinapigue NHS | DINAPIGUE | 4 |  | 1 | [5 empty] | 889647.51 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300529 | Don Mariano Marcos NHS | ECHAGUE | 4 |  | 1 | [5 empty] | 784636.12 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300539 | Highway Region NHS | ECHAGUE | 4 |  | 1 | [5 empty] | 820545.41 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300566 | Pangal Sur HS | ECHAGUE | 4 |  | 1 | [5 empty] | 831472.93 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300611 | Ugad HS | ECHAGUE | 4 |  | 1 | [5 empty] | 1062208.47 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300555 | Jones Rural School - Main | JONES | 4 |  | 1 | [5 empty] | 1480331.65 | UPGRADING | 1 | Completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300572 | Gen. Emilio Aguinaldo NHS | RAMON | 4 |  | 1 | [5 empty] | 817580.17 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300574 | Raniag HS | RAMON | 4 |  | 1 | [5 empty] | 1184147.04 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 306142 | San Sebastian Integrated School | RAMON | 4 |  | 1 | [5 empty] | 1149327.62 | UPGRADING | 1 | Completed | 70% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300518 | Dabubu High School Main & Annex | SAN AGUSTIN | 4 |  | 1 | [5 empty] | 1145258.17 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Isabela | 300591 | San Isidro NHS | SAN ISIDRO | 4 |  | 1 | [5 empty] | 903294.53 | UPGRADING | 1 | Completed | 70% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Nueva Vizcaya | 300617 | Ambaguio High School | AMBAGUIO | 0 |  | 1 | [5 empty] | 2380840.46 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region II | Nueva Vizcaya | 300620 | Bambang NHS | BAMBANG | 0 |  | 1 | [5 empty] | 4643660.5 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region II | Nueva Vizcaya | 300635 | Dupax del Norte NHS | DUPAX DEL NORTE | 0 |  | 1 | [5 empty] | 5168669.82 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region II | Nueva Vizcaya | 300628 | Dupax del Sur NHS | DUPAX DEL SUR | 0 |  | 1 | [5 empty] | 1453392.33 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region II | Nueva Vizcaya | 104098 | Papalungan ES | KASIBU | 0 |  | 1 | [5 empty] | 3440083.05 | SOLAR PANEL | 1 | Completed | 85% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region II | Nueva Vizcaya | 104114 | Ban-et PS | KAYAPA | 0 |  | 1 | [5 empty] | 1377860.4 | SOLAR PANEL | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region II | Nueva Vizcaya | 300633 | Martinez Cuyangan NHS | KAYAPA | 0 |  | 1 | [5 empty] | 2511723.29 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region II | Nueva Vizcaya | 306204 | Runruno National High School | QUEZON | 0 |  | 1 | [5 empty] | 2299961.96 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region II | Quirino | 300652 | Aglipay NHS | AGLIPAY | 0 |  | 1 | [5 empty] | 470878.68 | UPGRADING | 1 | Completed |  | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Quirino | 300653 | Victoria HS | AGLIPAY | 0 |  | 1 | [5 empty] | 605581.61 | UPGRADING | 1 | Completed |  | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Quirino | 300663 | Pinaripad NHS | AGLIPAY | 0 |  | 1 | [5 empty] | 722573.4 | UPGRADING | 1 | Completed |  | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Quirino | 300656 | Cabarroguis NSAT | CABARROGUIS (Capital) | 0 |  | 1 | [5 empty] | 938805.89 | UPGRADING | 1 | Completed |  | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Quirino | 300664 | Quirino General HS | CABARROGUIS (Capital) | 0 |  | 1 | [5 empty] | 995383.23 | UPGRADING | 1 | Completed |  | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Quirino | 300666 | Tucod HS | CABARROGUIS (Capital) | 0 |  | 1 | [5 empty] | 618440.27 | UPGRADING | 1 | Completed |  | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Quirino | 300657 | Diffun HS | DIFFUN | 0 |  | 1 | [5 empty] | 865201.89 | UPGRADING | 1 | Completed |  | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Quirino | 300661 | Magsaysay National High School | DIFFUN | 0 |  | 1 | [5 empty] | 561006.88 | UPGRADING | 1 | Completed |  | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Quirino | 300654 | Balligui HS | MADDELA | 0 |  | 1 | [5 empty] | 506369.85 | UPGRADING | 1 | Completed |  | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Quirino | 300660 | Maddela CHS | MADDELA | 0 |  | 1 | [5 empty] | 1181950.74 | UPGRADING | 1 | Completed |  | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Quirino | 306309 | San Martin IS | MADDELA | 0 |  | 1 | [5 empty] | 222063.52 | UPGRADING | 1 | Completed |  | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Quirino | 306317 | Dumabato Integrated School | MADDELA | 0 |  | 1 | [5 empty] | 742761.6 | UPGRADING | 1 | Completed |  | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Quirino | 300662 | Nagtipunan NHS | NAGTIPUNAN | 0 |  | 1 | [5 empty] | 687122.84 | UPGRADING | 1 | Completed |  | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Quirino | 306303 | Sangbay IS | NAGTIPUNAN | 0 |  | 1 | [5 empty] | 350034.81 | UPGRADING | 1 | Completed |  | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Quirino | 306310 | GIAYAN INTEGRATED SCHOOL | NAGTIPUNAN | 0 |  | 1 | [5 empty] | 2653311.76 | SOLAR PANEL | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | No guildelines for Solar Panel | N
Region II | Quirino | 306316 | Scala Integrated School | NAGTIPUNAN | 0 |  | 1 | [5 empty] | 759093.07 | UPGRADING | 1 | Completed |  | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Quirino | 300665 | Saguday NHS | SAGUDAY | 0 |  | 1 | [5 empty] | 716743.19 | UPGRADING | 1 | Completed |  | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Santiago City | 300578 | Rizal National High School | CITY OF SANTIAGO | 4 |  | 1 | [5 empty] | 1974024.18 | UPGRADING | 1 | Completed | 99% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Santiago City | 325201 | Santiago City National High School - Sinsayon | CITY OF SANTIAGO | 4 |  | 1 | [5 empty] | 372407.59 | UPGRADING | 1 | Completed | 99% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Tuguegarao City | 300669 | CATAGGAMAN NHS-SENIOR HIGH SCHOOL | Tuguegarao City | 0 |  | 1 | [5 empty] | 447205.36 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Tuguegarao City | 300668 | CAGAYAN NHS - SENIOR HIGH SCHOOL | Tuguegarao City | 0 |  | 1 | [5 empty] | 762912.06 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Tuguegarao City | 300670 | LINAO NHS - SENIOR HIGH SCHOOL | Tuguegarao City | 0 |  | 1 | [5 empty] | 369305.78 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region II | Tuguegarao City | 306401 | TUGUEGARAO CITY SENIOR HIGH SCHOOL | Tuguegarao City | 0 |  | 1 | [5 empty] | 751115.65 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For award
Region III | Angeles City | 307201 | Rafael L. Lazatin Mem. HS | ANGELES CITY | 1 |  | 1 | [5 empty] | 173058.28 | UPGRADING | 1 | Completed | 100% | 100% | 2018-09-22 | 2018-09-22 | [6 empty] | 2018-08-23 | Nulas Builders | 170000 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region III | Angeles City | 307202 | Angeles City Science HS | ANGELES CITY | 1 |  | 1 | [5 empty] | 173058.28 | UPGRADING | 1 | Completed | 100% | 100% | 2018-09-22 | 2018-09-22 | [6 empty] | 2018-08-23 | Nulas Builders | 170000 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region III | Aurora |  | Baler Stand Alone | BALER | 0 |  | 1 | [5 empty] | 1894542.42 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Aurora | 300672 | Aurora National Science HS | BALER (Capital) | 0 |  | 1 | [5 empty] | 1697974.27 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Aurora | 300673 | Aurora NHS | BALER (Capital) | 0 |  | 1 | [5 empty] | 930975.89 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Aurora | 300692 | Manggitahan NHS | DILASAG | 0 |  | 1 | [5 empty] | 1180594.82 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Aurora | 306504 | Diagyan NHS | DILASAG | 0 |  | 1 | [5 empty] | 1902320 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Aurora | 300689 | Juan C. Angara Memorial NHS | DINALUNGAN | 0 |  | 1 | [5 empty] | 1955011.71 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Aurora | 300693 | Dipaculao NHS | DIPACULAO | 0 |  | 1 | [5 empty] | 2318025.33 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Aurora | 300686 | Ditumabo NHS | SAN LUIS | 0 |  | 1 | [5 empty] | 1000358.11 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Aurora | 306508 | Rosauro R. Tangson, Sr. NHS | SAN LUIS | 0 |  | 1 | [5 empty] | 2758246.38 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Bataan | 300708 | Luakan National High School | DINALUPIHAN | 1 |  | 1 | [5 empty] | 1895363.51 | UPGRADING | 1 | Completed | 100% | 100% | 2018-09-07 |  |  |  | May 3-17, 2018 | 2018-05-10 | 2018-05-23 | 2018-06-04 | 2018-07-04 | BQA Construction& Trading | 1878142.77 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Bataan | 300719 | Samal NHS | SAMAL | 1 |  | 1 | [5 empty] | 1809224.16 | UPGRADING | 1 | Completed | 100% | 100% | 2018-09-07 |  |  |  | May 3-17, 2018 | 2018-05-10 | 2018-05-23 | 2018-06-04 | 2018-07-04 | BQA Construction& Trading | 1791256.13 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Bataan | 300703 | Bataan School of Fisheries | ORION | 2 |  | 1 | [5 empty] | 3559235.68 | UPGRADING | 1 | Completed | 100% | 100% | 2018-09-07 |  |  |  | May 3-17, 2018 | 2018-05-10 | 2018-05-23 | 2018-06-04 | 2018-07-04 | BQA Construction& Trading | 3529388.39 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Mabalacat City | 300895 | Mabalacat NHS | MABALACAT | 1 |  | 1 | [5 empty] | 341218.2 | UPGRADING | 1 | Completed | 100% | 100% | 2018-05-24 | [5 empty] | 2018-04-10 | 2018-04-16 | 2018-04-20 | R.S DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Mabalacat City | 306909 | Mabalacat TVS | MABALACAT | 1 |  | 1 | [5 empty] | 762937.98 | UPGRADING | 1 | Completed | 100% | 100% | 2018-05-24 | [5 empty] | 2018-04-10 | 2018-04-16 | 2018-04-20 | R.S DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Mabalacat City | 306942 | Santos Ventura NHS | MABALACAT | 1 |  | 1 | [5 empty] | 350614.35 | UPGRADING | 1 | Completed | 100% | 100% | 2018-05-24 | [5 empty] | 2018-04-10 | 2018-04-16 | 2018-04-20 | R.S DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Mabalacat City | 345342 | SHS w/in Sapang Biabas ES | MABALACAT | 1 |  | 1 | [5 empty] | 745566.71 | UPGRADING | 1 | Completed | 100% | 100% | 2018-05-24 | [5 empty] | 2018-04-10 | 2018-04-16 | 2018-04-20 | R.S DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Mabalacat City | 300889 | Madapdap Resettlement HS | MAGALANG | 1 |  | 1 | [5 empty] | 865728.1 | UPGRADING | 1 | Completed | 100% | 100% | 2018-05-24 | [5 empty] | 2018-04-10 | 2018-04-16 | 2018-04-20 | R.S DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Malolos City | 300750 | Malolos Marine Fishery School & Laboratory | CITY OF MALOLOS (Capital) | 1 |  | 1 | [5 empty] | 2604906.2 | UPGRADING | 1 | Completed | 100% | 100% |  |  | MLL2018-06 | MLL2018-06 |  | 2018-05-31 | 2018-06-22 | 2018-07-10 | 2018-07-18 | LOURBEL CONSTRUCTION & SUPPLY | 2573336.85 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Olongapo City | 162003 | Iram II ES | OLONGAPO CITY | 1 |  | 1 | [5 empty] | 2077391.62 | SOLAR PANEL | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region III | Tarlac | 300978 | Padapada NHS | SANTA IGNACIA | 1 |  | 1 | [5 empty] | 2770962.62 | UPGRADING | 1 | Completed | 40% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 301015 | Castillejos National High School | CASTILLEJOS | 1 |  | 1 | [5 empty] | 529630.83 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 307106 | JESUS F. MAGSAYSAY TECHNICAL-VOCATIONAL HIGH SCHOOL | CASTILLEJOS | 1 |  | 1 | [5 empty] | 359481.51 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 160503 | Chiang Chio Te Mem. Aeta School (Ibad PS) | SAN MARCELINO | 1 |  | 1 | [5 empty] | 578540.81 | SOLAR PANEL | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | NO NTP YET | N
Region III | Zambales | 301029 | San Guillermo NHS | SAN MARCELINO | 1 |  | 1 | [5 empty] | 555871.38 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 301036 | Subic National High School | SUBIC | 1 |  | 1 | [5 empty] | 433078.49 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 307112 | Nagyantok HS | SUBIC | 1 |  | 1 | [5 empty] | 238791.09 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 307124 | Subic NHS Annex IV - San Isidro HS | SUBIC | 1 |  | 1 | [5 empty] | 238791.09 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 160504 | Cabatuan ES | BOTOLAN | 2 |  | 1 | [5 empty] | 813993.9 | SOLAR PANEL | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | NO NTP YET | N
Region III | Zambales | 160515 | Villar ES | BOTOLAN | 2 |  | 1 | [5 empty] | 782336.4 | SOLAR PANEL | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | NO NTP YET | N
Region III | Zambales | 160523 | Burgos ES | BOTOLAN | 2 |  | 1 | [5 empty] | 787612.65 | SOLAR PANEL | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | NO NTP YET | N
Region III | Zambales | 160526 | Poon Bato Elementary School | BOTOLAN | 2 |  | 1 | [5 empty] | 782336.4 | SOLAR PANEL | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | NO NTP YET | N
Region III | Zambales | 301008 | Baquilan Resettlement High School | BOTOLAN | 2 |  | 1 | [5 empty] | 289720.92 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 301025 | Botolan National High School | BOTOLAN | 2 |  | 1 | [5 empty] | 2901396.11 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 301026 | New Taugtog National High School | BOTOLAN | 2 |  | 1 | [5 empty] | 302634.44 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 307131 | Lakas High School | BOTOLAN | 2 |  | 1 | [5 empty] | 229562.69 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales |  | MAGUISGUIS IS | BOTOLAN | 2 |  | 1 | [5 empty] | 940096.27 | SOLAR PANEL | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | NO NTP YET | N
Region III | Zambales | 301010 | Cabangan National High School | CABANGAN | 2 |  | 1 | [5 empty] | 2678122.02 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 307120 | Pamibian IS | CANDELARIA | 2 |  | 1 | [5 empty] | 378399.48 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 301004 | Amungan NHS | IBA (Capital) | 2 |  | 1 | [5 empty] | 402537.56 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 301037 | Zambales NHS | IBA (Capital) | 2 |  | 1 | [5 empty] | 2934885.85 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 301005 | Bani NHS | MASINLOC | 2 |  | 1 | [5 empty] | 347882.41 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 307103 | San Salvador HS | MASINLOC | 2 |  | 1 | [5 empty] | 320002.7 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales |  | TALTAL NHS | MASINLOC | 2 |  | 1 | [5 empty] | 439552.69 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 301027 | Rofulo M. Landa HS (Salaza NHS) | PALAUIG | 2 |  | 1 | [5 empty] | 347882.41 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 301028 | Locloc National High School | PALAUIG | 2 |  | 1 | [5 empty] | 347882.41 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 301032 | San Miguel NHS | SAN ANTONIO | 2 |  | 1 | [5 empty] | 438055.75 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 307107 | San Antonio National High School | SAN ANTONIO | 2 |  | 1 | [5 empty] | 391157.45 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 160520 | Banawen PS | SAN FELIPE | 2 |  | 1 | [5 empty] | 771783.9 | SOLAR PANEL | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | NO NTP YET | N
Region III | Zambales | 106975 | Babuyan ES | SANTA CRUZ | 2 |  | 1 | [5 empty] | 976746.37 | SOLAR PANEL | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | NO NTP YET | N
Region III | Zambales | 301014 | Guisguis NHS | SANTA CRUZ | 2 |  | 1 | [5 empty] | 455413.83 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 301033 | Sta. Cruz NHS | SANTA CRUZ | 2 |  | 1 | [5 empty] | 294724.19 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 307102 | Sta. Cruz NHS - Jesus F. Magsaysay HS Annex | SANTA CRUZ | 2 |  | 1 | [5 empty] | 323846.39 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales |  | LIPAY NHS | SANTA CRUZ | 2 |  | 1 | [5 empty] | 373296.29 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales |  | BOLITOC NHS | SANTA CRUZ | 2 |  | 1 | [5 empty] | 443158.94 | UPGRADING | 1 | Completed | 100% | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-A | Bacoor City | 107867 | Proposed Stand-Alone SHS 5- Bacoor ES | Bacoor City | 2 |  | 1 | [5 empty] | 1146067.18 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-A | Batangas City | 301470 | Balete NHS | BATANGAS CITY (Capital) | 2 |  | 1 | [5 empty] | 700915.01 | UPGRADING | 1 | ONGOING | 50% | 80% | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION | 695612.46 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-A | Batangas City | 301473 | Conde Labac NHS | BATANGAS CITY (Capital) | 2 |  | 1 | [5 empty] | 855711.74 | UPGRADING | 1 | ONGOING | 50% | 80% | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION | 850003.71 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-A | Batangas City | 301474 | Paharang NHS | BATANGAS CITY (Capital) | 2 |  | 1 | [5 empty] | 700915.01 | UPGRADING | 1 | ONGOING | 50% | 80% | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION | 695939.47 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-A | Batangas City | 301476 | Pinamukan NHS | BATANGAS CITY (Capital) | 2 |  | 1 | [5 empty] | 700915.01 | UPGRADING | 1 | ONGOING | 50% | 80% | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION | 697193.22 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-A | Batangas City | 301481 | Tabangao NHS | BATANGAS CITY (Capital) | 2 |  | 1 | [5 empty] | 855711.74 | UPGRADING | 1 | ONGOING | 50% | 80% | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION | 849691.66 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-A | Batangas City | 308201 | Natalia V. Ramos Memorial National High School | BATANGAS CITY (Capital) | 2 |  | 1 | [5 empty] | 855977.1 | UPGRADING | 1 | ONGOING | 50% | 80% | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION | 851559.48 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-A | CITY OF BIÑAN | 301230 | Biñan National High School | CITY OF BIÑAN | 1 |  | 1 | [5 empty] | 1581624.3 | UPGRADING | 1 | Completed | 90% | 100% | February 25, 2019 |  | R4A-BNN-2018-07 | R4A-BNN-2018-07 | July 19 - Aug. 8, 2018 | July 30, 2018 | August 13, 2018 | August 13, 2018 | August 25, 2018 | G.S Motar Builders Construction and Trading | 1560549.3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-A | CITY OF BIÑAN | 307931 | Saint Francis NHS | CITY OF BIÑAN | 1 |  | 1 | [5 empty] | 569350.89 | UPGRADING | 1 | Completed | 90% | 100% | February 25, 2019 |  | R4A-BNN-2018-07 | R4A-BNN-2018-07 | July 19 - Aug. 8, 2018 | July 30, 2018 | August 13, 2018 | August 13, 2018 | August 25, 2018 | G.S Motar Builders Construction and Trading | 543300.29 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-A | CITY OF BIÑAN | 307934 | SOUTHVILLE 5-A NATIONAL HIGH SCHOOL | CITY OF BIÑAN | 1 |  | 1 | [5 empty] | 607488.83 | UPGRADING | 1 | Completed | 90% | 100% | February 25, 2019 |  | R4A-BNN-2018-07 | R4A-BNN-2018-07 | July 19 - Aug. 8, 2018 | July 30, 2018 | August 13, 2018 | August 13, 2018 | August 25, 2018 | G.S Motar Builders Construction and Trading | 586424.13 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-A | Rizal | 301430 | Bayugo NHS | JALA-JALA | 2 |  | 1 | [5 empty] | 1995063.29 | UPGRADING | 1 | ONGOING | 50% | 72% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-A | Rizal | 301461 | Sto. Niño NHS | TANAY | 2 |  | 1 | [5 empty] | 1646492.71 | SOLAR PANEL | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-A | Rizal | 308133 | Laiban NHS | TANAY | 2 |  | 1 | [5 empty] | 1001553.79 | SOLAR PANEL | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-A | San Pablo City | 301504 | San Pablo City National High School | SAN PABLO CITY | 3 |  | 1 | [5 empty] | 497945.3776 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-26 |  |  | BRF-009-2018 | BRF-009-2018 | 2018-05-25 | 2018-06-08 | 2018-06-18 | 2018-06-21 | Power K Construction Supply and Services | 495945.38 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-A | San Pablo City | 301505 | Col. Lauro D. Dizon Memorial National High School | SAN PABLO CITY | 3 |  | 1 | [5 empty] | 497945.3776 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-26 |  |  | BRF-009-2018 | BRF-009-2018 | 2018-05-25 | 2018-06-08 | 2018-06-18 | 2018-06-21 | Power K Construction Supply and Services | 495945.38 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-A | San Pablo City | 308602 | San Jose National High School | SAN PABLO CITY | 3 |  | 1 | [5 empty] | 497945.3776 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-26 |  |  | BRF-009-2018 | BRF-009-2018 | 2018-05-25 | 2018-06-08 | 2018-06-18 | 2018-06-21 | Power K Construction Supply and Services | 495945.38 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-A | SAN PABLO CITY | 342575 | SAN PABLO CITY SENIOR HIGH SCHOOL (STAND ALONE) | SAN PABLO CITY | 3 |  | 1 | [5 empty] | 497945.3776 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-26 |  |  | BRF-009-2018 | BRF-009-2018 | 2018-05-25 | 2018-06-08 | 2018-06-18 | 2018-06-21 | Power K Construction Supply and Services | 495945.38 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-A | TANAUAN CITY | 301133 | Pantay NHS | CITY OF TANAUAN | 3 |  | 1 | [5 empty] | 490560.77 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-A | TANAUAN CITY | 301154 | Tanauan School of Fisheries | CITY OF TANAUAN | 3 |  | 1 | [5 empty] | 1383834.72 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-A | TAYABAS CITY | 342576 | STAND ALONE SHS (POTOL) | TAYABAS | 1 |  | 1 | [5 empty] | 1306742.55 | UPGRADING | 1 | Completed | 80% | 100% | October 1 ,2018 |  |  |  | 2018-06-07 | 2018-06-13 | 2018-06-25 | 2018-07-01 | 2018-07-04 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-B | Calapan City | 301798 | Canubing National High School | CITY OF CALAPAN (Capital) | 1 |  | 1 | [5 empty] | 415231.83 | UPGRADING | 1 | Completed |  | 100% | 10/25/2018 |  |  | 2018-18 | 07/17/2018 | 07/23/2018 | 08/06/2018 | 08/13/2018 | 08/22/2018 | ETVR TRADING & CONSTRUCTION | 392996.4016 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-B | Calapan City | 301802 | Nag-iba National High School | CITY OF CALAPAN (Capital) | 1 |  | 1 | [5 empty] | 446113.47 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed |  | 100% | 10/25/2018 |  |  | 2018-18 | 07/17/2018 | 07/23/2018 | 08/06/2018 | 08/13/2018 | 08/22/2018 | ETVR TRADING & CONSTRUCTION | 423592.7535 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-B | Marinduque | 109930 | Gaspar ES | GASAN | 0 |  | 1 | [5 empty] | 897069.46 | SOLAR PANEL | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-B | Marinduque | 301557 | Mogpog NCHS | MOGPOG | 0 |  | 1 | [5 empty] | 437061.38 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | error on reporting. Reported failed bidding August 7, 2019. Why so? | Y
Region IV-B | Marinduque | 301558 | Mongpong NHS | SANTA CRUZ | 0 |  | 1 | [5 empty] | 897069.46 | SOLAR PANEL | 1 | Completed | 20% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-B | Marinduque | 301553 | Maranlig National High School | TORRIJOS | 0 |  | 1 | [5 empty] | 437061.38 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | error on reporting. Reported failed bidding August 7, 2019. Why so? | N
Region IV-B | Marinduque | 301556 | Matuyatuya NHS | TORRIJOS | 0 |  | 1 | [5 empty] | 626955.35 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | error on reporting. Reported failed bidding August 7, 2019. Why so? | N
Region IV-B | Occidental Mindoro | 301583 | Looc National School Of Fisheries | LOOC | 0 |  | 1 | [5 empty] | 876671.83 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-B | Occidental Mindoro | 301605 | Sta Teresa NHS | MAGSAYSAY | 0 |  | 1 | [5 empty] | 562469.72 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-B | Occidental Mindoro | 301594 | Paluan NHS | PALUAN | 0 |  | 1 | [5 empty] | 866324.22 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-B | Occidental Mindoro | 301595 | RIZAL NATIONAL HIGH SCHOOL | RIZAL | 0 |  | 1 | [5 empty] | 817030.4 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-B | Occidental Mindoro | 301582 | Paulino Legaspi, Sr. Memorial. NHS | SABLAYAN | 0 |  | 1 | [5 empty] | 852498.82 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-B | Occidental Mindoro | 301589 | Magsaysay NHS - Mapaya Annex | SAN JOSE | 0 |  | 1 | [5 empty] | 849048.06 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-B | Occidental Mindoro | 301600 | Central NHS | SAN JOSE | 0 |  | 1 | [5 empty] | 881194.4 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-B | Occidental Mindoro | 308901 | San Jose National Agricultural and Industrial High School | SAN JOSE | 0 |  | 1 | [5 empty] | 869277.89 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-B | Occidental Mindoro | 308908 | San Jose NAIHS - Mangarin Annex | SAN JOSE | 0 |  | 1 | [5 empty] | 562469.72 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-B | Occidental Mindoro |  | Pinagturilan NHS | SANTA CRUZ | 0 |  | 1 | [5 empty] | 824424.34 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-B | Oriental Mindoro |  | Anastacio Dela Chica High School | BACO | 1 |  | 1 | [5 empty] | 1517078.45 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 20% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-B | Oriental Mindoro | 309004 | Puerto Galera NHS | PUERTO GALERA | 1 |  | 1 | [5 empty] | 631356.09 | UPGRADING | 1 | Completed | 30% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-B | Oriental Mindoro | 309035 | Puerto Galera NHS - San Isidro Ext. | PUERTO GALERA | 1 |  | 1 | [5 empty] | 583660.05 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 20% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-B | Oriental Mindoro | 301653 | San Teodoro NHS | SAN TEODORO | 1 |  | 1 | [5 empty] | 1324535.19 | UPGRADING | 1 | Completed | 15% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-B | Oriental Mindoro | 301655 | Villapagasa NHS | BANSUD | 2 |  | 1 | [5 empty] | 1384901.13 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 35% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-B | Oriental Mindoro | 301624 | Cawayan National High School | BONGABONG | 2 |  | 1 | [5 empty] | 938249.48 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 30% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-B | Oriental Mindoro | 301625 | Dayhagan NHS | BONGABONG | 2 |  | 1 | [5 empty] | 1343352.5 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 30% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-B | Oriental Mindoro | 309005 | Labasan National High School | BONGABONG | 2 |  | 1 | [5 empty] | 1075277.83 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 30% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-B | Oriental Mindoro | 301621 | Maujao National High School | BULALACAO (SAN PEDRO) | 2 |  | 1 | [5 empty] | 1494745.42 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 35% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-B | Oriental Mindoro | 301622 | San Roque NHS | BULALACAO (SAN PEDRO) | 2 |  | 1 | [5 empty] | 1325200.18 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 35% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-B | Oriental Mindoro | 301617 | Balugo NHS | MANSALAY | 2 |  | 1 | [5 empty] | 908171.38 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 10% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-B | Oriental Mindoro | 301652 | San Mariano NHS | ROXAS | 2 |  | 1 | [5 empty] | 944527.21 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 35% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-B | Palawan | 110742 | Concepcion ES | AGUTAYA | 1 |  | 1 | [5 empty] | 2124271.51 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 301695 | Gaudencio E. Abordo Mem. NHS | AGUTAYA | 1 |  | 1 | [5 empty] | 1244774.41 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Palawan | 309120 | Concepcion National High School | AGUTAYA | 1 |  | 1 | [5 empty] | 2509183.3 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 301662 | Araceli NHS | ARACELI | 1 |  | 1 | [5 empty] | 1348153.75 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Palawan | 301678 | Calandagan NHS | ARACELI | 1 |  | 1 | [5 empty] | 1856418.02 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Palawan | 301711 | New Busuanga NHS | BUSUANGA | 1 |  | 1 | [5 empty] | 1629060.37 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Palawan | 301734 | Salvacion NHS | BUSUANGA | 1 |  | 1 | [5 empty] | 1764088.55 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Palawan | 309134 | Cheey NHS | BUSUANGA | 1 |  | 1 | [5 empty] | 1436313.98 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Palawan | 309167 | Concepcion NHS | BUSUANGA | 1 |  | 1 | [5 empty] | 1415684.72 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Palawan | 110965 | Calusa ES | CAGAYANCILLO | 1 |  | 1 | [5 empty] | 2429697.81 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 110966 | Cawili Elementary School | CAGAYANCILLO | 1 |  | 1 | [5 empty] | 2080947.05 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 301677 | Cagayancillo NHS | CAGAYANCILLO | 1 |  | 1 | [5 empty] | 1443595.29 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 110973 | Banuang Daan ES | CORON | 1 |  | 1 | [5 empty] | 859977.49 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 110979 | Cabugao ES | CORON | 1 |  | 1 | [5 empty] | 966266.77 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 301684 | Coron SOF | CORON | 1 |  | 1 | [5 empty] | 1653895.31 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Palawan | 301685 | Borac National High School | CORON | 1 |  | 1 | [5 empty] | 1426067.75 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Palawan | 309168 | Decalachao NHS | CORON | 1 |  | 1 | [5 empty] | 1246826.83 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Palawan | 301687 | Culion Sanitarium Special NHS | CULION | 1 |  | 1 | [5 empty] | 1374419.64 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Palawan | 301688 | Cuyo NHS | CUYO | 1 |  | 1 | [5 empty] | 1278597.83 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Palawan | 301691 | Dumaran NHS | DUMARAN | 1 |  | 1 | [5 empty] | 1319944.07 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 301740 | Santa Teresita NHS | DUMARAN | 1 |  | 1 | [5 empty] | 1419892.76 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Palawan | 301737 | San Miguel NHS (Gaudencio Abordo NHS) | LINAPACAN | 1 |  | 1 | [5 empty] | 1411416.83 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Palawan | 301689 | Danawan NHS | MAGSAYSAY | 1 |  | 1 | [5 empty] | 1246964.61 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Palawan | 111155 | Maragoc ES | ROXAS | 1 |  | 1 | [5 empty] | 1942556.02 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 111166 | Salvador ES | ROXAS | 1 |  | 1 | [5 empty] | 2576686.91 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 170512 | Ramon Gacayan Elementary School | ROXAS | 1 |  | 1 | [5 empty] | 1970006.99 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 111223 | Casian ES | TAYTAY | 1 |  | 1 | [5 empty] | 2928722.65 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 301682 | Casian NHS | TAYTAY | 1 |  | 1 | [5 empty] | 4966964.86 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 301666 | Balabac NHS | BALABAC | 2 |  | 1 | [5 empty] | 1502475 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING |  | 10% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Palawan | 309113 | Bancalaan National High School | BALABAC | 2 |  | 1 | [5 empty] | 3065598.98 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 309127 | Sibaring NHS | BALABAC | 2 |  | 1 | [5 empty] | 730635 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 309149 | Taburi NHS | BALABAC | 2 |  | 1 | [5 empty] | 1202985 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 309126 | Tarusan NHS | BATARAZA | 2 |  | 1 | [5 empty] | 3048165 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 309129 | Southern Bataraza NHS | BATARAZA | 2 |  | 1 | [5 empty] | 2374815 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 301727 | Quezon-Aramaywan NHS | QUEZON | 2 |  | 1 | [5 empty] | 2594910 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 301729 | Quinlogan NHS | QUEZON | 2 |  | 1 | [5 empty] | 2221050 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 309146 | Panalingaan NHS | RIZAL | 2 |  | 1 | [5 empty] | 2107485 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 309160 | Canipaan NHS | RIZAL | 2 |  | 1 | [5 empty] | 2070300 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 301680 | Candawaga NHS | RIZAL (MARCOS) | 2 |  | 1 | [5 empty] | 1402980 | SOLAR PANEL | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Palawan | 301719 | Panitian National High School | SOFRONIO ESPAÑOLA | 2 |  | 1 | [5 empty] | 1430115 | UPGRADING | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Romblon | 301750 | Banton NHS | BANTON | 0 |  | 1 | [5 empty] | 1836679.92 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING | 80% | 80% | 2019-01-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction | 1811342.4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Romblon | 301753 | Lumbang East National High School | CAJIDIOCAN | 0 |  | 1 | [5 empty] | 1231361.43 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING | 80% | 80% | 2019-01-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction | 1204491.32 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Romblon | 301755 | Cambalo NHS | CAJIDIOCAN | 0 |  | 1 | [5 empty] | 1461469.76 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING | 90% | 90% | 2019-01-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction | 1409881.03 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Romblon | 309201 | Calatrava NHS | CALATRAVA | 0 |  | 1 | [5 empty] | 1323540.82 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING | 90% | 90% | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction | 1269933.37 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Romblon | 301757 | Corcuera NHS | CORCUERA | 0 |  | 1 | [5 empty] | 1282934.39 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING | 80% | 80% | 2019-01-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction | 1261369.12 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Romblon | 301761 | Ferrol National High School | FERROL | 0 |  | 1 | [5 empty] | 1565256.73 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING | 90% | 90% | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction | 1479621.63 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Romblon | 301769 | Odiongan, National High School | ODIONGAN | 0 |  | 1 | [5 empty] | 2144933.9 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING | 90% | 90% | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction | 1997168.88 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Romblon | 301749 | Esteban Madrona National High School | SAN AGUSTIN | 0 |  | 1 | [5 empty] | 1515602.48 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING | 90% | 90% | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction | 1488591.8 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Romblon | 309205 | Carmen NHS (Cabolutan NHS Ext.) | SAN AGUSTIN | 0 |  | 1 | [5 empty] | 1374449.99 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING | 90% | 90% | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction | 1324624.29 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Romblon | 301771 | San Andres NHS | SAN ANDRES | 0 |  | 1 | [5 empty] | 1416442.65 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING | 90% | 90% | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction | 1340420.86 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Romblon | 301763 | Sta. Fe NHS | SANTA FE | 0 |  | 1 | [5 empty] | 1464802.14 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING | 90% | 90% | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction | 1405144.61 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Romblon | 301774 | Santa Maria NHS | SANTA MARIA (IMELDA) | 0 |  | 1 | [5 empty] | 1707966.77 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | ONGOING | 90% | 90% | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction | 1647944.34 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IX | Zamboanga City | 303915 | Ayala NHS | ZAMBOANGA CITY | 1 |  | 1 | [5 empty] | 2010000 | UPGRADING | 1 | Completed | 80% | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG | 1788937.91 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga City | 303933 | Southcom NHS | ZAMBOANGA CITY | 1 |  | 1 | [5 empty] | 1005000 | UPGRADING | 1 | Completed | 80% | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG | 847456.17 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga City | 303935 | Talisayan NHS | ZAMBOANGA CITY | 1 |  | 1 | [5 empty] | 1005000 | UPGRADING | 1 | Completed | 80% | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG | 814771.02 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga City | 314805 | Recodo NHS | ZAMBOANGA CITY | 1 |  | 1 | [5 empty] | 1005000 | UPGRADING | 1 | Completed | 80% | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG | 838517.37 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga City | 345869 | Baliwasan Senior High School | ZAMBOANGA CITY | 1 |  | 1 | [5 empty] | 904500 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG | 738378.12 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga City | 303918 | Bunguiao NHS | ZAMBOANGA CITY | 2 |  | 1 | [5 empty] | 703500 | UPGRADING | 1 | Completed | 80% | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG | 629391.63 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga City | 303928 | Manicahan NHS | ZAMBOANGA CITY | 2 |  | 1 | [5 empty] | 703500 | UPGRADING | 1 | Completed | 80% | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG | 628909.03 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga City | 303929 | Mercedes NHS | ZAMBOANGA CITY | 2 |  | 1 | [5 empty] | 1005000 | UPGRADING | 1 | Completed | 80% | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG | 919671.2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga City | 303936 | Tictapul NHS | ZAMBOANGA CITY | 2 |  | 1 | [5 empty] | 703500 | UPGRADING | 1 | Completed | 80% | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG | 627582.12 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124398 | La Libertad CS | LA LIBERTAD | 1 |  | 1 | [5 empty] | 636254.46 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124540 | Mutia CS | MUTIA | 1 |  | 1 | [5 empty] | 640017.36 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124561 | Piñan CS | PIÑAN (NEW PIÑAN) | 1 |  | 1 | [5 empty] | 638434.48 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124579 | Polanco CS | POLANCO | 1 |  | 1 | [5 empty] | 637379.23 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124597 | Silawe CS | POLANCO | 1 |  | 1 | [5 empty] | 637379.23 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124610 | Rizal CS | RIZAL | 1 |  | 1 | [5 empty] | 640017.36 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124651 | Sergio Osmeña CS | SERGIO OSMEÑA SR. | 1 |  | 1 | [5 empty] | 641600.23 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124671 | San Isidro CS | SERGIO OSMEÑA SR. | 1 |  | 1 | [5 empty] | 643710.73 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124751 | Sibutad CS | SIBUTAD | 1 |  | 1 | [5 empty] | 641072.61 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124335 | Ponot CS | JOSE DALMAN (PONOT) | 2 |  | 1 | [5 empty] | 640544.98 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124369 | Katipunan CS | KATIPUNAN | 2 |  | 1 | [5 empty] | 638434.48 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124396 | Taga CS | KATIPUNAN | 2 |  | 1 | [5 empty] | 634829.87 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124510 | Manukan East CS | MANUKAN | 2 |  | 1 | [5 empty] | 638962.11 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124511 | Manukan West CS | MANUKAN | 2 |  | 1 | [5 empty] | 638962.11 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124524 | Gupot ES | MANUKAN | 2 |  | 1 | [5 empty] | 638962.11 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124488 | Roxas CS | PRES. MANUEL A. ROXAS | 2 |  | 1 | [5 empty] | 638434.48 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124495 | Dohinob CS | PRES. MANUEL A. ROXAS | 2 |  | 1 | [5 empty] | 638434.48 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124701 | Siayan CS | SIAYAN | 2 |  | 1 | [5 empty] | 637930.59 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124770 | Sindangan Pilot Demonstration School | SINDANGAN | 2 |  | 1 | [5 empty] | 640544.98 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124778 | Juan Bugarin CS | SINDANGAN | 2 |  | 1 | [5 empty] | 640544.98 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124802 | Mandih CS | SINDANGAN | 2 |  | 1 | [5 empty] | 640544.98 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124428 | Bacungan CS | BACUNGAN (LEON T. POSTIGO) | 3 |  | 1 | [5 empty] | 646551.25 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124278 | Godod CS | GODOD | 3 |  | 1 | [5 empty] | 646551.25 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124417 | Labason CS | LABASON | 3 |  | 1 | [5 empty] | 646551.25 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124454 | Liloy CS | LILOY | 3 |  | 1 | [5 empty] | 646551.25 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124463 | Baybay CS | LILOY | 3 |  | 1 | [5 empty] | 646551.25 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124623 | Salug CS | SALUG | 3 |  | 1 | [5 empty] | 646551.25 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124625 | Bacong CS | SALUG | 3 |  | 1 | [5 empty] | 646551.25 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124830 | Siocon CS | SIOCON | 3 |  | 1 | [5 empty] | 646551.25 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Norte | 124862 | Tampilisan CS | TAMPILISAN | 3 |  | 1 | [5 empty] | 646551.25 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 303766 | Commonwealth NHS | AURORA | 1 |  | 1 | [5 empty] | 974850 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 303780 | Aurora National High School | AURORA | 1 |  | 1 | [5 empty] | 1060275 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 125030 | Mate ES | DUMINGAG | 1 |  | 1 | [5 empty] | 547725 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | SOLAR PANEL (FOR ISSUANCE OF NEGATIVE SUB ARO) |  | NOT PROCURED; for issuance of Negative Sub-ARO
Region IX | Zamboanga del Sur | 196031 | Paliran ES | DUMINGAG | 1 |  | 1 | [5 empty] | 547725 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | SOLAR PANEL (FOR ISSUANCE OF NEGATIVE SUB ARO) |  | NOT PROCURED; for issuance of Negative Sub-ARO
Region IX | Zamboanga del Sur | 303773 | Dumingag National High School | DUMINGAG | 1 |  | 1 | [5 empty] | 1015050 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 303792 | Leonardo NHS | JOSEFINA | 1 |  | 1 | [5 empty] | 1206000 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 345844 | LABANGAN SENIOR HIGH SCHOOL | LABANGAN | 1 |  | 1 | [5 empty] | 1226100 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 125183 | Lactayan ES | MAHAYAG | 1 |  | 1 | [5 empty] | 874350 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | SOLAR PANEL (FOR ISSUANCE OF NEGATIVE SUB ARO) |  | NOT PROCURED; for issuance of Negative Sub-ARO
Region IX | Zamboanga del Sur | 125190 | Pilas ES | MAHAYAG | 1 |  | 1 | [5 empty] | 407025 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | SOLAR PANEL (FOR ISSUANCE OF NEGATIVE SUB ARO) |  | NOT PROCURED; for issuance of Negative Sub-ARO
Region IX | Zamboanga del Sur | 314228 | Sapa Anding National High School - Ramon Magsaysay Extension | RAMON MAGSAYSAY (LIARGO) | 1 |  | 1 | [5 empty] | 1125600 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 303817 | Sominot NHS | SOMINOT (DON MARIANO MARCOS) | 1 |  | 1 | [5 empty] | 849225 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 303819 | Tambulig NHS | TAMBULIG | 1 |  | 1 | [5 empty] | 1100475 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 124920 | Deporehan IES | BAYOG | 2 |  | 1 | [5 empty] | 532650 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | SOLAR PANEL |  | NOT PROCURED; for issuance of Negative Sub-ARO
Region IX | Zamboanga del Sur | 196004 | Lower Conacon ES | BAYOG | 2 |  | 1 | [5 empty] | 351750 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | SOLAR PANEL |  | NOT PROCURED; for issuance of Negative Sub-ARO
Region IX | Zamboanga del Sur | 303757 | Bayog NHS | BAYOG | 2 |  | 1 | [5 empty] | 1075350 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 303764 | Laureano Salusod NHS | DIMATALING | 2 |  | 1 | [5 empty] | 1226100 | UPGRADING | 1 | Completed | 98% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 303770 | Dimataling NHS | DIMATALING | 2 |  | 1 | [5 empty] | 994950 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 124983 | Sumilom PS | DINAS | 2 |  | 1 | [5 empty] | 593250 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 303771 | Dinas NHS | DINAS | 2 |  | 1 | [5 empty] | 1097460 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 303778 | Guipos NHS | GUIPOS | 2 |  | 1 | [5 empty] | 1085400 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 125104 | Mapao CPS | KUMALARANG | 2 |  | 1 | [5 empty] | 331650 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | SOLAR PANEL |  | NOT PROCURED; for issuance of Negative Sub-ARO
Region IX | Zamboanga del Sur | 303823 | Tubod NHS | LAKEWOOD | 2 |  | 1 | [5 empty] | 974850 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 314249 | Poblacion Comprehensive NHS | LAKEWOOD | 2 |  | 1 | [5 empty] | 1100475 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 125152 | Cubo ES | LAPUYAN | 2 |  | 1 | [5 empty] | 407025 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | SOLAR PANEL |  | NOT PROCURED; for issuance of Negative Sub-ARO
Region IX | Zamboanga del Sur | 125161 | Mahalingeb PS | LAPUYAN | 2 |  | 1 | [5 empty] | 362250 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 314261 | Lapuyan National High School - Maralag Extension | LAPUYAN | 2 |  | 1 | [5 empty] | 530250 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 303783 | Kalian NHS | MARGOSATUBIG | 2 |  | 1 | [5 empty] | 859275 | UPGRADING | 1 | Completed | 97% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 303804 | Paulino Dari NHS | PITOGO | 2 |  | 1 | [5 empty] | 829125 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 303776 | Eugenia Andrin NHS | SAN PABLO | 2 |  | 1 | [5 empty] | 854250 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 303813 | San Pablo NHS | SAN PABLO | 2 |  | 1 | [5 empty] | 844200 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 314251 | San Pablo NHS - Sacbulan Ext. | SAN PABLO | 2 |  | 1 | [5 empty] | 672000 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 303768 | Tabina NHS | TABINA | 2 |  | 1 | [5 empty] | 844200 | UPGRADING | 1 | Completed | 92% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 303753 | Antonio NHS | TIGBAO | 2 |  | 1 | [5 empty] | 844200 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 303800 | Nilo NHS | TIGBAO | 2 |  | 1 | [5 empty] | 844200 | UPGRADING | 1 | Completed | 95% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Zamboanga del Sur | 303782 | Kabatan NHS | VINCENZO A. SAGUN | 2 |  | 1 | [5 empty] | 1226100 | UPGRADING | 1 | Completed | 98% | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region V | Albay | 301871 | San Antonio NHS, Malilipot | MALILIPOT | 1 |  | 1 | [5 empty] | 1155364.48 | UPGRADING | 1 | ONGOING | 65% | 70% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Albay | 309505 | San Francisco NHS | MALILIPOT | 1 |  | 1 | [5 empty] | 1005974.09 | UPGRADING | 1 | ONGOING | 65% | 70% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Albay | 309515 | Malilipot NHS | MALILIPOT | 1 |  | 1 | [5 empty] | 2106133.08 | UPGRADING | 1 | ONGOING | 65% | 75% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Albay | 111639 | Baligang ES | CAMALIG | 2 |  | 1 | [5 empty] | 6161438.9 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | Y
Region V | Albay | 301813 | Batan National High School | RAPU-RAPU | 2 |  | 1 | [5 empty] | 1868547.6 | UPGRADING | 1 | ONGOING | 65% | 85% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Albay | 301882 | Villahermosa NHS | RAPU-RAPU | 2 |  | 1 | [5 empty] | 1709022.71 | UPGRADING | 1 | ONGOING | 65% | 85% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Albay | 301884 | Mancao National High School | RAPU-RAPU | 2 |  | 1 | [5 empty] | 1595786.93 | UPGRADING | 1 | ONGOING | 65% | 85% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Albay | 309509 | Bilbao National High School | RAPU-RAPU | 2 |  | 1 | [5 empty] | 1482133.62 | UPGRADING | 1 | ONGOING | 65% | 85% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Albay | 309519 | Tinopan HS | RAPU-RAPU | 2 |  | 1 | [5 empty] | 1570749.69 | UPGRADING | 1 | ONGOING | 65% | 85% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Albay | 111965 | Alabangpuro ES | PIO DURAN | 3 |  | 1 | [5 empty] | 1374646.64 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | Y
Region V | Albay | 301840 | Magpanambo NHS | POLANGUI | 3 |  | 1 | [5 empty] | 1496125.18 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Norte | 301898 | Jose Panganiban NHS | JOSE PANGANIBAN | 1 |  | 1 | [5 empty] | 3939736.92 | UPGRADING | 1 | Completed | 100% | 100% | 2018-07-01 | [9 empty] | 3913595.4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Norte | 301893 | Daguit NHS | LABO | 1 |  | 1 | [5 empty] | 2492745.53 | UPGRADING | 1 | Completed | 100% | 100% | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  | 2468080.15 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Norte | 301922 | Tulay Na Lupa NHS | LABO | 1 |  | 1 | [5 empty] | 3649542.64 | UPGRADING | 1 | Completed | 100% | 100% | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  | 1642239.75 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Norte | 301923 | Talobatib HS | LABO | 1 |  | 1 | [5 empty] | 1656810.17 | UPGRADING | 1 | Completed | 100% | 100% | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  | 3631385.71 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Norte | 301890 | Batobalani NHS | PARACALE | 1 |  | 1 | [5 empty] | 2626785.92 | UPGRADING | 1 | Completed | 100% | 100% | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  | 2596870.62 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Norte | 301910 | Paracale NHS | PARACALE | 1 |  | 1 | [5 empty] | 2634173.86 | UPGRADING | 1 | Completed | 100% | 100% | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  | 2608327.86 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Norte | 301889 | Basud NHS | BASUD | 2 |  | 1 | [5 empty] | 7013018.85 | UPGRADING | 1 | Completed | 100% | 100% | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  | 6963077.23 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Norte | 301906 | Moreno Integrated School | DAET (Capital) | 2 |  | 1 | [5 empty] | 3642946.55 | UPGRADING | 1 | Completed | 100% | 100% | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  | 3606232.35 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Norte | 301905 | Mercedes HS | MERCEDES | 2 |  | 1 | [5 empty] | 2523429.7 | UPGRADING | 1 | Completed | 100% | 100% | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  | 2495864 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Sur | 301988 | Lupi-Iligan HS | LUPI | 1 |  | 1 | [5 empty] | 2261423.66 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Sur | 301929 | Simeon Tycangco MHS | RAGAY | 1 |  | 1 | [5 empty] | 2549977.63 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Sur | 301930 | Sisa Feliciano MHS | RAGAY | 1 |  | 1 | [5 empty] | 2083426.75 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Sur | 309743 | Bolo Norte HS | SIPOCOT | 1 |  | 1 | [5 empty] | 2657221.68 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Sur | 309767 | Manangle High School | SIPOCOT | 1 |  | 1 | [5 empty] | 1015428.28 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Sur | 301935 | Bahao HS | LIBMANAN | 2 |  | 1 | [5 empty] | 2174993.93 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Sur | 301994 | Mambulo Nuevo High School | LIBMANAN | 2 |  | 1 | [5 empty] | 2474177.75 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Sur | 309745 | Northern Plain HS | LIBMANAN | 2 |  | 1 | [5 empty] | 1247131.89 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Sur | 302025 | Sagrada Familia High School | MINALABAC | 2 |  | 1 | [5 empty] | 2033467.72 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 309731 | Antipolo HS, Minalabac | MINALABAC | 2 |  | 1 | [5 empty] | 1947146.05 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 301968 | Don Mariano C. Veneracion NHS | PAMPLONA | 2 |  | 1 | [5 empty] | 1852571.57 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 302032 | Maura N. Sibulo National HS | PAMPLONA | 2 |  | 1 | [5 empty] | 1852571.57 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 301965 | Rolando R. Andaya, Sr. MHS | PASACAO | 2 |  | 1 | [5 empty] | 1293794.83 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 309732 | Dr. Lorenzo P. Ziga MHS | PASACAO | 2 |  | 1 | [5 empty] | 1886881.46 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 302053 | Sulpicio A. Roco MHS | BOMBON | 3 |  | 1 | [5 empty] | 1585526.55 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 309707 | Siembre HS | BOMBON | 3 |  | 1 | [5 empty] | 1096756.47 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 309735 | Northern Canaman HS | CANAMAN | 3 |  | 1 | [5 empty] | 1622289.56 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 301957 | Doroteo Federis, Sr. NHS (frmerly: Carangcang HS) | MAGARAO | 3 |  | 1 | [5 empty] | 1351201.39 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 302034 | Magarao NHS (formerly: San Isidro NHS) | MAGARAO | 3 |  | 1 | [5 empty] | 2031906.68 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 301946 | Binanuaanan NHS | PILI (Capital) | 3 |  | 1 | [5 empty] | 2223308.53 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 302017 | Gov.Mariano E. Villafuerte HS | PILI (Capital) | 3 |  | 1 | [5 empty] | 1913337.83 | UPGRADING | 1 | ONGOING | 92% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 302054 | Tabgon HS, Goa | GOA | 4 |  | 1 | [5 empty] | 1372217.91 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 301963 | Dahat National Vocational HS | LAGONOY | 4 |  | 1 | [5 empty] | 1291895.7 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Sur | 302039 | San Ramon Pilot NHS, Lagonoy (frmerly:Sn.Ramon Pilot HS) | LAGONOY | 4 |  | 1 | [5 empty] | 1914501.56 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Sur | 309768 | Cabotonan High School | LAGONOY | 4 |  | 1 | [5 empty] | 688543.69 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Sur | 309708 | Catalotoan HS | SAGÑAY | 4 |  | 1 | [5 empty] | 876848.61 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 309714 | Dr. Rodolfo V. Pamor MHS - Sagñay Southeastern Annex HS | SAGÑAY | 4 |  | 1 | [5 empty] | 1968881.53 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 301984 | Vivencio Obias - Kinalansan NHS (formerly: Kinalansan NHS) | SAN JOSE | 4 |  | 1 | [5 empty] | 3138071.77 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Sur | 309753 | Salogon HS | SAN JOSE | 4 |  | 1 | [5 empty] | 1614124.45 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Sur | 309771 | Villafuerte-Peña High School | SAN JOSE | 4 |  | 1 | [5 empty] | 1176699.96 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Sur | 301986 | La Salvacion NHS | TIGAON | 4 |  | 1 | [5 empty] | 2413979.33 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Sur | 302029 | Tinawagan NHS | TIGAON | 4 |  | 1 | [5 empty] | 2198602.27 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Camarines Sur | 309766 | San Rafael National High School - Cabalinadan Annex HS | TIGAON | 4 |  | 1 | [5 empty] | 1459235.29 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 112317 | Agdangan ES | BAAO | 5 |  | 1 | [5 empty] | 1335674.46 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 301933 | Eusebia Paz Arroyo Mem. NHS | BAAO | 5 |  | 1 | [5 empty] | 881608.32 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 302014 | Pararao HS | BALATAN | 5 |  | 1 | [5 empty] | 1558409.79 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 302059 | Tapayas HS | BALATAN | 5 |  | 1 | [5 empty] | 1339454.4 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 309759 | Pulang Daga High School | BALATAN | 5 |  | 1 | [5 empty] | 1826170.87 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 302026 | Salvacion HS, Bato | BATO | 5 |  | 1 | [5 empty] | 1791228.85 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 309746 | Payak HS | BATO | 5 |  | 1 | [5 empty] | 1375160.28 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 301971 | Fabrica HS | BULA | 5 |  | 1 | [5 empty] | 1395935.08 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 301982 | Inoyonan HS | BULA | 5 |  | 1 | [5 empty] | 1527923.25 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 302041 | San Ramon HS | BULA | 5 |  | 1 | [5 empty] | 945965.75 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Camarines Sur | 301992 | Tandaay Provincial HS | NABUA | 5 |  | 1 | [5 empty] | 1219125.3 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region V | Catanduanes | 302101 | Sicmil IS | GIGMOTO | 0 |  | 1 | [5 empty] | 1251978.25 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Catanduanes | 309802 | Cobo IS | PANDAN | 0 |  | 1 | [5 empty] | 1496144.39 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Catanduanes | 302091 | Manambrag NHS | SAN ANDRES (CALOLBON) | 0 |  | 1 | [5 empty] | 2069243.38 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Catanduanes | 302092 | Mayngaway NHS | SAN ANDRES (CALOLBON) | 0 |  | 1 | [5 empty] | 1955914.93 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Catanduanes | 302098 | San Miguel Rural DHS | SAN MIGUEL | 0 |  | 1 | [5 empty] | 2230044.6 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Iriga City | 343238 | San Agustin Senior High School | IRIGA CITY | 5 |  | 1 | [5 empty] | 1224536.41 | UPGRADING | 1 | ONGOING | 100% | 100% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | for award | Y
Region V | Legaspi City | 302261 | Pag-asa NHS | LEGAZPI CITY (Capital) | 2 |  | 1 | [5 empty] | 3313445.5 | UPGRADING | 1 | Completed | 100% | 100% | 2018-09-10 |  |  |  | 2018-04-12 | 2018-04-20 | 2018-05-02 | 2018-05-18 | 2018-05-21 | ZAREPATH Construction and Supply | 3106673.93 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Sorsogon | 302184 | Barcelona National Comprehensive HS | BARCELONA | 2 |  | 1 | [5 empty] | 1501127.63 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Sorsogon | 302190 | Bulan NHS | BULAN | 2 |  | 1 | [5 empty] | 1980291.25 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Sorsogon | 302214 | Gubat NHS | GUBAT | 2 |  | 1 | [5 empty] | 1447611.59 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Sorsogon | 302212 | Gallanosa National High School | IROSIN | 2 |  | 1 | [5 empty] | 1766634.29 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Sorsogon | 302186 | Biriran NHS | JUBAN | 2 |  | 1 | [5 empty] | 1317882.11 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Sorsogon | 302187 | Juban National High School | JUBAN | 2 |  | 1 | [5 empty] | 881760.7 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Sorsogon | 302245 | Sta. Magdalena National High School | SANTA MAGDALENA | 2 |  | 1 | [5 empty] | 967339.2 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Sorsogon City | 302271 | Buenavista National High School | CITY OF SORSOGON (Capital) | 1 |  | 1 | [5 empty] | 988154.78 | UPGRADING | 1 | Completed | 100% | 100% | October 31, 2018 |  |  |  |  | April 25, 2018 | May 7, 2018 |  |  | Riders Corner | 934630.94 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Sorsogon City | 302275 | Rawis National High School | CITY OF SORSOGON (Capital) | 1 |  | 1 | [5 empty] | 1153525.17 | UPGRADING | 1 | Completed | 100% | 100% | October 31, 2018 |  |  |  |  | April 25, 2018 | May 7, 2018 |  |  | Riders Corner | 1097641.39 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Sorsogon City | 302280 | Lydia D. Martinez Memorial High School | CITY OF SORSOGON (Capital) | 1 |  | 1 | [5 empty] | 656937.92 | UPGRADING | 1 | Completed | 100% | 100% | October 31, 2018 |  |  |  |  | April 25, 2018 | May 7, 2018 |  |  | Zarepath | 650397.97 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Sorsogon City | 302272 | MERCEDES B. PERALTA SENIOR HIGH SCHOOL | CITY OF SORSOGON (Capital) | 1 |  | 1 | [5 empty] | 1351069.37 | UPGRADING | 1 | ONGOING | 80% | 80% | October 31, 2018 |  |  |  |  | April 25, 2018 | May 7, 2018 |  |  | Zarepath | 1337619.24 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VI | Aklan | 302286 | ALTAVAS NATIONAL SCHOOL | ALTAVAS | 0 |  | 1 | [5 empty] | 1828613.6343 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction | 1817691.55 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302288 | LINAYASAN NHS | ALTAVAS | 0 |  | 1 | [5 empty] | 1054537.9176 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders | 1048040.97 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302289 | BACAN NATIONAL HIGH SCHOOL | BANGA | 0 |  | 1 | [5 empty] | 1252893.42 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders | 1244975.31 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302338 | TORRALBA NATIONAL HIGH SCHOOL | BANGA | 0 |  | 1 | [5 empty] | 1087308.492 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders | 1080649.5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302291 | BATAN ACADEMY (A NAT'L SCH.) | BATAN | 0 |  | 1 | [5 empty] | 1081899 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders | 1080649.5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302294 | BAY-ANG MAGPAG-ONG NHS | BATAN | 0 |  | 1 | [5 empty] | 1170314.3204 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction | 1163311.24 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302301 | CAMANCI NATIONAL HIGH SCHOOL | BATAN | 0 |  | 1 | [5 empty] | 1054537.9176 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction | 1048224.4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302333 | RIZAL J. RODRIGUEZ Sr. NATIONAL HIGH SCHOOL | BATAN | 0 |  | 1 | [5 empty] | 1071776.59 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders | 1065266.16 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302297 | BURUANGA VOCATIONAL SCHOOL | BURUANGA | 0 |  | 1 | [5 empty] | 1433471.0093 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders | 1424067.78 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302321 | NAILE NHS | IBAJAY | 0 |  | 1 | [5 empty] | 1170314.3204 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders | 1163244.61 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302322 | NAISUD NATIONAL HIGH SCHOOL | IBAJAY | 0 |  | 1 | [5 empty] | 1087308.49 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders | 1080648.45 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302330 | IBAJAY NATIONAL HIGH SCHOOL | IBAJAY | 0 |  | 1 | [5 empty] | 1087308.492 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders | 1080649.5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302332 | REGIONAL SCIENCE HIGH SCHOOL FOR REGION VI | KALIBO (Capital) | 0 |  | 1 | [5 empty] | 1076755.992 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction | 1070325.88 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 500170 | AGUINALDO T. REPIEDAD, Sr. INTEGRATED SCHOOL | BANGA | 0 |  | 1 | [5 empty] | 1334452.73 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders | 1325969.03 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 500171 | LEZO INTEGRATED SCHOOL | LEZO | 0 |  | 1 | [5 empty] | 1334452.7327 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders | 1326561.92 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 114791 | MAYTARAW PRIMARY SCHOOL | LIBACAO | 0 |  | 1 | [5 empty] | 558245.27 | SOLAR PANEL | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | cancelled | N
Region VI | Aklan | 114800 | TAROYTOY PRIMARY SCHOOL | LIBACAO | 0 |  | 1 | [5 empty] | 778090.89 | SOLAR PANEL | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | cancelled | N
Region VI | Aklan | 302310 | LIBACAO NFVHS | LIBACAO | 0 |  | 1 | [5 empty] | 1252893.4202 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders | 1245178.92 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302311 | GUADALUPE NHS | LIBACAO | 0 |  | 1 | [5 empty] | 1180866.8204 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders | 1173499.96 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 500181 | DALAGSAAN INTRGRATED SCHOOL | LIBACAO | 0 |  | 1 | [5 empty] | 689097.71 | SOLAR PANEL | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | cancelled | N
Region VI | Aklan | 302315 | MADALAG NHS | MADALAG | 0 |  | 1 | [5 empty] | 1087308.492 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction | 1080811.72 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302305 | ANSELMO B. LEGASPI NHS | MAKATO | 0 |  | 1 | [5 empty] | 1054537.92 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders | 1047441.42 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 500172 | MAKATO IS | MAKATO | 0 |  | 1 | [5 empty] | 1499637.911 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders | 1490537.95 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302317 | MALAY NHS | MALAY | 0 |  | 1 | [5 empty] | 1252893.4202 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders | 1245413.07 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302319 | MALINAO SFPC | MALINAO | 0 |  | 1 | [5 empty] | 1252893.4202 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders | 1245399.42 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302302 | CANDELARIA NHS | NEW WASHINGTON | 0 |  | 1 | [5 empty] | 1252893.4202 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders | 1245100.04 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302303 | NEW WASHINGTON NCHS | NEW WASHINGTON | 0 |  | 1 | [5 empty] | 1252893.4202 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders | 1244985.81 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302328 | OCHANDO NHS | NEW WASHINGTON | 0 |  | 1 | [5 empty] | 1087308.492 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders | 1080248.4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302327 | NUMANCIA NSOF | NUMANCIA | 0 |  | 1 | [5 empty] | 1334452.7327 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders | 1326239.93 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 500035 | NUMANCIA IS | NUMANCIA | 0 |  | 1 | [5 empty] | 1433471.0093 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders | 1424990.47 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 500173 | TAMALAGON INTEGRATED SCHOOL | TANGALAN | 0 |  | 1 | [5 empty] | 1071776.59 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders | 1065192.94 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 500183 | JAWILI INTEGRATED SCHOOL | TANGALAN | 0 |  | 1 | [5 empty] | 988371.02 | UPGRADING | 1 | ONGOING | 0% | 80% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction | 982463.37 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Antique | 302361 | Igpalge NHS | ANINI-Y | 0 |  | 1 | [5 empty] | 1473366.6544 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1098409.6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302376 | San Roque-Ezpeleta NHS | ANINI-Y | 0 |  | 1 | [5 empty] | 763541.358 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 737317.19 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302346 | Barbaza NHS | BARBAZA | 0 |  | 1 | [5 empty] | 1574739.8 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1142078.54 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302347 | Belison NS | BELISON | 0 |  | 1 | [5 empty] | 1893925.7549 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1511206.51 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302368 | Northern Bugasong NHS | BUGASONG | 0 |  | 1 | [5 empty] | 1167437.5 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 872394.36 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302379 | Southern Bugasong NHS | BUGASONG | 0 |  | 1 | [5 empty] | 1232482 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1150672.42 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 310709 | Northern Bugasong NHS Annex - Pangalcagan Campus | BUGASONG | 0 |  | 1 | [5 empty] | 1180187.63 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 867967.43 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302348 | Bitadton NHS | CULASI | 0 |  | 1 | [5 empty] | 1560551.4094 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1063790.67 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302349 | Buhang NHS | HAMTIC | 0 |  | 1 | [5 empty] | 1468090.4044 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1099736.23 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302358 | Gov. Julio V. Macuja MCHS | HAMTIC | 0 |  | 1 | [5 empty] | 1528613.09 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1213982.18 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302366 | Moscoso-Rios NHS | HAMTIC | 0 |  | 1 | [5 empty] | 1644507.0994 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1099736.23 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 310701 | Guintas NHS | HAMTIC | 0 |  | 1 | [5 empty] | 1576380.1594 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1102389.47 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 310704 | Gen. Leandro Fullon NS | HAMTIC | 0 |  | 1 | [5 empty] | 1552046.0944 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1099736.23 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302351 | Col. Ruperto Abellon NHS | LAUA-AN | 0 |  | 1 | [5 empty] | 1654631.47 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1185529.48 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302362 | Laua-an NHS | LAUA-AN | 0 |  | 1 | [5 empty] | 1546769.8444 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1063973.99 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302363 | Libertad NVS | LIBERTAD | 0 |  | 1 | [5 empty] | 1975998.14 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1439565.2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302383 | Union NHS | LIBERTAD | 0 |  | 1 | [5 empty] | 1557322.3444 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1073165.07 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302365 | Mag-aba NHS | PANDAN | 0 |  | 1 | [5 empty] | 1543540.7794 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1063790.67 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302369 | Pandan NVHS | PANDAN | 0 |  | 1 | [5 empty] | 1844124.87 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1331376.2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302372 | Patria NS | PANDAN | 0 |  | 1 | [5 empty] | 1229855.65 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 918108.34 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302380 | Sta. Ana NHS | PANDAN | 0 |  | 1 | [5 empty] | 1494471.6544 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1205431.84 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302343 | Aureliana NHS | PATNONGON | 0 |  | 1 | [5 empty] | 1459585.0894 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 999701.27 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302359 | Igburi NHS | PATNONGON | 0 |  | 1 | [5 empty] | 832310.3157 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 668041.78 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302364 | Lirio M. Escaño, Sr. NHS | PATNONGON | 0 |  | 1 | [5 empty] | 1329218.7011 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1299724.65 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302375 | San Pedro NHS | SAN JOSE (Capital) | 0 |  | 1 | [5 empty] | 1457911.07 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1133633.31 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302344 | Barangbang NHS | SAN REMIGIO | 0 |  | 1 | [5 empty] | 1528253.2 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1094086.08 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302357 | Gideon M. Cabigunda MS | SAN REMIGIO | 0 |  | 1 | [5 empty] | 700909.9822 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 597725.96 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 310707 | Gov. Evelio B. Javier MNHS | SAN REMIGIO | 0 |  | 1 | [5 empty] | 949316.1463 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 797834.36 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302377 | Sebaste HS | SEBASTE | 0 |  | 1 | [5 empty] | 1457911.07 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1095657.93 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302354 | Egaña NHS | SIBALOM | 0 |  | 1 | [5 empty] | 693745.6283 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 617849.38 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302370 | Pangpang NHS | SIBALOM | 0 |  | 1 | [5 empty] | 673996.0322 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 614584.85 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302373 | Pis-anan NHS | SIBALOM | 0 |  | 1 | [5 empty] | 1303808.4367 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1071547.63 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302378 | Sido-San Juan NHS | SIBALOM | 0 |  | 1 | [5 empty] | 610902.0933 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 489178.33 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 310703 | Sibalom NHS | SIBALOM | 0 |  | 1 | [5 empty] | 1653380.373 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1374861.34 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 310710 | Dr. Luis E. Baraquia NHS | SIBALOM | 0 |  | 1 | [5 empty] | 634046.1785 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 549869.52 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302381 | Sta. Justa NHS | TIBIAO | 0 |  | 1 | [5 empty] | 1488330.0994 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1057724.39 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 310702 | Tario Lim MHS | TIBIAO | 0 |  | 1 | [5 empty] | 1695162.5 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1270558.12 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302345 | Barasanan NHS | TOBIAS FORNIER (DAO) | 0 |  | 1 | [5 empty] | 1506206.0344 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1098596.17 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302352 | Concepcion L. Cazeñas MS | TOBIAS FORNIER (DAO) | 0 |  | 1 | [5 empty] | 1581682.35 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1206038.48 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302353 | Diclum NHS | TOBIAS FORNIER (DAO) | 0 |  | 1 | [5 empty] | 1166834.99 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 946551.84 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302360 | Igcado NHS | TOBIAS FORNIER (DAO) | 0 |  | 1 | [5 empty] | 1379634.7568 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1028762.01 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302371 | Pascual M. Osuyos MS | TOBIAS FORNIER (DAO) | 0 |  | 1 | [5 empty] | 1327737.5618 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 1029816.89 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 302384 | Valderrama NHS | VALDERRAMA | 0 |  | 1 | [5 empty] | 1046325.6906 | UPGRADING | 1 | Completed | 100% | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply | 985225.09 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Bacolod City | 302710 | Mandalagan NHS | BACOLOD CITY (Capital) | 0 |  | 1 | [5 empty] | 1198382.95 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | Y
Region VI | Bacolod City | 302713 | Jovito H. Sayson NHS | BACOLOD CITY (Capital) | 0 |  | 1 | [5 empty] | 1243711.98 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | Y
Region VI | Bacolod City | 302718 | Teofilo M. Gensoli Sr. NHS | BACOLOD CITY (Capital) | 0 |  | 1 | [5 empty] | 1183857.74 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | Y
Region VI | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 |  | 1 | [5 empty] | 1099930.86 | UPGRADING | 1 | ONGOING |  | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Bago City | 302720 | Ramon Torres Dulao NHS | BAGO CITY | 4 |  | 1 | [5 empty] | 1102366.73 | UPGRADING | 1 | ONGOING |  | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Bago City | 302721 | Ramon Torres Ma-ao Sugar Central NHS | BAGO CITY | 4 |  | 1 | [5 empty] | 1043874.29 | UPGRADING | 1 | ONGOING |  | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Bago City | 302722 | RAMON TORRES MALINGIN NATIONAL HIGH SCHOOL | BAGO CITY | 4 |  | 1 | [5 empty] | 699622.42 | UPGRADING | 1 | ONGOING |  | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Bago City | 302723 | Ramon Torres Sagasa National High School | BAGO CITY | 4 |  | 1 | [5 empty] | 684142.75 | UPGRADING | 1 | ONGOING |  | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Bago City | 302724 | Ramon Torres Louisiana NHS | BAGO CITY | 4 |  | 1 | [5 empty] | 1200557.89 | UPGRADING | 1 | ONGOING |  | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Bago City | 302725 | Ramon Torres Taloc NHS | BAGO CITY | 4 |  | 1 | [5 empty] | 817515.25 | UPGRADING | 1 | ONGOING |  | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Cadiz City | 302726 | Cadiz Viejo NHS | CADIZ CITY | 2 |  | 1 | [5 empty] | 1457684.85 | UPGRADING | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | for suspension
Region VI | Cadiz City | 302728 | Caduha-an NHS | CADIZ CITY | 2 |  | 1 | [5 empty] | 1457684.85 | UPGRADING | 1 | ONGOING |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | for suspension
Region VI | Cadiz City | 302732 | SPED High School | CADIZ CITY | 2 |  | 1 | [5 empty] | 1433253.74 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Cadiz City | 302733 | Tiglawigan NHS | CADIZ CITY | 2 |  | 1 | [5 empty] | 1476567.94 | SOLAR PANEL | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | UPGRADING | N
Region VI | Cadiz City | 302736 | Jerusalem National High School (Villacin NHS - Jerusalem Ext. HS) | CADIZ CITY | 2 |  | 1 | [5 empty] | 1433253.74 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Cadiz City | 311403 | Mabini NHS - Alimatoc Ext. HS | CADIZ CITY | 2 |  | 1 | [5 empty] | 1529330.44 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 310802 | Dao National High School | DAO | 1 |  | 1 | [5 empty] | 577012.2934 | UPGRADING | 1 | ONGOING |  | 48% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 570121.48 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302403 | Tuburan NHS | MA-AYON | 1 |  | 1 | [5 empty] | 487575.6349 | UPGRADING | 1 | ONGOING |  | 45% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 483682.9 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302404 | Florentina B. Degala NHS | MA-AYON | 1 |  | 1 | [5 empty] | 577012.2934 | UPGRADING | 1 | ONGOING |  | 48% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 570093.12 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302412 | East Villaflores NHS | MA-AYON | 1 |  | 1 | [5 empty] | 491147.8672 | UPGRADING | 1 | ONGOING |  | 45% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 487116.68 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302413 | Maayon NHS | MA-AYON | 1 |  | 1 | [5 empty] | 1169728.0681 | UPGRADING | 1 | ONGOING |  | 57% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 1162433.4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302395 | Comsr. Luis R. Asis NHS | PANAY | 1 |  | 1 | [5 empty] | 487575.6349 | UPGRADING | 1 | ONGOING |  | 45% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 483682.9 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302398 | Felix Balgos MNHS | PANAY | 1 |  | 1 | [5 empty] | 660495.2314 | UPGRADING | 1 | ONGOING |  | 50% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 654695.2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 310812 | Pawa National High School | PANAY | 1 |  | 1 | [5 empty] | 578203.0375 | UPGRADING | 1 | ONGOING |  | 48% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 571256.62 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302410 | Leodegario D. Deocampo Sr. NHS | PANITAN | 1 |  | 1 | [5 empty] | 641705.0278 | UPGRADING | 1 | ONGOING |  | 43% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 611148.81 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302418 | Panitan NHS | PANITAN | 1 |  | 1 | [5 empty] | 645277.2601 | UPGRADING | 1 | ONGOING |  | 44% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 611969.72 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302392 | Casanayan NHS | PILAR | 1 |  | 1 | [5 empty] | 745160.4082 | UPGRADING | 1 | ONGOING |  | 52% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 740395.36 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302400 | Dulangan NHS | PILAR | 1 |  | 1 | [5 empty] | 660495.2314 | UPGRADING | 1 | ONGOING |  | 50% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 654695.2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302419 | Marciano M. Patricio (Pilar) | PILAR | 1 |  | 1 | [5 empty] | 800353.36 | UPGRADING | 1 | ONGOING |  | 52% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 791538.42 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | CAPIZ | 302422 | San Nicolas NHS (Pilar) | PILAR | 1 |  | 1 | [5 empty] | 745160.4082 | UPGRADING | 1 | ONGOING |  | 52% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 738002.63 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 310811 | YATING NATIONAL HIGH SCHOOL | PILAR | 1 |  | 1 | [5 empty] | 491147.8672 | UPGRADING | 1 | ONGOING |  | 45% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 487116.68 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302405 | Hipona NHS | PONTEVEDRA | 1 |  | 1 | [5 empty] | 748732.6405 | UPGRADING | 1 | ONGOING |  | 52% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 743800.76 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302420 | Pontevedra NHS | PONTEVEDRA | 1 |  | 1 | [5 empty] | 658113.7432 | UPGRADING | 1 | ONGOING |  | 50% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 652424.93 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302388 | Cabugcabug NHS | PRESIDENT ROXAS | 1 |  | 1 | [5 empty] | 665249.7025 | UPGRADING | 1 | ONGOING |  | 51% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 659227.04 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302391 | Capiz National High School | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 359385.49 | UPGRADING | 1 | ONGOING |  | 23% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 297233.15 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302396 | Cuartero NHS | CUARTERO | 2 |  | 1 | [5 empty] | 896942.9884 | UPGRADING | 1 | ONGOING |  | 54% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 890528.4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302421 | Putian NHS | CUARTERO | 2 |  | 1 | [5 empty] | 920469.9982 | UPGRADING | 1 | ONGOING |  | 55% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 911404.75 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 310804 | Maindang NHS | CUARTERO | 2 |  | 1 | [5 empty] | 460476.3928 | UPGRADING | 1 | ONGOING |  | 41% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 454038.44 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 310808 | SAN ANTONIO NATIONAL HIGH SCHOOL | CUARTERO | 2 |  | 1 | [5 empty] | 720451.1596 | UPGRADING | 1 | ONGOING |  | 51% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 711055.12 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302385 | Arturo Jugo NHS | DAO | 2 |  | 1 | [5 empty] | 593486.4343 | UPGRADING | 1 | ONGOING |  | 48% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 568081.08 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302414 | MALONOY NATIONAL HIGH SCHOOL (DAO) | DAO | 2 |  | 1 | [5 empty] | 722824.1425 | UPGRADING | 1 | ONGOING |  | 48% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 713297.85 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302415 | Luis Escutin NHS | DAO | 2 |  | 1 | [5 empty] | 575821.5493 | UPGRADING | 1 | ONGOING |  | 51% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 568986.35 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302401 | Concepcion Castro Garcia NHS (Dumalag NHS) Sta. Cruz | DUMALAG | 2 |  | 1 | [5 empty] | 661685.9755 | UPGRADING | 1 | ONGOING |  | 50% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 655830.34 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 310806 | Dumalag Central NHS | DUMALAG | 2 |  | 1 | [5 empty] | 886226.2915 | UPGRADING | 1 | ONGOING |  | 53% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 877667.33 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302386 | Bungsuan NHS | DUMARAO | 2 |  | 1 | [5 empty] | 743969.6641 | UPGRADING | 1 | ONGOING |  | 52% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 733287.85 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302402 | Estefania Montemayor NHS | DUMARAO | 2 |  | 1 | [5 empty] | 833406.3226 | UPGRADING | 1 | ONGOING |  | 54% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 822785.16 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302416 | Manuel F. Onato NHS | DUMARAO | 2 |  | 1 | [5 empty] | 751114.1287 | UPGRADING | 1 | ONGOING |  | 53% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 740041.9 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302417 | Ramon A. Benjamin Sr. NHS | DUMARAO | 2 |  | 1 | [5 empty] | 632196.7399 | UPGRADING | 1 | ONGOING |  | 48% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 627717.72 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 310814 | Presentacion Diez Gregorio NHS | DUMARAO | 2 |  | 1 | [5 empty] | 745160.4082 | UPGRADING | 1 | ONGOING |  | 52% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 734413.53 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302406 | Ivisan NHS | IVISAN | 2 |  | 1 | [5 empty] | 835787.8108 | UPGRADING | 1 | ONGOING |  | 54% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 825036.51 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 310807 | Basiao NHS (formerly Ext. of Ivisan NHS) | IVISAN | 2 |  | 1 | [5 empty] | 829834.0903 | UPGRADING | 1 | ONGOING |  | 54% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 819408.14 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302407 | Macario Delfin Bermejo NHS | JAMINDAN | 2 |  | 1 | [5 empty] | 834605.572 | UPGRADING | 1 | ONGOING |  | 54% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 823919.46 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302408 | Jagnaya NHS | JAMINDAN | 2 |  | 1 | [5 empty] | 665258.2078 | UPGRADING | 1 | ONGOING |  | 51% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 659235.74 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302409 | Jamindan NHS | JAMINDAN | 2 |  | 1 | [5 empty] | 671211.9283 | UPGRADING | 1 | ONGOING |  | 51% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 659558.6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302411 | Lucero NHS | JAMINDAN | 2 |  | 1 | [5 empty] | 666448.9519 | UPGRADING | 1 | ONGOING |  | 51% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 660370.87 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302397 | David Moises MHS | MAMBUSAO | 2 |  | 1 | [5 empty] | 889798.5238 | UPGRADING | 1 | ONGOING |  | 53% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 881044.35 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 310805 | MAMBUSAO NATIONAL HIGH SCHOOL | MAMBUSAO | 2 |  | 1 | [5 empty] | 890989.2679 | UPGRADING | 1 | ONGOING |  | 54% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 882170.02 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 310813 | Mambusao East NHS (ext. of David Moises) | MAMBUSAO | 2 |  | 1 | [5 empty] | 883844.8033 | UPGRADING | 1 | ONGOING |  | 54% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 875415.98 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302424 | Sapian National High School | SAPI-AN | 2 |  | 1 | [5 empty] | 1228794.2095 | UPGRADING | 1 | ONGOING |  | 57% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 1198341.71 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 310810 | Lonoy National High School | SAPI-AN | 2 |  | 1 | [5 empty] | 749774.8687 | UPGRADING | 1 | ONGOING |  | 51% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 727257.71 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302399 | Vicente Andaya Sr. NHS | SIGMA | 2 |  | 1 | [5 empty] | 575821.5493 | UPGRADING | 1 | ONGOING |  | 48% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 564432.92 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 310815 | Mianay NHS | SIGMA | 2 |  | 1 | [5 empty] | 718069.6714 | UPGRADING | 1 | ONGOING |  | 50% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 708803.77 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302389 | Camburanan NHS | TAPAZ | 2 |  | 1 | [5 empty] | 574630.8052 | UPGRADING | 1 | ONGOING |  | 48% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 563307.25 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302390 | Candelaria NHS | TAPAZ | 2 |  | 1 | [5 empty] | 574630.8052 | UPGRADING | 1 | ONGOING |  | 48% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 563307.25 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302393 | Col. Patrocinio Artuz NHS | TAPAZ | 2 |  | 1 | [5 empty] | 578203.0375 | UPGRADING | 1 | ONGOING |  | 48% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 571256.62 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 302423 | San Nicolas NHS (Tapaz) | TAPAZ | 2 |  | 1 | [5 empty] | 575821.5493 | UPGRADING | 1 | ONGOING |  | 48% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 568986.35 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 310801 | Bagong Barrio NHS | TAPAZ | 2 |  | 1 | [5 empty] | 574630.8052 | UPGRADING | 1 | ONGOING |  | 48% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 563307.25 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 310803 | Tapaz NHS | TAPAZ | 2 |  | 1 | [5 empty] | 578203.0375 | UPGRADING | 1 | ONGOING |  | 48% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 571256.62 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | CAPIZ | 310809 | REV. TOMAS CONEJAR NHS | TAPAZ | 2 |  | 1 | [5 empty] | 578203.0375 | UPGRADING | 1 | ONGOING |  | 48% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 571256.62 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Capiz | 311705 | Candelaria NHS- Roxas Ext. | TAPAZ | 2 |  | 1 | [5 empty] | 631014.5011 | UPGRADING | 1 | ONGOING |  | 48% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services | 621557.81 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Escalante City | 302625 | Escalante NHS | CITY OF ESCALANTE | 1 |  | 1 | [5 empty] | 1141365.67 | UPGRADING | 1 | ONGOING |  | 64% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Guimaras | 310901 | Ayangan National High School | SIBUNAG | 0 |  | 1 | [5 empty] | 3911646.12 | UPGRADING | 1 | ONGOING |  | 0% | Sept. 30, 2018 |  | 02-2018 -lot 1 |  | March 12, 2018 | April 3, 2018 | April 3, 2018 | April 18, 2018 | May 18, 2018 | Noe's Builders | 3,660,995.52 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Iloilo | 302445 | Alejandro Firmeza MNHS | MIAGAO | 1 |  | 1 | [5 empty] | 3134244.08 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | rebid | Y
Region VI | Iloilo | 302531 | Miagao NHS | MIAGAO | 1 |  | 1 | [5 empty] | 4841253.95 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | for ntp | Y
Region VI | Iloilo | 302514 | Jose Facultad MNHS | POTOTAN | 3 |  | 1 | [5 empty] | 2447822.13 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | rebid | Y
Region VI | Iloilo | 302556 | Pototan National Comprehensive High School | POTOTAN | 3 |  | 1 | [5 empty] | 4063058.75 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | for ntp | Y
Region VI | Iloilo | 302455 | Banate NHS | BANATE | 4 |  | 1 | [5 empty] | 4136526.85 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | for ntp | Y
Region VI | Iloilo | 302489 | De La Paz National High School | BANATE | 4 |  | 1 | [5 empty] | 3496108.79 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | rebid | Y
Region VI | Iloilo | 302490 | Dingle NHS | DINGLE | 4 |  | 1 | [5 empty] | 4041949.4 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | for ntp | Y
Region VI | Iloilo | 311008 | Rufino G. Palabrica, Sr. NHS | DINGLE | 4 |  | 1 | [5 empty] | 3116337.49 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | rebid | Y
Region VI | Iloilo | 302532 | Milan NHS | LEMERY | 5 |  | 1 | [5 empty] | 2546414.24 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | rebid | Y
Region VI | Iloilo City | 302738 | Iloilo City NHS | ILOILO CITY (Capital) | 0 |  | 1 | [5 empty] | 4475369.9 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Kabankalan City | 117839 | D.C.Gurrucharri MS | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1189719.39 | UPGRADING | 1 | Completed |  | 100% | September 13,2018 |  |  | 2018-012 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 9,2018 | Micro-asia Builders Corporation | 1179653.73 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Kabankalan City | 117859 | Hilamonan ES | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1235574.22 | UPGRADING | 1 | Completed |  | 100% | September 13,2018 |  |  | 2018-012 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 9,2018 | Micro-asia Builders Corporation | 1222832.52 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Kabankalan City | 117867 | Pinaguinpinan ES | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1405408.16 | UPGRADING | 1 | Completed |  | 100% | September 8,2018 |  |  | 2018-013 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. | 1393914.58 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Kabankalan City | 117872 | Yanog ES | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 477986.55 | UPGRADING | 1 | Completed |  | 100% | September 8,2018 |  |  | 2018-013 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. | 471075.51 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Kabankalan City | 117885 | Locotan ES | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1524238.54 | UPGRADING | 1 | Completed |  | 100% | September 13,2018 |  |  | 2018-014 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 9,2018 | Micro-asia Builders Corporation | 1510168.12 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Kabankalan City | 117887 | Magballo ES | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1674056.79 | UPGRADING | 1 | Completed |  | 100% | September 8,2018 |  |  | 2018-013 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. | 1661209.91 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Kabankalan City | 117894 | Talubangi ES | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1294087.86 | UPGRADING | 1 | Completed |  | 100% | September 13,2018 |  |  | 2018-012 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 9,2018 | Micro-asia Builders Corporation | 1283512.02 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Kabankalan City | 117895 | Tapi ES | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 2109898.02 | UPGRADING | 1 | Completed |  | 100% | September 13, 2018 |  |  | 2018-014 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 8,2018 | Micro-asia Builders Corporation | 2090797.87 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Kabankalan City | 302785 | Bantayan NHS | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1242920.54 | UPGRADING | 1 | ONGOING |  | 95% | September 8,2018 |  |  | 2018-011 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. | 1233763.67 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1079432.83 | UPGRADING | 1 | ONGOING |  | 95% | September 8,2018 |  |  | 2018-009 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. | 1070675.04 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1062593.61 | UPGRADING | 1 | ONGOING |  | 95% | September 8,2018 |  |  | 2018-009 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. | 1053919.59 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Kabankalan City | 302792 | Camansi NHS | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 735237.11 | UPGRADING | 1 | ONGOING |  | 95% | September 8,2018 |  |  | 2018-010 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. | 729079.2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1470360.01 | UPGRADING | 1 | ONGOING |  | 95% | September 8,2018 |  |  | 2018-009 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. | 1459657.31 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Kabankalan City | 302796 | Salong NHS | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1211309.76 | UPGRADING | 1 | ONGOING |  | 95% | September 8,2018 |  |  | 2018-010 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. | 1203264.7 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 777804.47 | UPGRADING | 1 | ONGOING |  | 95% | September 8,2018 |  |  | 2018-010 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. | 771434.8 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Kabankalan City | 302798 | PINAGUINPINAN NHS | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1178458.45 | UPGRADING | 1 | ONGOING |  | 95% | September 8,2018 |  |  | 2018-011 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. | 1169522.29 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Kabankalan City | 302800 | Tampalon NHS | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1066144.14 | UPGRADING | 1 | ONGOING |  | 95% | September 8,2018 |  |  | 2018-010 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. | 1058821.3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Kabankalan City | 302801 | Tapi NHS | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1141365.67 | UPGRADING | 1 | ONGOING |  | 95% | September 8,2018 |  |  | 2018-011 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. | 1132714.04 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Kabankalan City | 312101 | TAN-AWAN NHS | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1015085.74 | UPGRADING | 1 | ONGOING |  | 95% | September 8,2018 |  |  | 2018-009 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. | 1006648.06 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Negros Occidental | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 |  | 1 | [5 empty] | 5285721.3 | UPGRADING | 1 | Completed | 65% | 100% |  |  | 5460136 | 18-09-013 | July 3, 2018 | July 11, 2018 | August 20, 2018 | September 10, 2018 | September 21, 2018 | TMTC Construction and Supply | 4974653.02 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Negros Occidental | 302652 | Inocencio V. Ferrer SOF (TASOF) (under the Reg'l Office) | CITY OF TALISAY | 3 |  | 1 | [5 empty] | 3764775.05 | UPGRADING | 1 | ONGOING | 57% | 95% |  |  | 5460154 | 18-09-014 | July 3, 2018 | July 11, 2018 | July 23, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise | 3721032.46 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Negros Occidental | 302678 | Rafael B. Lacson NHS | CITY OF TALISAY | 3 |  | 1 | [5 empty] | 3817604.51 | UPGRADING | 1 | Completed | 39% | 100% |  |  | 5605695 | 18-10-015 | September 4, 2018 | September 12, 2018 | September 24, 2018 | October 15, 2018 | November 27, 2018 | LJPM Builders and Construction Supply | 3788330.6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Negros Occidental | 302695 | Victorias National High School | CITY OF VICTORIAS | 3 |  | 1 | [5 empty] | 5241938.17 | UPGRADING | 1 | Completed | 39% | 100% |  |  | 5605347 | 18-10-014 | September 4, 2018 | September 12, 2018 | September 24, 2018 | October 15, 2018 | November 27, 2018 | LJPM Builders and Construction Supply | 5205258.47 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Negros Occidental | 302609 | Cansilayan NHS | MURCIA | 3 |  | 1 | [5 empty] | 1274910.45 | UPGRADING | 1 | Completed | 38% | 100% |  |  | 5463534 | 18-09-017 | July 4, 2018 | July 12, 2018 | July 24, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise | 1249959.61 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Negros Occidental | 302670 | Murcia National High School | MURCIA | 3 |  | 1 | [5 empty] | 3382586.69 | UPGRADING | 1 | ONGOING | 53% | 95% |  |  | 5460097 | 18-09-012 | July 3, 2018 | July 11, 2018 | July 23, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise | 3346741.14 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Negros Occidental | 302677 | Pontevedra NHS | PONTEVEDRA | 4 |  | 1 | [5 empty] | 3817604.51 | UPGRADING | 1 | Completed | 75% | 100% |  |  | 5463520 | 18-09-016 | July 4, 2018 | July 12, 2018 | July 24, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise | 3780045.51 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Negros Occidental | 116875 | Nabu-ac ES | BINALBAGAN | 5 |  | 1 | [5 empty] | 473564.08 | SOLAR PANEL | 1 | Completed | 40% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | allotment to be returned, no CAF send to EFD | N
Region VI | Negros Occidental | 116882 | Binadlan ES | BINALBAGAN | 5 |  | 1 | [5 empty] | 881548.26 | SOLAR PANEL | 1 | Completed | 40% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VI | Negros Occidental | 117087 | Tiqui ES | CITY OF HIMAMAYLAN | 5 |  | 1 | [5 empty] | 614377.15 | SOLAR PANEL | 1 | Completed | 40% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VI | Negros Occidental | 302651 | Hinigaran NHS | HINIGARAN | 5 |  | 1 | [5 empty] | 5608104.57 | UPGRADING | 1 | Completed | 84% | 100% |  |  | 5460162 | 18-09-015 | July 3, 2018 | July 11, 2018 | August 2, 2018 | September 10, 2018 | September 21, 2018 | TMTC Construction and Supply | 5180471.84 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Negros Occidental | 302668 | Negros Occ. NAISHI ( under the Reg'l Office) | HINIGARAN | 5 |  | 1 | [5 empty] | 3745342.73 | UPGRADING | 1 | Completed | 76% | 100% |  |  | 5460063 | 18-09-011 | July 3, 2018 | July 11, 2018 | August 2, 2018 | September 10, 2018 | September 21, 2018 | TMTC Construction and Supply | 3461829.73 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Negros Occidental | 302653 | Isabela National High School | ISABELA | 5 |  | 1 | [5 empty] | 2814054.98 | UPGRADING | 1 | Completed | 30% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Negros Occidental | 117256 | Agogolo ES | MOISES PADILLA (MAGALLON) | 5 |  | 1 | [5 empty] | 1287247.06 | SOLAR PANEL | 1 | Completed | 30% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VI | Negros Occidental | 117259 | Cuyaoyao ES | MOISES PADILLA (MAGALLON) | 5 |  | 1 | [5 empty] | 881548.26 | SOLAR PANEL | 1 | Completed | 30% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VI | Negros Occidental | 117270 | Nacurohan ES | MOISES PADILLA (MAGALLON) | 5 |  | 1 | [5 empty] | 1287247.06 | SOLAR PANEL | 1 | Completed | 30% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VI | Negros Occidental | 116967 | Jerusalem ES | CAUAYAN | 6 |  | 1 | [5 empty] | 612976.08 | SOLAR PANEL | 1 | Completed | 30% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VI | Negros Occidental | 117009 | Pinamay-an ES | CAUAYAN | 6 |  | 1 | [5 empty] | 1079342.74 | SOLAR PANEL | 1 | Completed | 30% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VI | Negros Occidental | 117359 | Hda. Maricalum ES | CITY OF SIPALAY | 6 |  | 1 | [5 empty] | 875895.2 | SOLAR PANEL | 1 | Completed | 30% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VI | Negros Occidental | 117378 | Patag Magbanua ES | CITY OF SIPALAY | 6 |  | 1 | [5 empty] | 1491653.57 | SOLAR PANEL | 1 | Completed | 30% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VI | Negros Occidental | 180521 | Dung-I ES | CITY OF SIPALAY | 6 |  | 1 | [5 empty] | 1079342.74 | SOLAR PANEL | 1 | Completed | 30% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VI | Negros Occidental | 302632 | GIL MONTILLA NATIONAL HIGH SCHOOL | CITY OF SIPALAY | 6 |  | 1 | [5 empty] | 4406315.1 | UPGRADING | 1 | Completed | 10% | 100% |  |  | 5605736 | 18-10-016 | September 4, 2018 | September 12, 2018 | September 24, 2018 | October 15, 2018 | November 27, 2018 | LJPM Builders and Construction Supply | 4372766.4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Passi City | 302806 | Efraim M. Santibanez National High School | CITY OF PASSI | 4 |  | 1 | [5 empty] | 3134244.08 | UPGRADING | 1 | ONGOING |  | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Roxas City | 117656 | Don Ynocencio del Rosario MS | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 579912.76 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 302755 | Bago NHS | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 547749.92 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 302756 | Balijuagan NHS | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 578369.05 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 302757 | Cong. Ramon A. Arnaldo HS | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 978658.94 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 302759 | Dumolog NHS | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 580044.6 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 302760 | Milibili NHS | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 578369.05 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 302761 | Tanque NHS | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 579559.79 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 311702 | Roxas City School for Philippine Craftsmen | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 679412.19 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 311703 | Marcos Fuentes IS | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 607797.44 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Sagay City | 302764 | Colonia Divina Integrated School | SAGAY CITY | 2 |  | 1 | [5 empty] | 1170095.84 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Failed Bidding. For Schedule of Bid this November 26, 2018
Region VI | Sagay City | 302765 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 |  | 1 | [5 empty] | 1496882.15 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Failed Bidding. For Schedule of Bid this November 26, 2018
Region VI | Sagay City | 302766 | Himogaan Baybay Integrated School | SAGAY CITY | 2 |  | 1 | [5 empty] | 1495260.19 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Failed Bidding. For Schedule of Bid this November 26, 2018
Region VI | Sagay City | 302767 | Sagay NHS | SAGAY CITY | 2 |  | 1 | [5 empty] | 1496882.15 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Failed Bidding. For Schedule of Bid this November 26, 2018
Region VI | Sagay City | 302768 | Bulanon National High School | SAGAY CITY | 2 |  | 1 | [5 empty] | 1191398.82 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Failed Bidding. For Schedule of Bid this November 26, 2018
Region VI | Sagay City | 302771 | Vito NHS | SAGAY CITY | 2 |  | 1 | [5 empty] | 1225112.25 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Failed Bidding. For Schedule of Bid this November 26, 2018
Region VI | Sagay City | 311802 | Sagay NHS-Rizal Ext. | SAGAY CITY | 2 |  | 1 | [5 empty] | 1271236.14 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Failed Bidding. For Schedule of Bid this November 26, 2018
Region VI | Sagay City | 311803 | Sagay NHS-Lopez Jaena Ext. | SAGAY CITY | 2 |  | 1 | [5 empty] | 1170095.84 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Failed Bidding. For Schedule of Bid this November 26, 2018
Region VI | Sagay City | 343922 | Sagay City SHS | SAGAY CITY | 2 |  | 1 | [5 empty] | 1496882.15 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Failed Bidding. For Schedule of Bid this November 26, 2018
Region VI | San Carlos City | 117755 | Rizal ES | SAN CARLOS CITY | 1 |  | 1 | [5 empty] | 1577032.92 | SOLAR PANEL | 1 | Completed |  | 100% |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2018 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VI | San Carlos City | 117759 | Gigalaman ES | SAN CARLOS CITY | 1 |  | 1 | [5 empty] | 1793278.34 | SOLAR PANEL | 1 | Completed |  | 100% |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2019 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VI | San Carlos City | 117761 | Handalago ES | SAN CARLOS CITY | 1 |  | 1 | [5 empty] | 1144542.09 | SOLAR PANEL | 1 | Completed |  | 100% |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2020 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VI | San Carlos City | 117778 | Lagha Elementary School - Extension | SAN CARLOS CITY | 1 |  | 1 | [5 empty] | 917691.67 | SOLAR PANEL | 1 | Completed |  | 100% |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2021 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VI | San Carlos City | 117797 | Pagbatangan ES | SAN CARLOS CITY | 1 |  | 1 | [5 empty] | 3955732.52 | SOLAR PANEL | 1 | Completed |  | 100% |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2022 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VI | San Carlos City | 117798 | Paniagan ES | SAN CARLOS CITY | 1 |  | 1 | [5 empty] | 928296.67 | SOLAR PANEL | 1 | ONGOING |  | 16% |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2023 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region VI | Silay City | 302778 | Brgy. Guimbala-on NHS | SILAY CITY | 3 |  | 1 | [5 empty] | 1226572.17 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Silay City | 302779 | Don Felix T. Lacson NHS (Brgy. Capitan Ramon) | SILAY CITY | 3 |  | 1 | [5 empty] | 1223049.33 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Silay City | 302781 | Brgy. E. Lopez National High School | SILAY CITY | 3 |  | 1 | [5 empty] | 1678512.43 | UPGRADING | 1 | Completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bais City | 303212 | Bais City National High School | BAIS CITY | 2 |  | 1 | [5 empty] | 4097269.85 | UPGRADING | 1 | ONGOING | 75% | 80% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Bais City | 303215 | Lonoy National High School | BAIS CITY | 2 |  | 1 | [5 empty] | 2638984.51 | UPGRADING | 1 | ONGOING | 73% | 80% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Bais City | 303216 | Bais City Science NHS | BAIS CITY | 2 |  | 1 | [5 empty] | 1627597.61 | UPGRADING | 1 | ONGOING | 75% | 80% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Bais City | 323007 | Mansangaban National HS | BAIS CITY | 2 |  | 1 | [5 empty] | 1435064.97 | UPGRADING | 1 | ONGOING | 70% | 80% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Bayawan City | 120111 | Cabigti-an ES | BASAY | 3 |  | 1 | [5 empty] | 1813292.52 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH | 1768728.41 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | SOLAR PANEL
Region VII | Bayawan City | 303217 | Basay National High School | BASAY | 3 |  | 1 | [5 empty] | 2410027.97 | UPGRADING | 1 | Completed | 25% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N | 2393026.79 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 303218 | Actin National High School | BASAY | 3 |  | 1 | [5 empty] | 1877651.65 | UPGRADING | 1 | Completed | 30% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N | 1863296.59 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 303219 | Bal-os National High School | BASAY | 3 |  | 1 | [5 empty] | 1499669.73 | UPGRADING | 1 | Completed | 45% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N | 1487208.28 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 303220 | Maglinao National High School | BASAY | 3 |  | 1 | [5 empty] | 1379975.04 | UPGRADING | 1 | Completed | 25% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N | 1368108.92 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 120131 | Kasla ES | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 767286.51 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH | 670969.06 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | SOLAR PANEL
Region VII | Bayawan City | 120146 | Canabuan PS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 1572433.82 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH | 1520756.68 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | SOLAR PANEL
Region VII | Bayawan City | 120150 | Guintana-an ES | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 1216320.41 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH | 988325.04 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | SOLAR PANEL
Region VII | Bayawan City | 120153 | Hag-um PS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 642505.31 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH | 435345.98 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | SOLAR PANEL
Region VII | Bayawan City | 120158 | Kangkawit PS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 1379061.37 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH | 1369638.42 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | SOLAR PANEL
Region VII | Bayawan City | 120159 | Lunoy Elementary School | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 1254280.16 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH | 1162458.67 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 232003 | Napo ES | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 1260825.01 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH | 1109689.97 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | SOLAR PANEL
Region VII | Bayawan City | 303221 | Bayawan National High School | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 4287728.97 | UPGRADING | 1 | Completed | 45% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N | 4258888.02 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 303227 | Dawis NHS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 2208937.86 | UPGRADING | 1 | Completed | 10% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N | 2190447.83 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 303237 | Kalumboyan NHS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 1920492.43 | UPGRADING | 1 | Completed | 20% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N | 1905937.13 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 303238 | Bugay NHS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 2286399.4 | UPGRADING | 1 | Completed | 15% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N | 2267516.46 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 303239 | Kalamtukan NHS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 2682519.69 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 2018-07-06 | 6/15/18 | 6/27/18 | 2018-05-07 | 2018-11-07 | MS CONSTN & MKTG | 2639904.02 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 303240 | Manduaw NHS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 2623847.79 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 2018-07-06 | 6/15/18 | 6/27/18 | 2018-05-07 | 2018-11-07 | MS CONSTN & MKTG | 2582259.02 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 303241 | Tabuan PCHS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 2814862.39 | UPGRADING | 1 | Completed | 10% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N | 2795857.65 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 303242 | Tayawan NHS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 2662911.37 | UPGRADING | 1 | Completed | 45% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N | 2642161.1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 303254 | Narra HS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 1881799.15 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | MS CONSTN & MKTG | 1872104.64 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 303256 | Omod National High School | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 1559432.94 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | MS CONSTN & MKTG | 1551470.34 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 321901 | Banaybanay NHS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 2306773.75 | UPGRADING | 1 | Completed | 25% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N | 2290297.1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 321902 | Bayawan City Science HS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 1428522.8 | UPGRADING | 1 | Completed | 25% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N | 1413910.11 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 321903 | Minaba HS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 1941999.9 | UPGRADING | 1 | Completed | 45% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N | 1924840.35 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 321904 | Villasol HS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 1464300.14 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 2018-07-06 | 6/15/18 | 6/27/18 | 2018-05-07 | 2018-11-07 | MS CONSTN & MKTG | 1455818.07 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 321905 | Lapay High School | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 1992340.81 | UPGRADING | 1 | Completed | 15% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N | 1974928.47 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 321906 | San Jose HS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 1431785.89 | UPGRADING | 1 | Completed | 25% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N | 1417162.97 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 321907 | Atilano B. Cabangal MHS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 1286681.59 | UPGRADING | 1 | Completed | 15% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N | 1275279.59 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 321908 | Antonio M. Lacson, Sr. MHS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 1725381.18 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | MS CONSTN & MKTG | 1716527.19 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 321909 | Malabugas HS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 2560876.57 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 2018-07-06 | 6/15/18 | 6/27/18 | 2018-05-07 | 2018-11-07 | MS CONSTN & MKTG | 2514873.29 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 321910 | Pagatban HS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 1892234.94 | UPGRADING | 1 | Completed | 35% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N | 1877816.51 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 321911 | Abundio Agarpao, Sr. MHS | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 1936621.59 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | MS CONSTN & MKTG | 1926822.56 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bayawan City | 321912 | Cansumalig High School | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | [5 empty] | 2168858.4 | UPGRADING | 1 | Completed | 100% | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | MS CONSTN & MKTG | 2157882.93 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302850 | Fatima NHS | CORTES | 1 |  | 1 | [5 empty] | 934429.73 | UPGRADING | 1 | ONGOING | 30% | 30% | [9 empty] | MEGABLUE KONTRAK CORP. |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Bohol | 302817 | Biking Tech-Voc HS | DAUIS | 1 |  | 1 | [5 empty] | 2927879.56 | UPGRADING | 1 | Completed | 90% | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302908 | Tabalong NHS | DAUIS | 1 |  | 1 | [5 empty] | 1170845.23 | UPGRADING | 1 | Completed | 90% | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302881 | Pagnito-an NHS | MARIBOJOC | 1 |  | 1 | [5 empty] | 1272128.36 | UPGRADING | 1 | Completed | 90% | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302906 | Sikatuna NHS | SIKATUNA | 1 |  | 1 | [5 empty] | 2100247.26 | UPGRADING | 1 | ONGOING | 32% | 32% | [9 empty] | MEGABLUE KONTRAK CORP. |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Bohol | 302822 | Tubigon West NHS | TUBIGON | 1 |  | 1 | [5 empty] | 1831127.71 | UPGRADING | 1 | Completed | 88% | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 312333 | Tubigon West Central HS | TUBIGON | 1 |  | 1 | [5 empty] | 1841339.03 | UPGRADING | 1 | Completed | 88% | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302886 | Pres. Carlos P. Garcia Technical Vocational School of Fisheries and Arts | BIEN UNIDO | 2 |  | 1 | [5 empty] | 2244438.83 | UPGRADING | 1 | Completed | 100% | 100% | [9 empty] | WIL TAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302830 | Cangawa NHS | BUENAVISTA | 2 |  | 1 | [5 empty] | 2190473.84 | UPGRADING | 1 | Completed | 95% | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302841 | Danao NHS | DANAO | 2 |  | 1 | [5 empty] | 1480446.26 | UPGRADING | 1 | Completed | 95% | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302842 | Cantubod NHS | DANAO | 2 |  | 1 | [5 empty] | 1473448.07 | UPGRADING | 1 | Completed | 95% | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302891 | San Jose NHS | INABANGA | 2 |  | 1 | [5 empty] | 1598514.16 | UPGRADING | 1 | Completed | 80% | 100% | [9 empty] | MAQUESERG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302913 | Tulang NHS | JETAFE | 2 |  | 1 | [5 empty] | 1705970.03 | UPGRADING | 1 | Completed | 80% | 100% | [9 empty] | MAQUESERG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302887 | San Agustin NHS | SAGBAYAN (BORJA) | 2 |  | 1 | [5 empty] | 2050773.44 | UPGRADING | 1 | Completed | 80% | 100% | [9 empty] | MAQUESERG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302888 | Eugenio V. Amores MHS | SAGBAYAN (BORJA) | 2 |  | 1 | [5 empty] | 1174611.91 | UPGRADING | 1 | Completed | 90% | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 312309 | JAPER Memorial High Shoool | SAGBAYAN (BORJA) | 2 |  | 1 | [5 empty] | 1478617.91 | UPGRADING | 1 | Completed | 90% | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2 |  | 1 | [5 empty] | 1998749.2 | UPGRADING | 1 | ONGOING | 80% | 60% | [9 empty] | MAQUESERG CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Bohol | 302816 | Biabas Trade High School | UBAY | 2 |  | 1 | [5 empty] | 1390322.41 | UPGRADING | 1 | Completed | 100% | 100% | [9 empty] | MABB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302825 | Camambugan NHS | UBAY | 2 |  | 1 | [5 empty] | 1568580.44 | UPGRADING | 1 | Completed | 100% | 100% | [9 empty] | MABB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302899 | San Pascual National Agr'l HS | UBAY | 2 |  | 1 | [5 empty] | 2030908.29 | UPGRADING | 1 | Completed | 100% | 100% | [9 empty] | MABB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302914 | Union NHS | UBAY | 2 |  | 1 | [5 empty] | 1471889.96 | UPGRADING | 1 | Completed | 100% | 100% | [9 empty] | MABB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302809 | Alicia Technical-Voc'l HS | ALICIA | 3 |  | 1 | [5 empty] | 2241906.13 | UPGRADING | 1 | Completed | 95% | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302810 | Ambassador Pablo R. Suarez, Jr. NHS | CARMEN | 3 |  | 1 | [5 empty] | 1064141.97 | UPGRADING | 1 | Completed | 80% | 100% | [9 empty] | HME CLAVITE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302860 | Katipunan NHS | CARMEN | 3 |  | 1 | [5 empty] | 2806151.62 | UPGRADING | 1 | Completed | 90% | 100% | [9 empty] | HME CLAVITE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302885 | Policronio S. Dano, Sr. HS | CARMEN | 3 |  | 1 | [5 empty] | 1112355.22 | UPGRADING | 1 | Completed | 90% | 100% | [9 empty] | HME CLAVITE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 312339 | Ponciano F. Ramasola Sr. High School | CARMEN | 3 |  | 1 | [5 empty] | 1294081.44 | UPGRADING | 1 | Completed | 80% | 100% | [9 empty] | HME CLAVITE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302884 | Pilar Technical-Vocational HS | PILAR | 3 |  | 1 | [5 empty] | 2898887.62 | UPGRADING | 1 | Completed | 100% | 100% | [9 empty] | WIL TAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302848 | Dusita High School | SIERRA BULLONES | 3 |  | 1 | [5 empty] | 1031990.82 | UPGRADING | 1 | Completed | 95% | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES | 3 |  | 1 | [5 empty] | 2750227.21 | UPGRADING | 1 | Completed | 98% | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302916 | Valencia Tech-Voc HS | VALENCIA | 3 |  | 1 | [5 empty] | 2980751.81 | UPGRADING | 1 | Completed | 95% | 100% | [9 empty] | LTS BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Carcar City | 302970 | Can-asujan NHS | CITY OF CARCAR | 1 |  | 1 | [5 empty] | 2347731.87 | UPGRADING | 1 | ONGOING | 95% | 95% | 2018-11-25 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ CAN-ASUJAN NATIONAL HIGH SCHOOL (Lot 1) | 2018-eloectrification-carcar-lot1 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-10 | 2018-08-20 | SUKI TRADING CORPORATION | 2217698.26 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Carcar City | 302972 | Carcar Central National High School (Pob. Night) | CITY OF CARCAR | 1 |  | 1 | [5 empty] | 2031404 | UPGRADING | 1 | ONGOING | 95% | 95% | 2018-11-25 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ CARCAR CENTRAL NATIONAL HIGH SCHOOL (Lot 2) | 2018-eloectrification-carcar-lot2 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-10 | 2018-08-20 | SUKI TRADING CORPORATION | 1873580.29 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Carcar City | 303016 | Maximino Noel Memorial National High School | CITY OF CARCAR | 1 |  | 1 | [5 empty] | 2770566.64 | UPGRADING | 1 | ONGOING | 95% | 95% | 2018-11-08 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ MAXIMINO NOEL MEMORIAL NATIONAL HIGH SCHOOL (Lot 3) | 2018-eloectrification-carcar-lot3 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-03 | 2018-08-03 | PJA CONSTRUCTION | 2327102.41 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Carcar City | 303066 | OCAÑA NHS | CITY OF CARCAR | 1 |  | 1 | [5 empty] | 1975444.19 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-08 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ OCAÑA NATIONAL HIGH SCHOOL (Lot 4) | 2018-eloectrification-carcar-lot4 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-03 | 2018-08-03 | PJA CONSTRUCTION | 1660698.44 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Carcar City | 303082 | ROBERTO E. SATO MEMORIAL NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1 |  | 1 | [5 empty] | 2010499.34 | UPGRADING | 1 | ONGOING | 95% | 95% | 2018-11-25 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ ROBERTO E. SATO MEMORIAL NATIONAL HIGH SCHOOL (Lot 5) | 2018-eloectrification-carcar-lot5 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-10 | 2018-08-20 | SUKI TRADING CORPORATION | 1896106.26 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Carcar City | 303126 | Valencia VOCATIONAL NHS | CITY OF CARCAR | 1 |  | 1 | [5 empty] | 2344712.74 | UPGRADING | 1 | ONGOING | 95% | 95% | 2018-11-25 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ VALENCIA VOCATIONAL NATIONAL HIGH SCHOOL (Lot 7) | 2018-eloectrification-carcar-lot6 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-10 | 2018-08-20 | SUKI TRADING CORPORATION | 2215627.09 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Carcar City | 324904 | Tuyom National High School | CITY OF CARCAR | 1 |  | 1 | [5 empty] | 2089088.32 | UPGRADING | 1 | Completed | 100% | 100% | 2018-11-08 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ TUYOM NATIONAL HIGH SCHOOL (Lot 6) | 2018-eloectrification-carcar-lot7 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-03 | 2018-08-03 | PJA CONSTRUCTION | 1743738.88 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Cebu | 302928 | Balao NHS | BARILI | 3 |  | 1 | [5 empty] | 1282976.83 | UPGRADING | 1 | ONGOING | 40% | 40% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VII | Cebu | 303069 | Bartolome & Manuela Pañares MNHS | BARILI | 3 |  | 1 | [5 empty] | 2547911.59 | UPGRADING | 1 | ONGOING | 40% | 40% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VII | Cebu | 302962 | Malingin NHS | DAANBANTAYAN | 4 |  | 1 | [5 empty] | 1250231.37 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VII | Cebu | 302964 | Tapilon National High School | DAANBANTAYAN | 4 |  | 1 | [5 empty] | 1244277.65 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VII | Cebu | 500220 | Anapog IS | San Remegio | 4 |  | 1 | [5 empty] | 1347045.04 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VII | Cebu | 500221 | Busogon IS | San Remegio | 4 |  | 1 | [5 empty] | 1067155.76 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VII | Cebu | 303030 | Lambusan NHS | SAN REMIGIO | 4 |  | 1 | [5 empty] | 1518405.3 | UPGRADING | 1 | ONGOING | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VII | Cebu | 303104 | Tabunan NHS | BORBON | 5 |  | 1 | [5 empty] | 1751641.51 | UPGRADING | 1 | ONGOING | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VII | Cebu | 303106 | Borbon NHS | BORBON | 5 |  | 1 | [5 empty] | 1792226.23 | UPGRADING | 1 | ONGOING | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VII | Cebu | 303107 | Campusong NHS | BORBON | 5 |  | 1 | [5 empty] | 1730711.16 | UPGRADING | 1 | ONGOING | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VII | Cebu | 302975 | Cantumog NHS | CARMEN | 5 |  | 1 | [5 empty] | 2388626.23 | UPGRADING | 1 | ONGOING | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VII | Cebu | 302979 | Ceferino Sususco MNHS | CATMON | 5 |  | 1 | [5 empty] | 2525970.55 | UPGRADING | 1 | ONGOING | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VII | Cebu | 302980 | Tinabyonan NHS | CATMON | 5 |  | 1 | [5 empty] | 1541167.6 | UPGRADING | 1 | ONGOING | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VII | Cebu | 312447 | Catmon Integrated School | CATMON | 5 |  | 1 | [5 empty] | 2468951.37 | UPGRADING | 1 | ONGOING | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VII | Cebu | 303062 | Mulao NHS | COMPOSTELA | 5 |  | 1 | [5 empty] | 1428334.68 | UPGRADING | 1 | ONGOING | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VII | Cebu | 312448 | Bagalnga Integrated School | COMPOSTELA | 5 |  | 1 | [5 empty] | 2018447.79 | UPGRADING | 1 | ONGOING | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VII | Cebu | 302954 | Cabangahan NHS | CONSOLACION | 6 |  | 1 | [5 empty] | 1381008.6 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Cebu | 302988 | Consolacion NHS - Day Class | CONSOLACION | 6 |  | 1 | [5 empty] | 1740293.68 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Cebu | 302989 | Consolacion NHS - Evening Class | CONSOLACION | 6 |  | 1 | [5 empty] | 1593451.38 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Cebu | 302992 | Tolotolo NHS | CONSOLACION | 6 |  | 1 | [5 empty] | 622369.41 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Cebu | 302993 | Tugbongan NHS | CONSOLACION | 6 |  | 1 | [5 empty] | 1130749.45 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Cebu | 303010 | Garing NHS | CONSOLACION | 6 |  | 1 | [5 empty] | 2014254.07 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Cebu | 302955 | Cordova NHS | CORDOBA | 6 |  | 1 | [5 empty] | 1284016.96 | UPGRADING | 1 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Dumaguete City | 303168 | Dumaguete City HS | DUMAGUETE CITY (Capital) | 2 |  | 1 | [5 empty] | 1552683.93 | UPGRADING | 1 | ONGOING | 94% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Dumaguete City | 303169 | RTPM - Dumaguete Science HS | DUMAGUETE CITY (Capital) | 2 |  | 1 | [5 empty] | 821230.26 | UPGRADING | 1 | Completed | 98% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Dumaguete City | 303171 | Taclobo NHS | DUMAGUETE CITY (Capital) | 2 |  | 1 | [5 empty] | 836109.56 | UPGRADING | 1 | Completed | 98% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Guihulngan City | 120239 | Busay Elementary School | CITY OF GUIHULNGAN | 1 |  | 1 | [5 empty] | 938136.67 | SOLAR PANEL | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | FOR ISSUANCE OF CAF | N
Region VII | Guihulngan City | 120258 | Trinidad ES | CITY OF GUIHULNGAN | 1 |  | 1 | [5 empty] | 1866055.02 | SOLAR PANEL | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | FOR ISSUANCE OF CAF | N
Region VII | Guihulngan City | 303230 | GUIHULNGAN NATIONAL AGRICULTURAL SCHOOL | CITY OF GUIHULNGAN | 1 |  | 1 | [5 empty] | 1657858.69 | UPGRADING | 1 | REVERTED | [13 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Region VII | Guihulngan City | 303231 | Guihulngan NHS - Poblacion | CITY OF GUIHULNGAN | 1 |  | 1 | [5 empty] | 2259021.5 | UPGRADING | 1 | REVERTED | [13 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Region VII | Guihulngan City | 312952 | Guihulngan National High School-Poblacion (Linantuyan Annex) | CITY OF GUIHULNGAN | 1 |  | 1 | [5 empty] | 1382422.08 | UPGRADING | 1 | REVERTED | [13 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Region VII | Lapu-Lapu City | 303174 | Bankal NHS | LAPU-LAPU CITY (OPON) | 6 |  | 1 | [5 empty] | 1934925.66 | UPGRADING | 1 | COMPLETED | 100% | 100% | September 27, 2018 | [6 empty] | April 23, 2018 | June 27, 2018 | Golden Hammer Const. & Supply | 1913070.65 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Lapu-Lapu City | 303177 | Lo-ok National High School | LAPU-LAPU CITY (OPON) | 6 |  | 1 | [5 empty] | 1823236.74 | UPGRADING | 1 | COMPLETED | 100% | 100% | September 27, 2018 | [6 empty] | April 23, 2018 | June 27, 2018 | Golden Hammer Const. & Supply | 2237468.87 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Lapu-Lapu City | 303184 | Pajo NHS | LAPU-LAPU CITY (OPON) | 6 |  | 1 | [5 empty] | 2250748.96 | UPGRADING | 1 | COMPLETED | 100% | 100% | September 27, 2018 | [6 empty] | April 23, 2018 | June 27, 2018 | Golden Hammer Const. & Supply | 1813193.79 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Mandaue City | 303195 | Canduman NHS | MANDAUE CITY | 6 |  | 1 | [5 empty] | 1191779.37 | UPGRADING | 1 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Mandaue City | 303198 | Jagobiao NHS | MANDAUE CITY | 6 |  | 1 | [5 empty] | 923407.94 | UPGRADING | 1 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Mandaue City | 303199 | Mandaue City Comprehensive NHS | MANDAUE CITY | 6 |  | 1 | [5 empty] | 1196363.52 | UPGRADING | 1 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Negros Oriental | 303277 | Mabato Provincial Community HS | AYUNGON | 1 |  | 1 | [5 empty] | 627304.52 | UPGRADING | 1 | Ongoing | 50% | 50% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | 621371.36 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 312949 | Ayungon Science High School | AYUNGON | 1 |  | 1 | [5 empty] | 484435.16 | UPGRADING | 1 | Ongoing | 50% | 50% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | 479852.65 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 312962 | Ayungon NHS - Carol-an Extension | AYUNGON | 1 |  | 1 | [5 empty] | 586439.48 | UPGRADING | 1 | Ongoing | 50% | 50% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | 580894.29 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 303229 | Demetrio Alviola NHS - Nalundan Annex | BINDOY (PAYABON) | 1 |  | 1 | [5 empty] | 457294.38 | UPGRADING | 1 | Ongoing | 16% | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | 452742 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 312917 | Cabcaban CHS | BINDOY (PAYABON) | 1 |  | 1 | [5 empty] | 616259.07 | UPGRADING | 1 | Ongoing | 16% | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | 610118.41 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 303251 | Manjuyod National High School | MANJUYOD | 1 |  | 1 | [5 empty] | 1027398.05 | UPGRADING | 1 | Ongoing | 97% | 97% | 2018-09-29 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-13 | MAQUESERG Contruction & Gen. Merchandise | 1009106.87 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 312902 | Sampiniton Provincial Community HS | MANJUYOD | 1 |  | 1 | [5 empty] | 596480.44 | UPGRADING | 1 | Ongoing | 97% | 97% | 2018-09-29 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-13 | MAQUESERG Contruction & Gen. Merchandise | 588081.49 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 312961 | Manjuyod Science High School | MANJUYOD | 1 |  | 1 | [5 empty] | 466436.24 | UPGRADING | 1 | Ongoing | 18% | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | 461791.5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 303211 | Bagtic National High School | MABINAY | 2 |  | 1 | [5 empty] | 659054.43 | UPGRADING | 1 | Ongoing | 16% | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | 652943.57 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 303245 | Barras Annex National High School | MABINAY | 2 |  | 1 | [5 empty] | 577903.93 | UPGRADING | 1 | Ongoing | 93% | 97% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 571012.457 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | recommended for termination
Region VII | Negros Oriental | 303246 | Dahile PCHS | MABINAY | 2 |  | 1 | [5 empty] | 605633.91 | UPGRADING | 1 | Ongoing | 93% | 97% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 599603.8 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | recommended for termination
Region VII | Negros Oriental | 303248 | Tara Provincial Community High School | MABINAY | 2 |  | 1 | [5 empty] | 659889.99 | UPGRADING | 1 | Ongoing | 16% | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | 653772.57 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 303260 | Pantao NHS | MABINAY | 2 |  | 1 | [5 empty] | 663993.05 | UPGRADING | 1 | Ongoing | 93% | 97% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 657672.6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 312923 | Canggohob HS | MABINAY | 2 |  | 1 | [5 empty] | 479603.42 | UPGRADING | 1 | Ongoing | 16% | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | 475162.71 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 312924 | Campanun-an Provincial Community High School | MABINAY | 2 |  | 1 | [5 empty] | 576820.9 | UPGRADING | 1 | Ongoing | 93% | 97% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 570934.14 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 312951 | Mabinay Science High School | MABINAY | 2 |  | 1 | [5 empty] | 623832.57 | UPGRADING | 1 | Ongoing | 93% | 97% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 616712.597 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 312959 | Mayaposi Community High School | MABINAY | 2 |  | 1 | [5 empty] | 631634.17 | UPGRADING | 1 | Ongoing | 93% | 97% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 624474.947 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 312967 | Manlingay High School | MABINAY | 2 |  | 1 | [5 empty] | 471654.73 | UPGRADING | 1 | Ongoing | 93% | 97% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 466289.46 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 303278 | Crisostomo O. Retes NHS (Tampi NHS) | SAN JOSE | 2 |  | 1 | [5 empty] | 769006.9 | UPGRADING | 1 | Completed | 92% | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 759164.24 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 303266 | San Miguel NHS | BACONG | 3 |  | 1 | [5 empty] | 778525.78 | UPGRADING | 1 | Completed | 92% | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 768635.76 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Negros Oriental | 303267 | Ong Che Tee - Bacong HS | BACONG | 3 |  | 1 | [5 empty] | 566903.28 | UPGRADING | 1 | Completed | 92% | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 560064.537 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Negros Oriental | 303224 | Apolinar B. Macias MHS (Casile NHS) | DAUIN | 3 |  | 1 | [5 empty] | 674191.81 | UPGRADING | 1 | Completed | 92% | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 666821.297 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Negros Oriental | 303225 | Dauin NHS | DAUIN | 3 |  | 1 | [5 empty] | 694285.21 | UPGRADING | 1 | Completed | 92% | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 686814.167 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Negros Oriental | 312919 | Malongcay Dacu HS | DAUIN | 3 |  | 1 | [5 empty] | 618741.84 | UPGRADING | 1 | Completed | 92% | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 611657.187 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Negros Oriental | 312921 | Froilan A. Alanano MHS | DAUIN | 3 |  | 1 | [5 empty] | 541118.53 | UPGRADING | 1 | Completed | 92% | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 534418.067 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Negros Oriental | 303206 | Avocado Community High School | SANTA CATALINA | 3 |  | 1 | [5 empty] | 549572.35 | UPGRADING | 1 | Ongoing | 16% | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | 544576 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 303250 | Casiano Z. Napigkit NHS (Manalongon NHS) | SANTA CATALINA | 3 |  | 1 | [5 empty] | 755011.31 | UPGRADING | 1 | Completed | 92% | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 745225.04 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Negros Oriental | 312929 | Cawitan High School | SANTA CATALINA | 3 |  | 1 | [5 empty] | 633408.36 | UPGRADING | 1 | Ongoing | 16% | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | 599043.49 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 312932 | Eligio T. Monte De Ramos HS (Milagrosa HS) | SANTA CATALINA | 3 |  | 1 | [5 empty] | 642188.83 | UPGRADING | 1 | Ongoing | 16% | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | 638347.21 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 312933 | Kakha High School | SANTA CATALINA | 3 |  | 1 | [5 empty] | 569707.8 | UPGRADING | 1 | Ongoing | 16% | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | 566218.9 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 312934 | San Miguel High School | SANTA CATALINA | 3 |  | 1 | [5 empty] | 685131.65 | UPGRADING | 1 | Completed | 92% | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 675674.96 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Negros Oriental | 312935 | Sta. Catalina Science High School | SANTA CATALINA | 3 |  | 1 | [5 empty] | 682615.65 | UPGRADING | 1 | Ongoing | 35% | 35% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | 678509.1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 312936 | Nagbalaye HS | SANTA CATALINA | 3 |  | 1 | [5 empty] | 661279.82 | UPGRADING | 1 | Ongoing | 27% | 27% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | 655171.5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 303252 | Maria Macahig National High School | SIATON | 3 |  | 1 | [5 empty] | 748699.97 | UPGRADING | 1 | Ongoing | 16% | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | 740620.75 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 312942 | Sumaliring HS [Inalad HS] | SIATON | 3 |  | 1 | [5 empty] | 664886.16 | UPGRADING | 1 | Ongoing | 16% | 92% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | 657899.52 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 303291 | Valencia National High School (Valencia Tech. Sch.) | VALENCIA (LUZURRIAGA) | 3 |  | 1 | [5 empty] | 891964.53 | UPGRADING | 1 | Completed | 92% | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 881506.89 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Negros Oriental | 312908 | Balugo National High School | VALENCIA (LUZURRIAGA) | 3 |  | 1 | [5 empty] | 773368.09 | UPGRADING | 1 | COMPLETED | 92% | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 763493.11 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Negros Oriental | 312947 | Zamboanguita Science HS | ZAMBOANGUITA | 3 |  | 1 | [5 empty] | 651972.91 | UPGRADING | 1 | COMPLETED | 92% | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. | 644724.747 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Siquijor | 303297 | Enrique Villanueva National High School | ENRIQUE VILLANUEVA | 0 |  | 1 | [5 empty] | 2787612.5 | UPGRADING | 1 | Ongoing | 45% | 55% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | 2338366.12 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Siquijor | 303303 | Basac National High School | LARENA | 0 |  | 1 | [5 empty] | 5937774.35 | UPGRADING | 1 | Ongoing | 35% | 45% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | 5314986.57 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Siquijor | 303293 | Campalanas National High School | LAZI | 0 |  | 1 | [5 empty] | 2636170.21 | UPGRADING | 1 | Ongoing | 55% | 75% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | 2467591.87 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Siquijor | 303295 | Leon Parami High School | LAZI | 0 |  | 1 | [5 empty] | 5722840.8 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | 5216947.16 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Siquijor | 303306 | DepED-Lazi National Agricultural School | LAZI | 0 |  | 1 | [5 empty] | 3700754.43 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | 3399753.16 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Siquijor | 120669 | Candaping Elementary School | MARIA | 0 |  | 1 | [5 empty] | 2800298.26 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VII | Siquijor | 303300 | Tambisan National High School | SAN JUAN | 0 |  | 1 | [5 empty] | 3067762.82 | UPGRADING | 1 | Ongoing | 60% | 80% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | 2795296.97 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Siquijor | 303305 | Catulayan National High School | SAN JUAN | 0 |  | 1 | [5 empty] | 2955591.79 | UPGRADING | 1 | Ongoing | 45% | 65% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | 2788223.92 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Siquijor | 120694 | Cang-alwang Elementary School | SIQUIJOR (Capital) | 0 |  | 1 | [5 empty] | 1677180.96 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VII | Siquijor | 303296 | Cang-alwang National High School | SIQUIJOR (Capital) | 0 |  | 1 | [5 empty] | 1677180.96 | UPGRADING | 1 | COMPLETED | 45% | 100% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | 1352254.37 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Siquijor | 303298 | San Antonio National High School | SIQUIJOR (Capital) | 0 |  | 1 | [5 empty] | 8550699.35 | UPGRADING | 1 | Ongoing | 65% | 80% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | 8162560.7 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Siquijor | 303301 | Siquijor Provincial Science High School | SIQUIJOR (Capital) | 0 |  | 1 | [5 empty] | 1606427.72 | UPGRADING | 1 | COMPLETED | 95% | 100% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | 1353112.32 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Siquijor | 303302 | Banban National High School | SIQUIJOR (Capital) | 0 |  | 1 | [5 empty] | 2657032.83 | UPGRADING | 1 | Ongoing | 30% | 95% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | 2608113.44 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Tagbilaran City | 302876 | Tagbilaran City Science High School | TAGBILARAN CITY (Capital) | 1 |  | 1 | [5 empty] | 1682365.93 | UPGRADING | 1 | Completed | 10% | 100% | December 31, 2018 | [8 empty] | DOLCI Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Talisay City | 119799 | Jaclupan ES | CITY OF TALISAY | 1 |  | 1 | [5 empty] | 478753.59 | UPGRADING | 1 | COMPLETED | 50% | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction | 475256.61 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Talisay City | 303020 | Pooc NHS (Jaclupan NHS - Pooc Ext.) | CITY OF TALISAY | 1 |  | 1 | [5 empty] | 460428.75 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction | 456866.8163 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Talisay City | 303040 | Lawaan NHS, Talisay | CITY OF TALISAY | 1 |  | 1 | [5 empty] | 509937.6 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction | 505787.3821 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Talisay City | 303056 | Mohon NHS (Mohon Divino Amore NHS) | CITY OF TALISAY | 1 |  | 1 | [5 empty] | 415655.55 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction | 412816.1243 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Talisay City | 303088 | San Roque NHS ( Laray NHS - Jaclupan NHS Ext.) | CITY OF TALISAY | 1 |  | 1 | [5 empty] | 415293.38 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction | 412850.5643 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Talisay City | 303111 | Tabunok Night HS | CITY OF TALISAY | 1 |  | 1 | [5 empty] | 475590.16 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction | 471024.6803 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Talisay City | 303113 | Talisay City National High School | CITY OF TALISAY | 1 |  | 1 | [5 empty] | 570530.15 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction | 566019.5863 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Talisay City | 322201 | Maghaway NHS | CITY OF TALISAY | 1 |  | 1 | [5 empty] | 552344.64 | UPGRADING | 1 | COMPLETED | 50% | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction | 547585.844 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Talisay City | 322204 | Bulacao NHS | CITY OF TALISAY | 1 |  | 1 | [5 empty] | 435845.86 | UPGRADING | 1 | COMPLETED | 50% | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction | 432795.6713 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Talisay City | 322206 | Lagtang Night HS | CITY OF TALISAY | 1 |  | 1 | [5 empty] | 431634.01 | UPGRADING | 1 | COMPLETED | 50% | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction | 428633.8283 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Talisay City | 322208 | Tapul NHS | CITY OF TALISAY | 1 |  | 1 | [5 empty] | 483053.92 | UPGRADING | 1 | COMPLETED | 50% | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction | 479566.3253 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Tanjay City | 303279 | Tanjay Legislated HS | CITY OF TANJAY | 2 |  | 1 | [5 empty] | 960052.61 | UPGRADING | 1 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Tanjay City | 303280 | Tanjay NHS (Opao) | CITY OF TANJAY | 2 |  | 1 | [5 empty] | 1463896.74 | UPGRADING | 1 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Tanjay City | 303283 | Tanjay Science HS | CITY OF TANJAY | 2 |  | 1 | [5 empty] | 835379.14 | UPGRADING | 1 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Tanjay City | 303284 | Lourdes L. del Prado MNHS | CITY OF TANJAY | 2 |  | 1 | [5 empty] | 1361578.17 | UPGRADING | 1 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Tanjay City | 322303 | Nagsala HS | CITY OF TANJAY | 2 |  | 1 | [5 empty] | 1848529.77 | UPGRADING | 1 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Tanjay City | 303273 | Sta. Agueda NHS | PAMPLONA | 2 |  | 1 | [5 empty] | 1027752.07 | UPGRADING | 1 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Tanjay City | 303274 | Isidoro Salma MHS (Balayong ) | PAMPLONA | 2 |  | 1 | [5 empty] | 883293.56 | UPGRADING | 1 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Tanjay City | 312911 | Hunop Community High School | PAMPLONA | 2 |  | 1 | [5 empty] | 674059.51 | UPGRADING | 1 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Tanjay City | 312926 | Apolinario Gerarda Arnaiz HS | PAMPLONA | 2 |  | 1 | [5 empty] | 665880.84 | UPGRADING | 1 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VIII | Borongan City | 303526 | Maypangdan NHS | CITY OF BORONGAN (Capital) | 0 |  | 1 | [5 empty] | 2514611.87 | UPGRADING | 1 | COMPLETED | 100% | 100% | July 4, 2018 |  | CY 2018 BEFF - ELECTRIFICATION OF UNENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 BORONGAN CITY - LOT 1 | CY 2018 - BEFF ELECTRIFICATION - 01 | February 26, 2018 | March 7, 2018 | March 20, 2018 | March 26, 2018 | March 29, 2018 | YFL BUILDERS | 2482032.29 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Borongan City | 313504 | Benowangan NHS (Lalawigan NHS - Benowangan Annex) | CITY OF BORONGAN (Capital) | 0 |  | 1 | [5 empty] | 1481515.29 | UPGRADING | 1 | COMPLETED | 100% | 100% | July 4, 2019 |  | CY 2018 BEFF - ELECTRIFICATION OF UNENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 BORONGAN CITY - LOT 2 | CY 2018 - BEFF ELECTRIFICATION - 02 | February 26, 2018 | March 7, 2018 | March 20, 2018 | March 26, 2018 | March 29, 2018 | TUBIGAN BUILDERS | 1468931.48 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Borongan City | 313515 | E. Samar NCHS - Supt. Fidel E. Anacta, Sr. MHS Annex | CITY OF BORONGAN (Capital) | 0 |  | 1 | [5 empty] | 2534404.17 | UPGRADING | 1 | COMPLETED | 100% | 100% | July 4, 2020 |  | CY 2018 BEFF - ELECTRIFICATION OF UNENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 BORONGAN CITY - LOT 3 | CY 2018 - BEFF ELECTRIFICATION - 03 | February 26, 2018 | March 7, 2018 | March 20, 2018 | March 26, 2018 | March 29, 2018 | YFL BUILDERS | 2501753.8 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Calbayog City | 303644 | Mag-Ubay National High School | CALBAYOG CITY | 1 |  | 1 | [5 empty] | 978107.61 | UPGRADING | 1 | COMPLETED | 40% | 100% |  |  | CAL ESUP CY2018 B1 | CAL ESUP CY2018 B1 | 2018-04-21 | 2018-04-20 | 2018-05-11 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Calbayog City | 303645 | Malaga National High School | CALBAYOG CITY | 1 |  | 1 | [5 empty] | 1485553.14 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  | CAL ESUP CY2018 B2 | CAL ESUP CY2018 B1 | 2018-04-21 | 2018-04-20 | 2018-05-11 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Calbayog City | 303646 | Oquendo National High School | CALBAYOG CITY | 1 |  | 1 | [5 empty] | 1195826.77 | UPGRADING | 1 | Completed | 55% | 100% |  |  | CAL ESUP CY2018 B3 | CAL ESUP CY2018 B1 | 2018-04-21 | 2018-04-20 | 2018-05-11 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Catbalogan City | 303623 | Silanga NHS | CITY OF CATBALOGAN (Capital) | 2 |  | 1 | [5 empty] | 967974.4 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  | CY 2018- BEFF- ESUP- R8 - CC- L1 |  | 2018-07-05 | 2018-07-13 | 2018-08-01 | 2018-08-20 | 2018-08-31 | WC CONSTRUCTION | 953285.25 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Catbalogan City | 313701 | Catbalogan NCHS | CITY OF CATBALOGAN (Capital) | 2 |  | 1 | [5 empty] | 907149.62 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  | CY 2018- BEFF- ESUP- R8 - CC- L3 |  | 2018-07-05 | 2018-07-13 | 2018-08-01 | 2018-09-03 | 2018-09-28 | RNA CONSTRUCTION AND SUPPLY | 892311.17 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Catbalogan City | 313706 | Pangdan National High School | CITY OF CATBALOGAN (Capital) | 2 |  | 1 | [5 empty] | 978526.9 | UPGRADING | 1 | Completed | 92% | 100% |  |  | CY 2018- BEFF- ESUP- R8 - CC- L2 |  | 2018-07-05 | 2018-07-13 | 2018-08-01 | 2018-09-16 | 2018-10-05 | J .Custorio Construction | 933000 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Eastern Samar | 303510 | Jipapad NHS | JIPAPAD | 0 |  | 1 | [5 empty] | 1899932.73 | UPGRADING | 1 | COMPLETED | 95% | 100% | August 25, 2018 |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 ESAMAR-LOT 4 | CY 2018-BEFF ELECTRIFICATION-04 | March 16, 2018 | March 26, 2018 | April 10, 2018 | Arpil 17, 2018 | April 20, 2018 | TUBIGAN BUILDERS | 1883623.09 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Eastern Samar | 303518 | Mercedes HS | MERCEDES | 0 |  | 1 | [5 empty] | 2174089.73 | UPGRADING | 1 | COMPLETED | 95% | 100% | August 25, 2018 |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 ESAMAR-LOT 5 | CY 2018-BEFF ELECTRIFICATION-05 | March 16, 2018 | March 26, 2018 | April 10, 2018 | Arpil 17, 2018 | April 20, 2018 | DAY-BREAK ENTERPRISES | 2133791.35 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Eastern Samar | 303516 | Matarinao SOF | SALCEDO | 0 |  | 1 | [5 empty] | 2480957.29 | UPGRADING | 1 | COMPLETED | 95% | 100% | August 25, 2018 |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 ESAMAR-LOT 3 | CY 2018-BEFF ELECTRIFICATION-03 | March 16, 2018 | March 26, 2018 | April 10, 2018 | Arpil 17, 2018 | April 20, 2018 | DAY-BREAK ENTERPRISES | 2443569.47 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Eastern Samar | 303524 | San Julian NHS | SAN JULIAN | 0 |  | 1 | [5 empty] | 2683247.19 | UPGRADING | 1 | COMPLETED | 95% | 100% | August 25, 2018 |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 ESAMAR-LOT 1 | CY 2018-BEFF ELECTRIFICATION-01 | March 16, 2018 | March 26, 2018 | April 10, 2018 | Arpil 17, 2018 | April 20, 2018 | LOBRIÑO'S CONSOLIDATED CONSTRUCTION | 2659952.85 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Eastern Samar | 303527 | Sulat NHS | SULAT | 0 |  | 1 | [5 empty] | 3227556.88 | UPGRADING | 1 | COMPLETED | 95% | 100% | August 25, 2018 |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 ESAMAR-LOT 2 | CY 2018-BEFF ELECTRIFICATION-02 | March 16, 2018 | March 26, 2018 | April 10, 2019 | Arpil 17, 2018 | April 20, 2018 | LOBRIÑO'S CONSOLIDATED CONSTRUCTION | 3199782.49 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303389 | Villaba NHS (LNCAST) | VILLABA | 3 |  | 1 | [5 empty] | 1184101.21 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  | lot 1-cy-2018-E-B1-leyte | lot 1-cy-2018-E-B1-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | R.M. PADILLO BUILDERS | 1151115.37 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303442 | Villaba National Comprehensive High School | VILLABA | 3 |  | 1 | [5 empty] | 3162822.17 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  | lot 2-cy-2018-E-B1-leyte | lot 2-cy-2018-E-B1-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | D.L. AUREO CONSTRUCTION | 3098929.27 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 313322 | Cahigan NHS | VILLABA | 3 |  | 1 | [5 empty] | 1104935.83 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  | lot 3-cy-2018-E-B1-leyte | lot 3-cy-2018-E-B1-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | NV& C CONSTRUCTION AND GENERAL SUPPLY | 1086973.98 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 313345 | Sulpa NHS | VILLABA | 3 |  | 1 | [5 empty] | 1232603.71 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  | lot 4-cy-2018-E-B1-leyte | lot 4-cy-2018-E-B1-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | AGB CONSTRUCTION AND SUPPLY | 1198725.5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Northern Samar | 303535 | Bobon School for Philippine Craftsmen | BOBON | 1 |  | 1 | [5 empty] | 3153787.21 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  | BEFF2018-B1-E-NS-L1 | BEFF2018-B1-E-NS-L1 | June 6, 2018 | June 14, 2018 | June 28, 2018 | 2018-07-25 |  | MAGA Construction & Supply | 2636473.12 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Northern Samar | 303548 | Eladio T. Balite Memorial School of Fisheries | BOBON | 1 |  | 1 | [5 empty] | 2555079.02 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  | BEFF2018-B1-E-NS-L2 | BEFF2018-B1-E-NS-L2 | June 6, 2019 | June 14, 2019 | June 28, 2018 | 2018-07-25 |  | ROSS Engineering & Construction | 2237178.28 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Northern Samar | 303541 | Catarman National High School | CATARMAN (Capital) | 1 |  | 1 | [5 empty] | 3833968.6 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  | BEFF2018-B1-E-NS-L3 | BEFF2018-B1-E-NS-L3 | June 6, 2020 | June 14, 2020 | June 28, 2018 | 2018-07-25 |  | MAGA Construction & Supply | 3205230.91 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Northern Samar | 303566 | Mondragon Agro-Ind'L HS | MONDRAGON | 1 |  | 1 | [5 empty] | 3334063.59 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  | BEFF2018-B1-E-NS-L4 | BEFF2018-B1-E-NS-L4 | June 6, 2021 | June 14, 2021 | June 28, 2018 | 2018-07-25 |  | ROSS Engineering & Construction | 2918463.7 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Northern Samar | 313605 | Leonardo M. Amigo High School | MONDRAGON | 1 |  | 1 | [5 empty] | 1149519.71 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  | BEFF2018-B1-E-NS-L5 | BEFF2018-B1-E-NS-L5 | June 6, 2022 | June 14, 2022 | June 28, 2018 | 2018-07-25 |  | MAGA Construction & Supply | 996008.08 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Northern Samar | 303539 | Capacujan NHS | PALAPAG | 2 |  | 1 | [5 empty] | 1675760.29 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  | BEFF2018-B1-E-NS-L6 | BEFF2018-B1-E-NS-L6 | June 6, 2023 | June 14, 2023 | June 28, 2018 | 2018-07-25 |  | MAGA Construction & Supply | 1408308.9477 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Northern Samar | 313609 | Cabatuan NHS | PALAPAG | 2 |  | 1 | [5 empty] | 954013.8 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  | BEFF2018-B1-E-NS-L6 | BEFF2018-B1-E-NS-L6 | June 6, 2024 | June 14, 2024 | June 28, 2018 | 2018-07-25 |  | MAGA Construction & Supply | 801753.1975 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Northern Samar | 313621 | Zoilo T. Lobos Memorial High School | PAMBUJAN | 2 |  | 1 | [5 empty] | 1393081.21 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  | BEFF2018-B1-E-NS-L7 | BEFF2018-B1-E-NS-L7 | June 6, 2025 | June 14, 2025 | June 28, 2018 | 2018-07-25 | 2018-08-10 | SMU Construction & Supplies | 1220283.63 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Northern Samar | 313618 | Balnasan National High School | SAN ROQUE | 2 |  | 1 | [5 empty] | 1577033.76 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  | BEFF2018-B1-E-NS-L8 | BEFF2018-B1-E-NS-L8 | June 6, 2026 | June 14, 2026 | June 28, 2018 | 2018-07-25 | 2018-08-10 | SMU Construction & Supplies | 1381476.98 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 303654 | Dolores National High School | ORMOC CITY | 4 |  | 1 | [5 empty] | 3007642.38 | UPGRADING | 1 | COMPLETED | 100% | 100% | Aug. 19 |  | 2018-beff-e-b1-c5 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | JB BautistaEnterprises | 2957771.42 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 303655 | Ipil National High School | ORMOC CITY | 4 |  | 1 | [5 empty] | 2515883.21 | UPGRADING | 1 | COMPLETED | 100% | 100% | Aug. 19 |  | 2018-beff-e-b1-c6 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | JRM Construction & Supply | 2462794.19 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 303656 | Linao National High School | ORMOC CITY | 4 |  | 1 | [5 empty] | 3128532.52 | UPGRADING | 1 | COMPLETED | 100% | 100% | Aug. 19 |  | 2018-beff-e-b1-c4 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Melgazo construction & Supply | 3081891.71 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 303657 | Margen National High School | ORMOC CITY | 4 |  | 1 | [5 empty] | 2153212.81 | UPGRADING | 1 | COMPLETED | 100% | 100% | Aug. 19 |  | 2018-beff-e-b1-c9 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Vhits. D.G. Builders Enterprises | 2121357.24 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 303658 | New Ormoc City National High School | ORMOC CITY | 4 |  | 1 | [5 empty] | 3781284.86 | UPGRADING | 1 | COMPLETED | 100% | 100% | Aug. 19 |  | 2018-beff-e-b1-c1 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | QCC Consuction & Supply | 3728200.82 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 303660 | Rustico Capahi Sr. Memorial National High School | ORMOC CITY | 4 |  | 1 | [5 empty] | 2017943.15 | UPGRADING | 1 | COMPLETED | 100% | 100% | Aug. 19 |  | 2018-beff-e-b1-c11 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | HD Golden Buliders & Supply Inc. | 1958299.41 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 303661 | Genero B. Lureñana National High School | ORMOC CITY | 4 |  | 1 | [5 empty] | 3292258.37 | UPGRADING | 1 | COMPLETED | 100% | 100% | Aug. 19 |  | 2018-beff-e-b1-c3 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | silverscket Enterprises | 3200462.84 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 303662 | Valencia National High School | ORMOC CITY | 4 |  | 1 | [5 empty] | 3293173.99 | UPGRADING | 1 | COMPLETED | 100% | 100% | Aug. 19 |  | 2018-beff-e-b1-c2 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Vhits D.G. Builders Enterprise | 3254055.18 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 313901 | Lilo-an National High School | ORMOC CITY | 4 |  | 1 | [5 empty] | 2032322.68 | UPGRADING | 1 | COMPLETED | 100% | 100% | Aug. 19 |  | 2018-beff-e-b1-c10 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Tom bUilders & supply | 1947137.8 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 313902 | Pedro G. Bañez National High School | ORMOC CITY | 4 |  | 1 | [5 empty] | 1551618.51 | UPGRADING | 1 | COMPLETED | 100% | 100% | Aug. 19 |  | 2018-beff-e-b1-c13 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Bench Construction & Supply | 1476661.27 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 313903 | Cabintan National High School | ORMOC CITY | 4 |  | 1 | [5 empty] | 1654412.29 | UPGRADING | 1 | COMPLETED | 100% | 100% | Aug. 19 |  | 2018-beff-e-b1-c12 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | V.JYN Enterprises | 1620629.31 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 313904 | Matica-a National High School | ORMOC CITY | 4 |  | 1 | [5 empty] | 2381911.9 | UPGRADING | 1 | COMPLETED | 100% | 100% | Aug. 19 |  | 2018-beff-e-b1-c7 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Melgazo construction & Supply | 1799816.48 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 313906 | Julian C. Gantuangco NHS | ORMOC CITY | 4 |  | 1 | [5 empty] | 1440097.15 | UPGRADING | 1 | COMPLETED | 100% | 100% | Aug. 19 |  | 2018-beff-e-b1-c14 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | JFR COnstrUction | 1410802.45 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 330523 | Ormoc City Senior High School | ORMOC CITY | 4 |  | 1 | [5 empty] | 2158792.3 | UPGRADING | 1 | COMPLETED | 100% | 100% | Aug. 19 |  | 2018-beff-e-b1-c8 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Vhits. D.G. Builders Enterprises | 2126853.5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Samar (Western Samar) | 123509 | Gandara I CS | GANDARA | 1 |  | 1 | [5 empty] | 3200049.06 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-10-11 |  | CY2018BEFF-ELB1-L1 | CY2018BEFF-ELB1-L1 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | ROS Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Samar (Western Samar) | 313727 | Mabini NHS | BASEY | 2 |  | 1 | [5 empty] | 1271594.45 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-10-11 |  | CY2018BEFF-ELB1-L2 | CY2018BEFF-ELB1-L2 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Samar (Western Samar) | 303597 | CALBIGA NATIONAL HIGH SCHOOL | CALBIGA | 2 |  | 1 | [5 empty] | 2166391.77 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-10-11 |  | CY2018BEFF-ELB1-L3 | CY2018BEFF-ELB1-L3 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | Maga Construction | 2140444.93 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Samar (Western Samar) | 303601 | Daram NHS | DARAM | 2 |  | 1 | [5 empty] | 1531224.89 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | COMPLETED | 100% | 100% | 2018-10-11 |  | CY2018BEFF-ELB1-L4 | CY2018BEFF-ELB1-L4 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | Maga Construction | 1513553.01 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Samar (Western Samar) | 313719 | Bagacay NHS-Daram NHS Annex | DARAM | 2 |  | 1 | [5 empty] | 1725508.53 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-10-04 |  | CY2018BEFF-ELB1-L5 | CY2018BEFF-ELB1-L5 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Maga Construction | 1710108.44 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Samar (Western Samar) | 313710 | Malino National High School | JIABONG | 2 |  | 1 | [5 empty] | 965109.08 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-10-04 |  | CY2018BEFF-ELB1-L6 | CY2018BEFF-ELB1-L6 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Tubigan Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Samar (Western Samar) | 303611 | Marabut NHS | MARABUT | 2 |  | 1 | [5 empty] | 526801.85 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | COMPLETED | 100% | 100% | 2018-10-11 |  | CY2018BEFF-ELB1-L2 | CY2018BEFF-ELB1-L2 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Samar (Western Samar) | 303596 | Calapi NHS | MOTIONG | 2 |  | 1 | [5 empty] | 1723736.2 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-10-04 |  | CY2018BEFF-ELB1-L8 | CY2018BEFF-ELB1-L8 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Maga Construction | 1713315.58 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Samar (Western Samar) | 303641 | Wright NHS | PARANAS (WRIGHT) | 2 |  | 1 | [5 empty] | 793826.39 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | COMPLETED | 100% | 100% | 2018-10-04 |  | CY2018BEFF-ELB1-L7 | CY2018BEFF-ELB1-L7 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Samar (Western Samar) | 313718 | Primitivo T. Torrechiva National High School | VILLAREAL | 2 |  | 1 | [5 empty] | 467199.47 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-10-04 |  | CY2018BEFF-ELB1-L7 | CY2018BEFF-ELB1-L7 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Samar (Western Samar) | 313721 | San Isidro NHS | ZUMARRAGA | 2 |  | 1 | [5 empty] | 504571.49 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-10-04 |  | CY2018BEFF-ELB1-L6 | CY2018BEFF-ELB1-L6 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Tubigan Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Tacloban City | 303663 | Leyte NHS | TACLOBAN CITY (Capital) | 1 |  | 1 | [5 empty] | 3268867.99 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-07-23 |  | CY 2018_BEFF ELECTRIFICATION-Batch 1 | CY 2018_BEFF ELECTRIFICATION-Batch 1 | 2018-04-19 | 2018-04-26 | 2018-05-08 | 2018-05-15 | 2018-05-17 | JELM CONSTRUCTION | 3232604.53 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Bukidnon | 303968 | Libona NHS | LIBONA | 1 |  | 1 | [5 empty] | 421084.28 | UPGRADING | 1 | Ongoing | 10% | 85% | 2018-11-12 |  | 07-2018 | 28-2018 |  | 2018-08-08 | 2018-08-20 |  | 2018-09-10 | Digos Constrak Corporation | 334843.13 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Bukidnon | 314901 | Dalirig NHS | MANOLO FORTICH | 1 |  | 1 | [5 empty] | 591286.35 | UPGRADING | 1 | Ongoing | 20% | 80% | 2018-10-28 |  | 07-2018 | 29-2018 |  | 2018-08-08 | 2018-08-20 |  | 2018-09-10 | Digos Constrak Corporation | 588344.62 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Bukidnon | 314903 | San Vicente NHS | SUMILAO | 1 |  | 1 | [5 empty] | 318600.41 | UPGRADING | 1 | Ongoing | 20% | 80% | 2018-11-12 |  | 07-2018 | 30-2018 |  | 2018-08-08 | 2018-08-20 |  | 2018-09-10 | Digos Constrak Corporation | 285324.63 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Bukidnon | 303987 | Talakag NHS | TALAKAG | 1 |  | 1 | [5 empty] | 946827.8 | UPGRADING | 1 | Ongoing | 12% | 85% | 2018-10-28 |  | 07-2018 | 31-2018 |  | 2018-08-08 | 2018-08-20 |  | 2018-09-10 | Digos Constrak Corporation | 753354.56 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Bukidnon | 314908 | Cabulohan-Paradise NHS - Townsite Annex | CABANGLASAN | 2 |  | 1 | [5 empty] | 624418.88 | UPGRADING | 1 | Ongoing | 20% | 50% | 2018-10-28 |  | 07-2018 | 32-2018 |  | 2018-08-08 | 2018-08-20 |  | 2018-09-10 | Digos Constrak Corporation | 558710.14 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Bukidnon |  | Lantapan Stand-Alone SHS | LANTAPAN | 2 |  | 1 | [5 empty] | 1811677.5 | UPGRADING | 1 | Ongoing | 20% | 80% | 2018-12-12 |  | 07-2018 | 33-2018 |  | 2018-08-08 | 2018-08-20 |  | 2018-09-10 | Digos Constrak Corporation | 1622321.51 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Bukidnon | 314907 | Halapitan NHS - Little Baguio Annex | SAN FERNANDO | 2 |  | 1 | [5 empty] | 564410.03 | UPGRADING | 1 | Ongoing | 20% | 70% | 2018-12-12 |  | 07-2018 | 34-2018 |  | 2018-08-08 | 2018-08-20 |  | 2018-09-10 | Digos Constrak Corporation | 504908.55 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Cagayan de Oro City | 304108 | Bulua NHS | CAGAYAN DE ORO CITY (Capital) | 1 |  | 1 | [5 empty] | 1012007.31 | UPGRADING | 1 | Ongoing | 67% | 83% |  |  |  | 208-011 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. | 989436.07 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Cagayan de Oro City | 315403 | Cagayan de Oro NHS - Balulang Annex | CAGAYAN DE ORO CITY (Capital) | 1 |  | 1 | [5 empty] | 3465288.73 | UPGRADING | 1 | Ongoing | 94% | 99% |  |  |  | 208-012 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. | 3379251.62 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Cagayan de Oro City | 304104 | Agusan National High School | CAGAYAN DE ORO CITY (Capital) | 2 |  | 1 | [5 empty] | 4433497.52 | UPGRADING | 1 | Ongoing | 91% | 91% |  |  |  | 208-013 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. | 4323276.69 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Cagayan de Oro City | 304115 | Gusa NHS-Cugman Annex | CAGAYAN DE ORO CITY (Capital) | 2 |  | 1 | [5 empty] | 1642134.89 | UPGRADING | 1 | Ongoing | 82% | 99% |  |  |  | 208-011 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. | 1601120.29 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Cagayan de Oro City | 304118 | Lapasan National High School | CAGAYAN DE ORO CITY (Capital) | 2 |  | 1 | [5 empty] | 1550067.26 | UPGRADING | 1 | Ongoing | 76% | 99% |  |  |  | 208-011 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. | 1511066.11 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Cagayan de Oro City | 315401 | Balubal NHS | CAGAYAN DE ORO CITY (Capital) | 2 |  | 1 | [5 empty] | 3049898.1 | UPGRADING | 1 | Ongoing | 85% | 86% |  |  |  | 208-014 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. | 2973777.69 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Camiguin | 303989 | Bonbon NHS | CATARMAN | 0 |  | 1 | [5 empty] | 1419115.71 | UPGRADING | 1 | Ongoing | 65% | 95% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Camiguin | 303990 | Camiguin NHS | CATARMAN | 0 |  | 1 | [5 empty] | 8681319.02 | UPGRADING | 1 | Ongoing | 85% | 95% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Camiguin | 303992 | Lawigan-Bura National High School | CATARMAN | 0 |  | 1 | [5 empty] | 2682276.05 | UPGRADING | 1 | Ongoing | 80% | 95% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Camiguin | 303991 | Guinsiliban National High School | GUINSILIBAN | 0 |  | 1 | [5 empty] | 3019910.32 | UPGRADING | 1 | Ongoing | 55% | 60% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Camiguin | 315001 | Maac National High School | GUINSILIBAN | 0 |  | 1 | [5 empty] | 4812666.4 | UPGRADING | 1 | Ongoing | 45% | 50% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Camiguin | 303993 | SIXTO A. ABAO NHS | MAHINOG | 0 |  | 1 | [5 empty] | 6434149.04 | UPGRADING | 1 | Ongoing | 70% | 95% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Camiguin | 303994 | Mambajao NHS | MAMBAJAO (Capital) | 0 |  | 1 | [5 empty] | 13653985.18 | UPGRADING | 1 | Ongoing | 85% | 95% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Camiguin | 303996 | Tupsan NHS | MAMBAJAO (Capital) | 0 |  | 1 | [5 empty] | 2773140.02 | UPGRADING | 1 | Ongoing | 60% | 95% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Camiguin | 303997 | Yumbing National High School | MAMBAJAO (Capital) | 0 |  | 1 | [5 empty] | 5469760.43 | UPGRADING | 1 | Ongoing | 60% | 95% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Camiguin | 303995 | Eulalio U. Pabillore National High Sschool | SAGAY | 0 |  | 1 | [5 empty] | 4193168.3 | UPGRADING | 1 | Ongoing | 20% | 40% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | El Salvador | 315305 | Molugan NHS | CITY OF EL SALVADOR | 2 |  | 1 | [5 empty] | 2639714.7 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-11-05 |  |  | 2018-04-0087 | 2018-04-28 | 2018-05-15 | 2018-05-05 | 2018-06-20 | 2018-06-28 | JOASH AR ENG'G | 2612299.53 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Malaybalay City | 303946 | Bangcud NHS | CITY MALAYBALAY (Capital) | 2 |  | 1 | [5 empty] | 3156028.23 | UPGRADING | 1 | Ongoing | 30% | 30% |  |  |  |  | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | MEGABLUE KONSTRAK CORPORATION | 3156028.23 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Malaybalay City | 303950 | Bukidnon NHS | CITY MALAYBALAY (Capital) | 2 |  | 1 | [5 empty] | 3467155.4 | UPGRADING | 1 | Ongoing | 30% | 30% |  |  |  |  | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | MEGABLUE KONSTRAK CORPORATION | 3467155.4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Malaybalay City | 314914 | Casisang NHS | CITY MALAYBALAY (Capital) | 2 |  | 1 | [5 empty] | 469166.48 | UPGRADING | 1 | Ongoing | 30% | 30% |  |  |  |  | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | MEGABLUE KONSTRAK CORPORATION | 469166.48 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Malaybalay City | 314905 | Silae NHS - Annex St. Peter | CITY MALAYBALAY (Capital) | 2 |  | 1 | [5 empty] | 355302.54 | UPGRADING | 1 | Ongoing | 30% | 50% |  |  |  |  | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | DIGOS CONSTRAK CORPORATION | 355302.54 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Malaybalay City | 303973 | Managok NHS | CITY MALAYBALAY (Capital) | 2 |  | 1 | [5 empty] | 3568524.3986 | UPGRADING | 1 | Ongoing | 30% | 50% |  |  |  |  | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | DIGOS CONSTRAK CORPORATION | 3568524.3986 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Malaybalay City | 314920 | Managok NHS - Miglamin Annex | CITY MALAYBALAY (Capital) | 2 |  | 1 | [5 empty] | 314861.94 | UPGRADING | 1 | Ongoing | 30% | 50% |  |  |  |  | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | DIGOS CONSTRAK CORPORATION | 314861.94 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Malaybalay City | 325505 | Apo Macote NHS | CITY MALAYBALAY (Capital) | 2 |  | 1 | [5 empty] | 395210.89 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | Ongoing | 30% | 30% |  |  |  |  | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | MEGABLUE KONSTRAK CORPORATION | 395210.89 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Malaybalay City | 500245 | Can-ayan IS | CITY MALAYBALAY (Capital) | 2 |  | 1 | [5 empty] | 473176.9 | UPGRADING | 1 | Ongoing | 30% | 30% |  |  |  |  | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | MEGABLUE KONSTRAK CORPORATION | 473176.9 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Misamis Oriental | 304077 | Kinoguitan NAHS | KINOGUITAN | 1 |  | 1 | [5 empty] | 5246873.25 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King | 481205.07 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Misamis Oriental | 304089 | Medina NCHS | MEDINA | 1 |  | 1 | [5 empty] | 5813168.42 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  |  |  | 2018-06-25 | 2018-07-03 | 2018-07-17 |  | 2018-09-10 | Meter King | 5007063.86 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Misamis Oriental | 304096 | Salay NHS | SALAY | 1 |  | 1 | [5 empty] | 5713806 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King | 5174548.22 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Misamis Oriental | 304093 | Talisayan NHS | TALISAYAN | 1 |  | 1 | [5 empty] | 5439018.9 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  |  |  | 2018-06-25 | 2018-07-03 | 2018-07-17 |  | 2018-09-10 | Meter King | 4726011.85 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Misamis Oriental | 304073 | Jasaan NHS | JASAAN | 2 |  | 1 | [5 empty] | 5740187.25 | UPGRADING | 1 | COMPLETED | 80% | 100% |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King | 5314879.97 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Misamis Oriental | 315307 | Manticao NHS | MANTICAO | 2 |  | 1 | [5 empty] | 2269686.96 | UPGRADING | 1 | COMPLETED | 95% | 100% |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King | 2014354.88 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Misamis Oriental | 315303 | Naawan NHS | NAAWAN | 2 |  | 1 | [5 empty] | 2304636.87 | UPGRADING | 1 | COMPLETED | 95% | 100% |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King | 2035580.88 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Misamis Oriental | 341230 | Naawan SHS (Maputi ES Campus) | NAAWAN | 2 |  | 1 | [5 empty] | 2219343.3 | UPGRADING | 1 | COMPLETED | 95% | 100% |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King | 1957650.56 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Misamis Oriental | 304102 | Tagoloan NHS | TAGOLOAN | 2 |  | 1 | [5 empty] | 4013228.99 | UPGRADING | 1 | COMPLETED | 100% | 100% |  |  |  |  | 2018-06-25 | 2018-07-03 | 2018-07-17 |  | 2018-09-06 | Meter King | 3571331.04 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Oroquieta City | 304045 | Misamis Occidental NHS | OROQUIETA CITY (Capital) | 1 |  | 1 | [5 empty] | 4830487.89 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-10-18 |  | n/a | n/a | 2018-02-28 | 2018-03-08 | 2018-03-20 | 2018-04-12 | 2018-05-21 | J.C DELA VEGA CONSTRUCTION AND SUPPLY | 4804355.61 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | noa | Y
Region X | Oroquieta City | 304057 | Talairon NHS | OROQUIETA CITY (Capital) | 1 |  | 1 | [5 empty] | 2770270.4 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-09-18 |  | n/a | n/a | 2018-02-28 | 2018-03-08 | 2018-03-20 | 2018-04-12 | 2018-05-21 | J.C DELA VEGA CONSTRUCTION AND SUPPLY | 2754387.96 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | noa | Y
Region XI | Compostela Valley | 304183 | San Miguel NHS | COMPOSTELA | 1 |  | 1 | [5 empty] | 1536512.2 | UPGRADING | 1 | Ongoing | 99% | 99% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 304187 | Gabi NHS | COMPOSTELA | 1 |  | 1 | [5 empty] | 2215840.5 | UPGRADING | 1 | COMPLETED | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Compostela Valley | 304196 | Maparat NHS | COMPOSTELA | 1 |  | 1 | [5 empty] | 1842092.83 | UPGRADING | 1 | Ongoing | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 304210 | Siocon NHS | COMPOSTELA | 1 |  | 1 | [5 empty] | 1982927.43 | UPGRADING | 1 | COMPLETED | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Compostela Valley | 315819 | Bango NHS | COMPOSTELA | 1 |  | 1 | [5 empty] | 1577775.19 | UPGRADING | 1 | Ongoing | 85% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 304198 | Maragusan NHS | MARAGUSAN (SAN MARIANO) | 1 |  | 1 | [5 empty] | 2216542.6 | UPGRADING | 1 | Ongoing | 85% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 304213 | Tupaz NHS | MARAGUSAN (SAN MARIANO) | 1 |  | 1 | [5 empty] | 2049802.28 | UPGRADING | 1 | Ongoing | 85% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 304200 | Awao NHS | MONKAYO | 1 |  | 1 | [5 empty] | 1590494.75 | UPGRADING | 1 | Ongoing | 85% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 304202 | Montevista NHS | MONTEVISTA | 1 |  | 1 | [5 empty] | 2256983.26 | UPGRADING | 1 | Ongoing | 85% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 304206 | New Bataan NHS | NEW BATAAN | 1 |  | 1 | [5 empty] | 3230614.47 | UPGRADING | 1 | Ongoing | 85% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 304185 | Don Vicente Romualdez NHS | LAAK (SAN VICENTE) | 2 |  | 1 | [5 empty] | 1815283.9 | UPGRADING | 1 | Ongoing | 85% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 315812 | San Antonio NHS | LAAK (SAN VICENTE) | 2 |  | 1 | [5 empty] | 1611721.23 | UPGRADING | 1 | Ongoing | 85% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 304192 | Mabini NHS | MABINI (DOÑA ALICIA) | 2 |  | 1 | [5 empty] | 1967172.3 | UPGRADING | 1 | Ongoing | 90% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 315805 | Pindasan NHS | MABINI (DOÑA ALICIA) | 2 |  | 1 | [5 empty] | 1973452.43 | UPGRADING | 1 | Ongoing | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 304193 | Atty. Orlando S. Rimando National High School | MACO | 2 |  | 1 | [5 empty] | 2108048.83 | UPGRADING | 1 | Ongoing | 80% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 304194 | Mainit NHS | NABUNTURAN (Capital) | 2 |  | 1 | [5 empty] | 1527258.38 | UPGRADING | 1 | Ongoing | 85% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 304195 | Manat NHS | NABUNTURAN (Capital) | 2 |  | 1 | [5 empty] | 1584788.55 | UPGRADING | 1 | Ongoing | 85% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 315818 | New Sibonga NHS | NABUNTURAN (Capital) | 2 |  | 1 | [5 empty] | 1656335.98 | UPGRADING | 1 | Ongoing | 85% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 304179 | Bongabong NHS | PANTUKAN | 2 |  | 1 | [5 empty] | 1646320.97 | UPGRADING | 1 | Ongoing | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 304208 | Pantukan NHS | PANTUKAN | 2 |  | 1 | [5 empty] | 2390105.78 | UPGRADING | 1 | Ongoing | 80% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 304211 | Tambongon NHS | PANTUKAN | 2 |  | 1 | [5 empty] | 1647295.44 | UPGRADING | 1 | Ongoing | 98% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 315807 | Magnaga NHS | PANTUKAN | 2 |  | 1 | [5 empty] | 1444563.04 | UPGRADING | 1 | Ongoing | 85% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 315816 | Napnapan NHS | PANTUKAN | 2 |  | 1 | [5 empty] | 1739949.59 | UPGRADING | 1 | Ongoing | 85% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Davao del Norte | 304217 | Asuncion National High School | ASUNCION (SAUG) | 1 |  | 1 | [5 empty] | 4595542.1 | UPGRADING | 1 | COMPLETED | 98% | 100% | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction | 4565466.8962 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao del Norte | 304233 | Kapalong National High School | KAPALONG | 1 |  | 1 | [5 empty] | 7579333.47 | UPGRADING | 1 | COMPLETED | 98% | 100% | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction | 7535212.4937 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao del Norte | 304243 | Semong NHS | KAPALONG | 1 |  | 1 | [5 empty] | 2515559.99 | UPGRADING | 1 | COMPLETED | 98% | 100% | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction | 2495918.5425 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao del Norte | 304239 | Limbaan NHS | NEW CORELLA | 1 |  | 1 | [5 empty] | 2198146.77 | UPGRADING | 1 | COMPLETED | 98% | 100% | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction | 2179840.7665 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao del Norte | 304248 | New Corella NHS | NEW CORELLA | 1 |  | 1 | [5 empty] | 7374066.58 | UPGRADING | 1 | COMPLETED | 98% | 100% | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction | 7330665.0978 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao del Norte | 304240 | Linao NHS | SAN ISIDRO | 1 |  | 1 | [5 empty] | 2119197.91 | UPGRADING | 1 | COMPLETED | 98% | 100% | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction | 2101855.5785 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao del Sur | 304286 | Marber NHS | BANSALAN | 1 |  | 1 | [5 empty] | 1637941.03 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-12-03 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-31 | NLC Construction and Supplies | 1596873.83 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao del Sur | 304275 | Hagonoy NHS | HAGONOY | 1 |  | 1 | [5 empty] | 1776384.43 | UPGRADING | 1 | COMPLETED | 90% | 100% | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction | 1739801.33 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao del Sur | 304288 | Matanao National High School | MATANAO | 1 |  | 1 | [5 empty] | 3208710.59 | UPGRADING | 1 | Ongoing | 90% | 95% | 2018-11-28 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-08-02 | Optimun Equipment Management & Exchange Inc. | 2958144.97 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Davao del Sur | 304289 | Bangkal NHS | MATANAO | 1 |  | 1 | [5 empty] | 1438008.41 | UPGRADING | 1 | Ongoing | 90% | 95% | 2018-11-28 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-08-02 | Optimun Equipment Management & Exchange Inc. | 1541904.44 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Davao del Sur | 316003 | SALUD CAGAS TECH.& VOC. H.S | MATANAO | 1 |  | 1 | [5 empty] | 1525198.43 | UPGRADING | 1 | Ongoing | 90% | 95% | 2018-11-28 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-08-02 | Optimun Equipment Management & Exchange Inc. | 1578855.9 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Davao del Sur | 316002 | Padada NHS | PADADA | 1 |  | 1 | [5 empty] | 1528067.29 | UPGRADING | 1 | COMPLETED | 90% | 100% | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction | 1518730.69 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao del Sur | 304294 | Sta. Cruz National High School | SANTA CRUZ | 1 |  | 1 | [5 empty] | 1931198.96 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-12-03 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-31 | NLC Construction and Supplies | 1916291.38 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao del Sur | 304295 | Bato NHS | SANTA CRUZ | 1 |  | 1 | [5 empty] | 1636984.63 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-12-03 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-31 | NLC Construction and Supplies | 1617487.41 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao del Sur | 304274 | Gov. N. Llanos NHS | KIBLAWAN | 1 |  | 1 | [5 empty] | 1258038.7 | UPGRADING | 1 | COMPLETED | 90% | 100% | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction | 1250520.38 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao del Sur | 304277 | Ihan NHS | KIBLAWAN | 1 |  | 1 | [5 empty] | 1059283.01 | UPGRADING | 1 | COMPLETED | 90% | 100% | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction | 1052188.73 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao del Sur | 316001 | Molopolo National High School | KIBLAWAN | 1 |  | 1 | [5 empty] | 1689841.2 | UPGRADING | 1 | COMPLETED | 95% | 100% | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction | 1679718.85 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao del Sur | 304270 | Davao Del Sur SOF | MALALAG | 1 |  | 1 | [5 empty] | 1532696.52 | UPGRADING | 1 | COMPLETED | 90% | 100% | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction | 1523160.17 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao del Sur | 304297 | Sulop NHS | SULOP | 1 |  | 1 | [5 empty] | 1673254.53 | UPGRADING | 1 | COMPLETED | 90% | 100% | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction | 1663115.64 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao del Sur | 316005 | Felipe-Inocencia Deluao NHS | SULOP | 1 |  | 1 | [5 empty] | 1415134.64 | UPGRADING | 1 | COMPLETED | 100% | 100% | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction | 1405605.54 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao Occidental | 304272 | Don Marcelino NHS | DON MARCELINO | 0 |  | 1 | [5 empty] | 1196696.01 | UPGRADING | 1 | Ongoing | 77% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Davao Occidental | 304291 | Lawa NHS | DON MARCELINO | 0 |  | 1 | [5 empty] | 1369552.62 | UPGRADING | 1 | Ongoing | 77% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Davao Occidental | 304264 | Balangonan NHS | JOSE ABAD SANTOS (TRINIDAD) | 0 |  | 1 | [5 empty] | 1247574.58 | UPGRADING | 1 | Ongoing | 70% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Davao Occidental | 304273 | Edna Guillermo MHS | JOSE ABAD SANTOS (TRINIDAD) | 0 |  | 1 | [5 empty] | 1407917.46 | UPGRADING | 1 | Ongoing | 70% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Davao Occidental | 304281 | Jose Abad Santos NHS | JOSE ABAD SANTOS (TRINIDAD) | 0 |  | 1 | [5 empty] | 1912853.84 | UPGRADING | 1 | Ongoing | 50% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Davao Occidental | 304283 | Kalbay NHS | JOSE ABAD SANTOS (TRINIDAD) | 0 |  | 1 | [5 empty] | 1461438.74 | UPGRADING | 1 | Ongoing | 70% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Davao Occidental | 304271 | Demolok Valley NHS | MALITA | 0 |  | 1 | [5 empty] | 1406972.92 | UPGRADING | 1 | Ongoing | 77% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Davao Occidental | 304287 | Mariano Peralta NHS | MALITA | 0 |  | 1 | [5 empty] | 1586869.34 | UPGRADING | 1 | Ongoing | 77% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Davao Occidental | 304266 | Basiawan NHS | SANTA MARIA | 0 |  | 1 | [5 empty] | 1403358.25 | UPGRADING | 1 | Ongoing | 20% | 60% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Davao Occidental | 304268 | Tubalan Comprehensive NHS | SANTA MARIA | 0 |  | 1 | [5 empty] | 1441567.12 | UPGRADING | 1 | Ongoing | 20% | 60% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Davao Occidental | 304276 | Heracleo Casco MNHS | SANTA MARIA | 0 |  | 1 | [5 empty] | 4916224.97 | UPGRADING | 1 | Ongoing | 20% | 60% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Island Garden City of Samal | 128598 | Angel Villarica CES | ISLAND GARDEN CITY OF SAMAL | 2 |  | 1 | [5 empty] | 2121738.8 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | rebid | Y |  | rebid
Region XI | Island Garden City of Samal | 128599 | Balet ES | ISLAND GARDEN CITY OF SAMAL | 2 |  | 1 | [5 empty] | 1586670.16 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | rebid | Y |  | rebid
Region XI | Island Garden City of Samal | 304216 | Anonang National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 1 | [5 empty] | 1720922.63 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Island Garden City of Samal | 304223 | Cogon NHS | ISLAND GARDEN CITY OF SAMAL | 2 |  | 1 | [5 empty] | 1278338.16 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | rebid | Y |  | rebid
Region XI | Island Garden City of Samal | 304236 | Kaputian National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 1 | [5 empty] | 1719112.37 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Island Garden City of Samal | 304245 | Mambago-B NHS | ISLAND GARDEN CITY OF SAMAL | 2 |  | 1 | [5 empty] | 1994248.56 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Island Garden City of Samal | 304247 | Matanos NHS | ISLAND GARDEN CITY OF SAMAL | 2 |  | 1 | [5 empty] | 1227424.98 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Island Garden City of Samal | 304259 | Tagbitan-Ag NHS | ISLAND GARDEN CITY OF SAMAL | 2 |  | 1 | [5 empty] | 1624588.6 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Island Garden City of Samal | 323402 | Del Monte National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 1 | [5 empty] | 1376220.48 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Island Garden City of Samal | 323403 | Nieves Villarica NHS | ISLAND GARDEN CITY OF SAMAL | 2 |  | 1 | [5 empty] | 1813766.35 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Island Garden City of Samal | 330002 | San Jose NHS | ISLAND GARDEN CITY OF SAMAL | 2 |  | 1 | [5 empty] | 1296202.48 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Island Garden City of Samal | 330003 | Bandera NHS | ISLAND GARDEN CITY OF SAMAL | 2 |  | 1 | [5 empty] | 1321344.21 | UPGRADING | 1 | under procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | rebid | Y |  | rebid
Region XI | Island Garden City of Samal | 330004 | Libertad NHS | ISLAND GARDEN CITY OF SAMAL | 2 |  | 1 | [5 empty] | 1653793.35 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XII | North Cotabato | 304412 | Alamada NHS | ALAMADA | 1 |  | 1 | [5 empty] | 2028571.9982 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | North Cotabato | 304413 | Aleosan NHS | ALEOSAN | 1 |  | 1 | [5 empty] | 2024350.9982 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | North Cotabato | 304461 | Libungan NHS | LIBUNGAN | 1 |  | 1 | [5 empty] | 2024562.0482 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | North Cotabato | 304432 | Dilangalen National High School | MIDSAYAP | 1 |  | 1 | [5 empty] | 2024878.6232 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | North Cotabato | 304493 | Pigcawayan National High School | PIGKAWAYAN | 1 |  | 1 | [5 empty] | 2028360.9482 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | North Cotabato | 304494 | Pikit NHS | PIKIT | 1 |  | 1 | [5 empty] | 2022240.4982 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | North Cotabato | 304415 | Antipas NHS | ANTIPAS | 2 |  | 1 | [5 empty] | 2029099.6232 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | North Cotabato | 304436 | Greenfield NHS | ARAKAN | 2 |  | 1 | [5 empty] | 2035958.7482 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | North Cotabato | 304463 | Magpet NHS | MAGPET | 2 |  | 1 | [5 empty] | 2022768.1232 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | North Cotabato | 304466 | Makilala NHS | MAKILALA | 2 |  | 1 | [5 empty] | 2021185.2482 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | North Cotabato | 304496 | Pres. Roxas National High School | PRESIDENT ROXAS | 2 |  | 1 | [5 empty] | 2023295.7482 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | North Cotabato | 304420 | Banisilan NHS | BANISILAN | 3 |  | 1 | [5 empty] | 2041234.9982 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | North Cotabato | 304427 | Carmen NHS | CARMEN | 3 |  | 1 | [5 empty] | 1992027.4212 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | North Cotabato | 304444 | Kabacan NHS | KABACAN | 3 |  | 1 | [5 empty] | 2020129.9982 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | North Cotabato | 304452 | Kibia HS | MATALAM | 3 |  | 1 | [5 empty] | 2024350.9982 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | North Cotabato | 304478 | Matalam NHS, Brgy Poblacion | MATALAM | 3 |  | 1 | [5 empty] | 2020129.9982 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | North Cotabato | 304480 | M'lang NHS | M'LANG | 3 |  | 1 | [5 empty] | 2021712.8732 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | North Cotabato | 304515 | Tulunan NHS | TULUNAN | 3 |  | 1 | [5 empty] | 2025406.2482 | UPGRADING | 1 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CAR | Apayao | 305108 | BAC-DA National High School | LUNA | 0 |  | 1 | [5 empty] | 952154.67 | UPGRADING | 2 | COMPLETED | 95% | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES | 922980.49 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Apayao | 318801 | Tumog National Agricultural and trade High School | LUNA | 0 |  | 1 | [5 empty] | 998955.38 | UPGRADING | 2 | COMPLETED | 95% | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES | 961612.22 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Apayao | 305118 | Mataguisi Comp. HS Main | PUDTOL | 0 |  | 1 | [5 empty] | 879844.34 | UPGRADING | 2 | COMPLETED | 95% | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES | 851601.82 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Baguio City | 305275 | Mil-an National High School | BAGUIO CITY | 0 |  | 1 | [5 empty] | 4892682 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Baguio City | 305278 | San Vicente National High School (Integrated Senior High School) | BAGUIO CITY | 0 |  | 1 | [5 empty] | 3894208.64 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Baguio City | 305279 | Sto. Tomas National High School | BAGUIO CITY | 0 |  | 1 | [5 empty] | 3283387.46 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Baguio City | 305280 | Irisan National High School | BAGUIO CITY | 0 |  | 1 | [5 empty] | 4182575.32 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Baguio City | 136382 | Baguio Central school | BAGUIO CITY | 0 |  | 1 | [5 empty] | 5037080.62 | UPGRADING | 2 | COMPLETED | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Baguio City | 136417 | SPED Center (FL) | BAGUIO CITY | 0 |  | 1 | [5 empty] | 3136655.76 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Baguio City | 136388 | Elpidio R. Quirino Elementary School | BAGUIO CITY | 0 |  | 1 | [5 empty] | 4795287.5 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Ifugao | 305173 | Haliap NHS | ASIPULO | 0 |  | 1 | [5 empty] | 2115765.21 | UPGRADING | 2 | completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Ifugao | 319001 | Bangbang National High School | HUNGDUAN | 0 |  | 1 | [5 empty] | 1968987.41 | UPGRADING | 2 | completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Ifugao | 305168 | Ayangan National Agricultural & Vocational HS | LAGAWE (Capital) | 0 |  | 1 | [5 empty] | 1619239.19 | UPGRADING | 2 | completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Ifugao | 305176 | Hapid NHS | LAMUT | 0 |  | 1 | [5 empty] | 1450065.49 | UPGRADING | 2 | completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Ifugao | 305181 | Ifugao Prov'l. Science HS | LAMUT | 0 |  | 1 | [5 empty] | 1676892.23 | UPGRADING | 2 | completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Ifugao | 305192 | Tinoc NHS | TINOC | 0 |  | 1 | [5 empty] | 1443313.95 | UPGRADING | 2 | completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Tabuk City | 305203 | Cudal National High School | CITY OF TABUK (Capital) | 0 |  | 1 | [5 empty] | 1566626.32 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Tabuk City | 319104 | Bado Dangwa National High School | CITY OF TABUK (Capital) | 0 |  | 1 | [5 empty] | 1737997.5 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Tabuk City | 305222 | New Tanglag National High School | CITY OF TABUK (Capital) | 0 |  | 1 | [5 empty] | 1321850.18 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CARAGA | Agusan del Norte | 304680 | Casiklan NHS- Durian NHS Annex | LAS NIEVES | 1 |  | 1 | [5 empty] | 908776.8783 | UPGRADING | 2 | completed | 90% | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Norte | 304689 | Las Nieves NHS | LAS NIEVES | 1 |  | 1 | [5 empty] | 1995482.4464 | UPGRADING | 2 | completed | 90% | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Norte | 304679 | Durian NHS | LAS NIEVES | 1 |  | 1 | [5 empty] | 1001800.817 | UPGRADING | 2 | completed | 90% | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Norte | 304694 | Marcos Calo NHS | LAS NIEVES | 1 |  | 1 | [5 empty] | 1000395.19 | UPGRADING | 2 | completed | 90% | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Norte | 304674 | Buenavista NHS | BUENAVISTA | 2 |  | 1 | [5 empty] | 1375813.6202 | UPGRADING | 2 | completed | 90% | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Norte | 304682 | Guinabsan NHS | BUENAVISTA | 2 |  | 1 | [5 empty] | 890124.6 | UPGRADING | 2 | completed | 90% | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Norte | 500049 | Manapa II Integrated School | BUENAVISTA | 2 |  | 1 | [5 empty] | 1485353.95 | UPGRADING | 2 | completed | 90% | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Norte | 317304 | Cahayagan NHS (Carmen NHS Annex) | CARMEN | 2 |  | 1 | [5 empty] | 722664.43 | UPGRADING | 2 | completed | 90% | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Norte | 304685 | Jabonga NHS | JABONGA | 2 |  | 1 | [5 empty] | 1264534.97 | UPGRADING | 2 | ongoing | 85% | 85% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
CARAGA | Agusan del Norte | 304688 | Kitcharao NHS | KITCHARAO | 2 |  | 1 | [5 empty] | 1511842.0007 | UPGRADING | 2 | ongoing | 70% | 70% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
CARAGA | Agusan del Norte | 304691 | Magallanes National High School | MAGALLANES | 2 |  | 1 | [5 empty] | 1352554.6445 | UPGRADING | 2 | completed | 90% | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Norte | 304696 | Nasipit National Vocational School | NASIPIT | 2 |  | 1 | [5 empty] | 1598975.7697 | UPGRADING | 2 | completed | 90% | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Norte | 317302 | Nasipit NHS | NASIPIT | 2 |  | 1 | [5 empty] | 781156.32 | UPGRADING | 2 | completed | 90% | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Norte | 304673 | Agay National High School | REMEDIOS T. ROMUALDEZ | 2 |  | 1 | [5 empty] | 1461966.2225 | UPGRADING | 2 | completed | 90% | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Norte | 304686 | Jagupit NHS | SANTIAGO | 2 |  | 1 | [5 empty] | 1422466.5055 | UPGRADING | 2 | ongoing | 70% | 70% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
CARAGA | Agusan del Norte | 304698 | Santiago NHS | SANTIAGO | 2 |  | 1 | [5 empty] | 1381089.87 | UPGRADING | 2 | ongoing | 70% | 70% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
CARAGA | Agusan del Norte | 317309 | Dona Rosario NHS - Tubay NHS Annex | TUBAY | 2 |  | 1 | [5 empty] | 1058491.7855 | UPGRADING | 2 | completed | 90% | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Norte | 304701 | Tubay NHS | TUBAY | 2 |  | 1 | [5 empty] | 1063694.0519 | UPGRADING | 2 | completed | 85% | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Sur | 304730 | Patin-ay National High School | PROSPERIDAD (Capital) | 1 |  | 1 | [5 empty] | 3637477.62 | UPGRADING | 2 | completed | 100% | 100% |  |  |  | 2018-09-012 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | RJB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Sur | 317428 | West Prosperidad Nhs | PROSPERIDAD (Capital) | 1 |  | 1 | [5 empty] | 2904296.75 | UPGRADING | 2 | completed | 100% | 100% |  |  |  | 2018-09-013 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | A-MARTINA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Sur | 304749 | Sta. Irene National High School | PROSPERIDAD (Capital) | 1 |  | 1 | [5 empty] | 5421042.52 | UPGRADING | 2 | completed | 100% | 100% |  |  |  | 2018-09-014 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | A-MARTINA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Sur | 304731 | Prosperidad NHS | PROSPERIDAD (Capital) | 1 |  | 1 | [5 empty] | 4255007.78 | UPGRADING | 2 | completed | 100% | 100% |  |  |  | 2018-09-015 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | A-MARTINA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Sur | 304709 | Bunawan National High School | BUNAWAN | 2 |  | 1 | [5 empty] | 4335897.39 | UPGRADING | 2 | completed | 100% | 100% |  |  |  | 2018-09-016 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | ARCLER BUILDERS & CONST. SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Sur | 304744 | Sta. Cruz NHS | ROSARIO | 2 |  | 1 | [5 empty] | 3571779.59 | UPGRADING | 2 | completed | 100% | 100% |  |  |  | 2018-09-017 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | ARCLER BUILDERS & CONST. SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Sur | 304745 | Bayugan III NHS | ROSARIO | 2 |  | 1 | [5 empty] | 3924975.51 | UPGRADING | 2 | completed | 100% | 100% |  |  |  | 2018-09-018 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | ARCLER BUILDERS & CONST. SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Agusan del Sur | 317402 | Bayugan II National High School | SAN FRANCISCO | 2 |  | 1 | [5 empty] | 2315300.82 | UPGRADING | 2 | completed | 100% | 100% |  |  |  | 2018-09-019 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | ARCLER BUILDERS & CONST. SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Bayugan City | 340297 | STAND ALONE SHS | CITY OF BAYUGAN | 1 |  | 1 | [5 empty] | 2716825.75 | UPGRADING | 2 | completed | 100% | 100% |  | February 8, 2019 |  | 2019-004 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Bayugan City | 304728 | Noli National High School | CITY OF BAYUGAN | 1 |  | 1 | [5 empty] | 1313237.32 | UPGRADING | 2 | completed | 100% | 100% |  | December 21, 2018 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Bayugan City | 304723 | Marcelina NHS | CITY OF BAYUGAN | 1 |  | 1 | [5 empty] | 1247694.45 | UPGRADING | 2 | completed | 100% | 100% |  | December 21, 2018 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Bislig City | 304865 | Bislig City NHS | CITY OF BISLIG | 2 |  | 1 | [5 empty] | 2627484.1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 2 | completed | 100% | 100% | Sept. 26, 2018 |  | 2018BEFF-Electrification-C1 | 2018BEFF-Electrification-C1 | 2018-03-23 | 2018-04-05 | 2018-04-17 | 2018-04-25 | May 23, 2018 | MAG Corporation | 2596626.53 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CARAGA | Bislig City | 304869 | Sikahoy NHS | CITY OF BISLIG | 2 |  | 1 | [5 empty] | 1144311.01 | ELECTRIFICATION OF SCHOOLS ON-GRID | 2 | completed | 100% | 100% | Aug. 27, 2018 |  | 2018BEFF-Electrification-C2 | 2018BEFF-Electrification-C2 | 2018-03-23 | 2018-04-05 | 2018-04-17 | 2018-04-25 | May 23, 2018 | MAG Corporation | 1130069.36 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CARAGA | Bislig City | 304919 | Mangagoy NHS | CITY OF BISLIG | 2 |  | 1 | [5 empty] | 1519924.76 | ELECTRIFICATION OF SCHOOLS ON-GRID | 2 | completed | 100% | 100% | Aug. 27, 2018 |  | 2018BEFF-Electrification-C2 | 2018BEFF-Electrification-C2 | 2018-03-23 | 2018-04-05 | 2018-04-17 | 2018-04-25 | May 23, 2018 | MAG Corporation | 1502002.64 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CARAGA | Bislig City | 340306 | Stand Alone SHS | CITY OF BISLIG | 2 |  | 1 | [5 empty] | 1438901.82 | ELECTRIFICATION OF SCHOOLS ON-GRID | 2 | completed | 100% | 100% | Sept. 26, 2018 |  | 2018BEFF-Electrification-C1 | 2018BEFF-Electrification-C1 | 2018-03-23 | 2018-04-05 | 2018-04-17 | 2018-04-25 | May 23, 2018 | MAG Corporation | 1422202.03 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CARAGA | Butuan City | 340337 | Butuan City Senior High School Stand Alone | BUTUAN CITY (Capital) | 1 |  | 1 | [5 empty] | 2762431.87 | UPGRADING | 2 | completed | 100% | 100% | December 15, 2018 |  | RRC-2018-006 | RRC-2018-006 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | july, 23, 2018 | ETP Builders | 1818553.25 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Butuan City | 304756 | Agusan National High School | BUTUAN CITY (Capital) | 1 |  | 1 | [5 empty] | 2221583.24 | UPGRADING | 2 | completed | 90% | 100% | December 15, 2018 |  | RRC-2018-006 | RRC-2018-006 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | july, 23, 2018 | ETP Builders | 1949719.39 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Butuan City | 304762 | Butuan City Sch. of Arts & Trades | BUTUAN CITY (Capital) | 1 |  | 1 | [5 empty] | 2205770.32 | UPGRADING | 2 | completed | 100% | 100% | December 15, 2018 |  | RRC-2018-007 | RRC-2018-007 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | July 6, 2018 | Two J.E. Construction & Supply | 1877249.5724 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Butuan City | 304763 | Libertad Integrated Senior High School | BUTUAN CITY (Capital) | 1 |  | 1 | [5 empty] | 1663800.35 | UPGRADING | 2 | completed | 100% | 100% | December 15, 2018 |  | RRC-2018-007 | RRC-2018-007 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | July 6, 2018 | Two J.E. Construction & Supply | 1414442.2064 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Butuan City | 304771 | Taligaman NHS | BUTUAN CITY (Capital) | 1 |  | 1 | [5 empty] | 1663800.35 | UPGRADING | 2 | completed | 100% | 100% | December 15, 2018 |  | RRC-2018-006 | RRC-2018-006 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | july, 23, 2018 | ETP Builders | 1652389.55 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Butuan City | 304769 | San Vicente National High School | BUTUAN CITY (Capital) | 1 |  | 1 | [5 empty] | 1663800.35 | UPGRADING | 2 | completed | 100% | 100% | December 15, 2018 |  | RRC-2018-007 | RRC-2018-007 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | July 6, 2018 | Two J.E. Construction & Supply | 1414442.2064 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Butuan City | 304757 | Agusan Pequeno NHS | BUTUAN CITY (Capital) | 1 |  | 1 | [5 empty] | 1663800.35 | UPGRADING | 2 | completed | 100% | 100% | December 15, 2018 |  | RRC-2018-007 | RRC-2018-007 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | July 6, 2018 | Two J.E. Construction & Supply | 1414442.2064 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Cabadbaran City | 304676 | Calamba NHS | CITY OF CABADBARAN | 2 |  | 1 | [5 empty] | 1117389.43 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Cabadbaran City | 340341 | La Union SHS (Stand Alone) | CITY OF CABADBARAN | 2 |  | 1 | [5 empty] | 1006220.12 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Siargao | 304784 | Roxas National High School | SAN ISIDRO | 1 |  | 1 | [5 empty] | 2109106.54 | UPGRADING | 2 | completed | 100% | 100% | 100% | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CARAGA | Surigao City | 304801 | Surigao City NHS | SURIGAO CITY (Capital) | 2 |  | 1 | [5 empty] | 2488304.96 | UPGRADING | 2 | awaiting for energization of Elec. Coop | 95% | 95% | 95% | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CARAGA | Surigao City | 304794 | Caraga Regional Science HS | SURIGAO CITY (Capital) | 2 |  | 1 | [5 empty] | 567310.44 | UPGRADING | 2 | awaiting for energization of Elec. Coop | 95% | 95% | 95% | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | For Award
CARAGA | Surigao City | 340383 | Cabrera-Altres National High School | SURIGAO CITY (Capital) | 2 |  | 1 | [5 empty] | 565967.91 | UPGRADING | 2 | awaiting for energization of Elec. Coop | 95% | 95% | 95% | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | (realigned to CARAGA Regional Science and Anomar NHS
CARAGA | Surigao City | 304800 | Anomar NHS | SURIGAO CITY (Capital) | 2 |  | 1 | [5 empty] | 568659.84 | UPGRADING | 2 | awaiting for energization of Elec. Coop | 95% | 95% | 95% | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | For Award
CARAGA | Surigao City | 304799 | mat-i national high school | SURIGAO CITY (Capital) | 2 |  | 1 | [5 empty] | 1356411.85 | UPGRADING | 2 | awaiting for energization of Elec. Coop | 95% | 95% | 95% | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CARAGA | Surigao del Sur | 304861 | Barobo National High School | BAROBO | 1 |  | 1 | [5 empty] | 1215833.39 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 304888 | Gamut National School (Barobo) | BAROBO | 1 |  | 1 | [5 empty] | 1132934.81 | UPGRADING | 2 | Completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 304895 | Lingig National High School | LINGIG | 1 |  | 1 | [5 empty] | 2040849.84 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 304862 | Cabacungan National High School | BAROBO | 2 |  | 1 | [5 empty] | 826611.18 | UPGRADING | 2 | Completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 304864 | Tambis National High School | BAROBO | 2 |  | 1 | [5 empty] | 1165346.88 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 317941 | Rizal National High School | BAROBO | 2 |  | 1 | [5 empty] | 989901.63 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 304890 | Hinatuan National Comprehensive High School | HINATUAN | 2 |  | 1 | [5 empty] | 1958192.28 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 304891 | Dugmanon National High School | HINATUAN | 2 |  | 1 | [5 empty] | 1285902.31 | UPGRADING | 2 | completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 304920 | Tagasaka National High School | HINATUAN | 2 |  | 1 | [5 empty] | 1018059.73 | UPGRADING | 2 | ongoing | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
CARAGA | Surigao del Sur | 304921 | Tagasaka NHS - Bigaan NHS Annex | HINATUAN | 2 |  | 1 | [5 empty] | 699350.11 | UPGRADING | 2 | completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 304923 | Tidman National High School | HINATUAN | 2 |  | 1 | [5 empty] | 1039113.16 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 317910 | Tagasaka NHS - Loyola NHS Annex | HINATUAN | 2 |  | 1 | [5 empty] | 1686150.22 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 500577 | Baculin Integrated School | HINATUAN | 2 |  | 1 | [5 empty] | 1230229.49 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 500579 | Tarusan Integrated School | HINATUAN | 2 |  | 1 | [5 empty] | 980049.41 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 317939 | Hinatuan NCHS - Roxas NHS Annex | HINATUAN | 2 |  | 1 | [5 empty] | 1076759.56 | UPGRADING | 2 | completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 317940 | Hinatuan NCHS - Cambatong NHS Annex | HINATUAN | 2 |  | 1 | [5 empty] | 2157380.51 | UPGRADING | 2 | completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 304860 | BARCELONA NATIONAL HIGH SCHOOL | LINGIG | 2 |  | 1 | [5 empty] | 1692675.85 | UPGRADING | 2 | completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 304896 | M.K.Yusingco National High School | LINGIG | 2 |  | 1 | [5 empty] | 1370222.68 | UPGRADING | 2 | completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 500581 | Anibongan Integrated School | LINGIG | 2 |  | 1 | [5 empty] | 634932.93 | UPGRADING | 2 | completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 500327 | Rajah Cabungsuan Integrated School | LINGIG | 2 |  | 1 | [5 empty] | 886819.09 | UPGRADING | 2 | completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 304879 | Dante Luib Osano Maputi National High School | TAGBINA | 2 |  | 1 | [5 empty] | 1426254.45 | UPGRADING | 2 | ongoing | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
CARAGA | Surigao del Sur | 304880 | Kahayagan National High School | TAGBINA | 2 |  | 1 | [5 empty] | 1167541.05 | UPGRADING | 2 | ongoing | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
CARAGA | Surigao del Sur | 304881 | Maglatab National High School | TAGBINA | 2 |  | 1 | [5 empty] | 1117283.12 | UPGRADING | 2 | ongoing | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
CARAGA | Surigao del Sur | 304883 | Sta. Juana National High School | TAGBINA | 2 |  | 1 | [5 empty] | 1162498.57 | UPGRADING | 2 | ongoing | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
CARAGA | Surigao del Sur | 500580 | Osmeña Integrated School | TAGBINA | 2 |  | 1 | [5 empty] | 1356777.94 | UPGRADING | 2 | ongoing | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
CARAGA | Surigao del Sur | 500582 | Malixi Integrated School | TAGBINA | 2 |  | 1 | [5 empty] | 1210039.51 | UPGRADING | 2 | ongoing | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
CARAGA | Surigao del Sur | 500583 | Quezon Integrated School | TAGBINA | 2 |  | 1 | [5 empty] | 1275561.55 | UPGRADING | 2 | completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 500584 | Sta. Maria Integrated School | TAGBINA | 2 |  | 1 | [5 empty] | 1295078.32 | UPGRADING | 2 | ongoing | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
CARAGA | Surigao del Sur | 500585 | Manambia Integrated School | TAGBINA | 2 |  | 1 | [5 empty] | 1130028.26 | UPGRADING | 2 | ongoing | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
CARAGA | Surigao del Sur | 500586 | Jobar Integrated School | TAGBINA | 2 |  | 1 | [5 empty] | 1034475.45 | UPGRADING | 2 | ongoing | 90% | 85% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
CARAGA | Surigao del Sur | 500324 | Maglambing Integrated School | TAGBINA | 2 |  | 1 | [5 empty] | 1136011.53 | UPGRADING | 2 | completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 500325 | Quary I Integrated School | TAGBINA | 2 |  | 1 | [5 empty] | 829362.43 | UPGRADING | 2 | completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Sur | 500326 | Carpenito Integrated School | TAGBINA | 2 |  | 1 | [5 empty] | 1162180.11 | UPGRADING | 2 | ongoing | 90% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
NCR | Caloocan City |  | Camarin Brixton Senior High School | KALOOKAN CITY |  |  | 1 | [5 empty] | 672163.77 | UPGRADING | 2 | completed | 50% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
NCR | Caloocan City |  | Sampaguita Senior High School | KALOOKAN CITY |  |  | 1 | [5 empty] | 743289.98 | UPGRADING | 2 | completed | 50% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
NCR | Caloocan City |  | Samaria Tala Senior High School | KALOOKAN CITY |  |  | 1 | [5 empty] | 754858.4 | UPGRADING | 2 | completed | 20% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
NCR | Las Piñas City | 136784 | Dona Manuela ES | CITY OF LAS PIÑAS | 0 |  | 1 | [5 empty] | 1947303.36 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
NCR | Malabon City | 305447 | Malabon NHS | CITY OF MALABON | 0 |  | 1 | [5 empty] | 4724091.14 | UPGRADING | 2 | completed | 70% | 100% | 2019-06-20 |  |  |  |  | 2018-11-07 | 2018-11-19 | 2018-12-03 | 2018-12-26 | MRRM Trading & Construction | 3665127.39 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG | 0 |  | 1 | [5 empty] | 4891117.15 | UPGRADING | 2 | completed | 95% | 100% | 2019-01-31 | 2019-01-31 | 2018-Mandauyong -19 | 2018-Mandauyong -19 | July 19, 2018-August 6, 2018 | 2018-07-26 | 2018-08-07 | 2018-08-10 | 2019-08-20 | New Rich General Contractor Services & Trading Co., Inc. | 3650087.43 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
NCR | Mandaluyong City | 500331 | Isaac Lopez Integrated School (Isaac Lopez ES) | CITY OF MANDALUYONG | 0 |  | 1 | [5 empty] | 3345858.02 | UPGRADING | 2 | completed | 95% | 100% |  |  | 2018-Mandauyong -19 | 2018-Mandauyong -19 | July 19, 2018-August 6, 2018 | 2018-07-26 | 2018-08-07 | 2018-08-10 | 2019-08-20 | New Rich General Contractor Services & Trading Co., Inc. | 2496908.97 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
NCR | Manila | 305308 | Valeriano E. Fugoso Memorial High School | SAMPALOC | 4 |  | 1 | [5 empty] | 3105124.57 | UPGRADING | 2 | ongoing | 30% | 70% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
NCR | Marikina City | 136682 | H. Bautista ES | CITY OF MARIKINA | 2 |  | 1 | [5 empty] | 591084.11 | UPGRADING | 2 | completed | 100% | 100% | June 16, 2018 | May 22, 2018 |  |  | March 22, 2018 |  | March 27, 2018 | March 27, 2018 | April 12, 2018 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
NCR | Marikina City | 500052 | Concepcion Integrated School | CITY OF MARIKINA | 2 |  | 1 | [5 empty] | 784512.82 | UPGRADING | 2 | completed | 100% | 100% | June 16, 2019 | May 22, 2019 |  |  | March 22, 2019 |  | March 27, 2019 | March 27, 2019 | April 12, 2019 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
NCR | Muntinlupa City | 320704 | Muntinlupa NHS -Tunasan Annex | CITY OF MUNTINLUPA | 0 |  | 1 | [5 empty] | 1192859.58 | UPGRADING | 2 | ongoing | 0% | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | procured | Y
NCR | Muntinlupa City | 136911 | Buli ES | CITY OF MUNTINLUPA | 0 |  | 1 | [5 empty] | 679397.49 | UPGRADING | 2 | completed | 85% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
NCR | Navotas | 305457 | Tangos National High School | CITY OF NAVOTAS | 0 |  | 1 | [5 empty] | 2194937.52 | UPGRADING | 2 | completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
NCR | Pasay City | 500328 | Philippine National School for the Blind | PASAY CITY | 0 |  | 1 | [5 empty] | 4774665.87 | UPGRADING | 2 | completed | 85% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
NCR | Taguig | 305466 | Pateros National High School | PATEROS | 1 |  | 1 | [5 empty] | 2165075.77 | UPGRADING | 2 | completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
NCR | Valenzuela City | 320404 | Bignay National High School | CITY OF VALENZUELA | 1 |  | 1 | [5 empty] | 2484345.88 | UPGRADING | 2 | ongoing | 20% | 70% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Alaminos City | 300155 | Alaminos City NHS | CITY OF ALAMINOS | 1 |  | 1 | [5 empty] | 2376416.44 | UPGRADING | 2 | completed | 100% | 100% | 2018-07-19 | 2018-07-19 |  |  | 2018-04-13 | 2018-04-19 | 2018-05-03 | 2018-05-10 | 2018-05-21 | ALCEL CONSTRUCTION | 2364155.76 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Batac City | 300005 | Batac National High School | Batac City | 2 |  | 1 | [5 empty] | 1305111.24 | UPGRADING | 2 | ongoing |  | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Suspended ( INEC Resurvey,Right of Way Concern) | Y
Region I | Batac City | 300012 | CRISPINA MARCOS VALDEZ NHS | Batac City | 2 |  | 1 | [5 empty] | 1305111.24 | UPGRADING | 2 | ongoing |  | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Suspended ( INEC Resurvey,Right of Way Concern) | Y
Region I | Dagupan City | 500054 | Federico N. Ceralde IS | DAGUPAN CITY | 4 |  | 1 | [5 empty] | 1136698.75 | UPGRADING | 2 | completed | 100% | 100% | 2018-09-25 | 2018-09-25 | [5 empty] | 2018-06-28 | 2018-07-06 |  | 1127180.5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Ilocos Norte | 300006 | Burgos Agro-Industrial School | BURGOS | 1 |  | 1 | 1 |  |  |  |  | 804898.5191 | UPGRADING | 2 | ongoing | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 787840.2812 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 300019 | Luzong NHS | PAGUDPUD | 1 |  | 1 | 1 |  |  |  |  | 650890.0578 | UPGRADING | 2 | ongoing | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 634920.9062 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 300024 | PAGUDPUD NHS | PAGUDPUD | 1 |  | 1 | 1 |  |  |  |  | 712493.4423 | UPGRADING | 2 | ongoing | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 695928.5312 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1 |  | 1 | 1 |  |  |  |  | 804898.5191 | UPGRADING | 2 | ongoing | 60% | 60% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 787840.2812 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 300029 | Sarrat National High School | SARRAT | 1 |  | 1 | 1 |  |  |  |  | 804898.5191 | UPGRADING | 2 | ongoing | 75% | 75% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 787039.6562 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 320816 | STA. ROSA NATIONAL HIGH SCHOOL | SARRAT | 1 |  | 1 | 1 |  |  |  |  | 681691.7501 | UPGRADING | 2 | ongoing | 75% | 75% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 665344.6562 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 500592 | Pandan IS | SARRAT | 1 |  | 1 | 1 |  |  |  |  | 650890.0578 | UPGRADING | 2 | ongoing | 50% | 50% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 634920.9062 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 320821 | ISIC-ISIC NATIONAL HIGH SCHOOL | VINTAR | 1 |  | 1 | 1 |  |  |  |  | 589286.6733 | UPGRADING | 2 | ongoing | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 573753.1562 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 500344 | SALPAD INTEGRATED SCHOOL | VINTAR | 1 |  | 1 | 1 |  |  |  |  | 620088.3656 | UPGRADING | 2 | ongoing | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 603536.4062 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 300002 | Bacarra NCHS | BACARRA | 2 |  | 1 | 1 |  |  |  |  | 881902.7497 | UPGRADING | 2 | ongoing | 75% | 75% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 864700.2812 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 300021 | Nagrebcan NHS | BADOC | 2 |  | 1 | 1 |  |  |  |  | 681691.7501 | UPGRADING | 2 | ongoing | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 665344.6562 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 500000 | Caraitan Integrated School | BADOC | 2 |  | 1 | 1 |  |  |  |  | 681691.7501 | UPGRADING | 2 | ongoing | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 665024.4062 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 300003 | Bangui NHS | BANGUI | 2 |  | 1 | 1 |  |  |  |  | 681691.7501 | UPGRADING | 2 | ongoing | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 665504.7812 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 300008 | Caestebanan NHS | BANNA (ESPIRITU) | 2 |  | 1 | 1 |  |  |  |  | 620088.3656 | UPGRADING | 2 | ongoing | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 604337.0312 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 300013 | Currimao NHS | CURRIMAO | 2 |  | 1 | 1 |  |  |  |  | 650890.0578 | UPGRADING | 2 | ongoing | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 634120.2812 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region I | Ilocos Norte | 320806 | Dingras NHS/Lt. Edgar Foz Mem. NHS (Barong Campus) | DINGRAS | 2 |  | 1 | 1 |  |  |  |  | 589286.6733 | UPGRADING | 2 | ongoing | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 573593.0312 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 320807 | San Marcelino National High School | DINGRAS | 2 |  | 1 | 1 |  |  |  |  | 620088.3656 | UPGRADING | 2 | ongoing | 60% | 60% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 604240.9563 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 320809 | Dingras NHS/Lt. Edgar Foz Mem. NHS- (Sulquiano Campus) | DINGRAS | 2 |  | 1 | 1 |  |  |  |  | 650890.0578 | UPGRADING | 2 | ongoing | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 634920.9062 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 300020 | Marcos NHS | MARCOS | 2 |  | 1 | 1 |  |  |  |  | 650890.0578 | UPGRADING | 2 | ongoing | 50% | 50% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 634920.9062 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 300022 | NUEVA ERA NATIONAL HIGH SCHOOL | NUEVA ERA | 2 |  | 1 | 1 |  |  |  |  | 650890.0578 | UPGRADING | 2 | ongoing | 50% | 50% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 634920.9062 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 320814 | Paoay National High School | PAOAY | 2 |  | 1 | 1 |  |  |  |  | 804898.5191 | UPGRADING | 2 | ongoing | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 787039.6562 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 500593 | Sacritan IS | PINILI | 2 |  | 1 | 1 |  |  |  |  | 650890.0578 | UPGRADING | 2 | ongoing | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 634920.9062 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 300028 | San Nicolas NHS | SAN NICOLAS | 2 |  | 1 | 1 |  |  |  |  | 727894.2885 | UPGRADING | 2 | ongoing | 75% | 75% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 710980.2812 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Ilocos Norte | 300030 | Solsona National High School | SOLSONA | 2 |  | 1 | 1 |  |  |  |  | 774096.8268 | UPGRADING | 2 | ongoing | 0% | 25% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction | 711620.7812 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Laoag City | 300374 | ILOCOS NORTE NATIONAL HIGH SCHOOL | LAOAG CITY | 1 |  | 1 | [5 empty] | 2213609.278 | UPGRADING | 2 | ongoing |  | 85% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Suspended ( INEC Resurvey, DPWH Duplicate Works to the proposed building) | Y
Region I | Pangasinan I, Lingayen | 300158 | Anda National High School | ANDA | 1 |  | 1 | [5 empty] | 940466.25 | UPGRADING | 2 | ongoing |  | 60% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan I, Lingayen | 300173 | Bocboc East NHS | AGUILAR | 2 |  | 1 | [5 empty] | 1180826.86 | UPGRADING | 2 | ongoing |  | 60% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300326 | Mangaldan National High School | MANGALDAN | 4 |  | 1 | [5 empty] | 2534915.7 | UPGRADING | 2 | ongoing |  | 80% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300290 | Bobonan National High School | POZORRUBIO | 5 |  | 1 | [5 empty] | 827525 | UPGRADING | 2 | ongoing |  | 70% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300287 | Benigno V. Aldana NHS | POZORRUBIO | 5 |  | 1 | [5 empty] | 820000 | UPGRADING | 2 | ongoing |  | 70% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 500380 | Dilan Integrated School | POZORRUBIO | 5 |  | 1 | [5 empty] | 814693.9 | UPGRADING | 2 | ongoing |  | 70% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 500378 | Don Valentin Torres Integrated School | SISON | 5 |  | 1 | [5 empty] | 881072.42 | UPGRADING | 2 | ongoing |  | 70% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300279 | Alejandro F. Oligan HS (Asan Sur NHS) | SISON | 5 |  | 1 | [5 empty] | 853000 | UPGRADING | 2 | ongoing |  | 70% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300300 | Carosucan Sur NHS | ASINGAN | 6 |  | 1 | [5 empty] | 653572.63 | UPGRADING | 2 | ongoing |  | 70% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300281 | Balungao NHS | BALUNGAO | 6 |  | 1 | [5 empty] | 874817.26 | UPGRADING | 2 | ongoing |  | 70% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300331 | Natividad NHS | NATIVIDAD | 6 |  | 1 | [5 empty] | 759129.66 | UPGRADING | 2 | ongoing |  | 70% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300311 | Eugenio P. Perez NHS | POZORRUBIO | 6 |  | 1 | [5 empty] | 886391.64 | UPGRADING | 2 | ongoing |  | 70% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300328 | Mataas Na Paaralang Juan C. Laya | SAN MANUEL | 6 |  | 1 | [5 empty] | 921000 | UPGRADING | 2 | ongoing |  | 70% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | Pangasinan II, Binalonan | 300309 | Eastern Pangasinan Agricultural College | SANTA MARIA | 6 |  | 1 | [5 empty] | 1598495.33 | UPGRADING | 2 | ongoing |  | 70% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | San Carlos City | 300380 | COLILING NATIONAL HIGH SCHOOL | SAN CARLOS CITY | 3 |  | 1 | [5 empty] | 1004365.1075 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | San Carlos City | 300390 | Tandoc NHS | SAN CARLOS CITY | 3 |  | 1 | [5 empty] | 1361537.6706 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | San Carlos City | 300391 | Turac NHS | SAN CARLOS CITY | 3 |  | 1 | [5 empty] | 1464095.4917 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | San Fernando City | 500602 | San Fernando South Central Integrated School (South CIS) | CITY OF SAN FERNANDO (Capital) | 1 |  | 1 | [5 empty] | 620849.2327 | UPGRADING | 2 | completed | 100% | 100% |  |  |  |  | 2018-04-27 | 2018-05-08 | 2018-05-18 | 2018-05-30 | 2018-06-01 | AE SQUARE ENTERPRISES | 541254.44 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | San Fernando City | 500983 | San Fernando City SPED Integrated School | CITY OF SAN FERNANDO (Capital) | 1 |  | 1 | [5 empty] | 1097980.9423 | UPGRADING | 2 | completed | 100% | 100% |  |  |  |  | 2018-04-27 | 2018-05-08 | 2018-05-18 | 2018-05-30 | 2018-06-01 | AE SQUARE ENTERPRISES | 917243.5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | San Fernando City | 300099 | Bangbangolan NHS | CITY OF SAN FERNANDO (Capital) | 1 |  | 1 | [5 empty] | 1328769.3294 | UPGRADING | 2 | completed | 100% | 100% |  |  |  |  | 2018-04-27 | 2018-05-08 | 2018-05-18 | 2018-05-30 | 2018-06-01 | AE SQUARE ENTERPRISES | 1189731.25 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | San Fernando City | 101030 | San Fernando North CS (North CES) | CITY OF SAN FERNANDO (Capital) | 1 |  | 1 | [5 empty] | 1051360.8415 | UPGRADING | 2 | completed | 100% | 100% |  |  |  |  | 2018-04-27 | 2018-05-08 | 2018-05-18 | 2018-05-30 | 2018-06-01 | AE SQUARE ENTERPRISES | 925785.69 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Urdaneta City | 300395 | Cabaruan NHS | CITY OF URDANETA | 5 |  | 1 | [5 empty] | 1068477.85 | UPGRADING | 2 | completed | 100% | 100% | 8-16-2018 | 10-15-2018 |  |  | 2018-02-04 | 2018-10-04 | 4-23-2018 | 2018-07-05 | 2018-11-05 | LAV Construction | 957618.51 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | Urdaneta City | 500007 | Catablan IS | CITY OF URDANETA | 5 |  | 1 | [5 empty] | 913475.77 | UPGRADING | 2 | completed | 100% | 100% | 8-16-2018 | 10-15-2018 |  |  | 2018-02-04 | 2018-10-04 | 4-23-2018 | 2018-07-05 | 2018-11-05 | LAV Construction | 843045.43 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region II | Isabela | 500077 | Bimonton Integrated School | MALLIG | 2 |  | 1 | 1218106.74 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools |  |  |  | 1218106.74 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 300500 | Alicia National High School | ALICIA | 3 |  | 1 | [5 empty] | 1648463.28 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 300612 | Echague National High School | ECHAGUE | 4 |  | 1 | [5 empty] | 825152.88 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 300571 | Ramon National High School | RAMON | 4 |  | 1 | [5 empty] | 967178.24 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 500092 | San Miguel Integrated School-Main | RAMON | 4 |  | 1 | [5 empty] | 1127436.31 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Tuguegarao City |  | GOSI NHS - SENIOR HIGH SCHOOL | TUGUEGARAO CITY(Capital) | 3 |  | 1 | [5 empty] | 440825.28 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region III | Aurora | 300680 | Casiguran NHS | CASIGURAN | 0 |  | 1 | [5 empty] | 2088109.79 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Aurora | 300690 | Lual NHS | CASIGURAN | 0 |  | 1 | [5 empty] | 2088109.79 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Aurora | 300682 | Dilasag NHS | DILASAG | 0 |  | 1 | [5 empty] | 2077387.33 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Aurora | 306501 | Mariano D. Marquez Memorial NHS | DINALUNGAN | 0 |  | 1 | [5 empty] | 2088109.79 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Aurora | 300685 | Dingalan NHS | DINGALAN | 0 |  | 1 | [5 empty] | 2064302.23 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Bataan | 306606 | Orani NHS - Parang-Parang | ORANI | 1 |  | 1 | [5 empty] | 3272047.49 | UPGRADING | 2 | completed | 100% | 100% | 2018-09-07 |  |  |  | April 24, 2018- May 7, 2018 | 2018-05-03 | 2018-05-21 | 2018-06-04 | 2018-07-04 | BQA Construction& Trading | 3247080.92 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Bulacan | 306711 | San Francisco Xavier High School | BULACAN | 1 |  | 1 | [5 empty] | 5985580.68 | UPGRADING | 2 | completed | 100% | 100% | 2019-01-26 |  |  |  | 2018-07-30 | 2018-08-06 | 2018-08-20 | 2018-09-03 | 2018-09-24 | Eirish Builders & Supply Inc. | 5060899.37 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Bulacan | 300755 | San Pedro National High School | HAGONOY | 1 |  | 1 | [5 empty] | 3732220.36 | UPGRADING | 2 | completed | 100% | 100% | 2019-01-27 |  |  |  | 2018-07-30 | 2018-08-06 | 2018-08-20 | 2018-09-03 | 2018-09-25 | G.M. Caparas Construction & Supply | 3342196.08 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Bulacan | 300756 | Sta. Monica National High School | HAGONOY | 1 |  | 1 | [5 empty] | 3027526.83 | UPGRADING | 2 | completed | 100% | 100% | 2019-01-27 |  |  |  | 2018-07-30 | 2018-08-06 | 2018-08-20 | 2018-09-03 | 2018-09-25 | G.M. Caparas Construction & Supply | 2768984.18 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Bulacan | 300741 | Felizardo C. Lipana NHS (Sta. Rita HS) | GUIGUINTO | 2 |  | 1 | [5 empty] | 4117936.44 | UPGRADING | 2 | completed | 100% | 100% | 2019-01-26 |  |  |  | 2018-07-30 | 2018-08-06 | 2018-08-20 | 2018-09-03 | 2018-09-24 | Eirish Builders & Supply Inc. | 3482904.82 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Bulacan | 300773 | San Rafael Nat'l Trade School | SAN RAFAEL | 3 |  | 1 | [5 empty] | 3003849.46 | UPGRADING | 2 | completed | 100% | 100% | 2019-01-26 |  |  |  | 2018-07-30 | 2018-08-06 | 2018-08-20 | 2018-09-03 | 2018-09-24 | Eirish Builders & Supply Inc. | 2543748.22 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Cabanatuan City | 301045 | Camp Tinio National High School | CABANATUAN CITY | 3 |  | 1 | [5 empty] | 2498371.74 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Munoz Science City | 500630 | SAN ANTONIO INTEGRATED SCHOOL | SCIENCE CITY OF MUÑOZ | 2 |  | 1 | [5 empty] | 752305.07 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Munoz Science City | 322801 | Munoz National High School (Annex) | SCIENCE CITY OF MUÑOZ | 2 |  | 1 | [5 empty] | 686281.39 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300839 | Restituto B. Peria HS | ALIAGA | 1 |  | 1 | [5 empty] | 378620.37 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300842 | Salagusog National High School | CUYAPO | 1 |  | 1 | [5 empty] | 415294.65 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300801 | Cuyapo National High School | CUYAPO | 1 |  | 1 | [5 empty] | 346345.28 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija |  | Cuyapo National High School (SHS) | CUYAPO | 1 |  | 1 | [5 empty] | 508561.84 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300803 | Dr. Ramon de Santos NHS | CUYAPO | 1 |  | 1 | [5 empty] | 268199.97 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300806 | Galvan National High School | GUIMBA | 1 |  | 1 | [5 empty] | 257461.33 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300869 | Triala NHS | GUIMBA | 1 |  | 1 | [5 empty] | 305424.83 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300837 | Recuerdo NHS | NAMPICUAN | 1 |  | 1 | [5 empty] | 334163.36 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija |  | Eduardo L. Joson Mem. HS (SHS) | QUEZON | 1 |  | 1 | [5 empty] | 380604.8 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300814 | Julia Ortiz Luiz NHS | SANTO DOMINGO | 1 |  | 1 | [5 empty] | 463571.14 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300857 | Sto. Domingo NTS | SANTO DOMINGO | 1 |  | 1 | [5 empty] | 541860.51 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300865 | Tabacao National High School | TALAVERA | 1 |  | 1 | [5 empty] | 648501.1 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija |  | Carmen NHS (SHS) | ZARAGOZA | 1 |  | 1 | [5 empty] | 276511.45 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300798 | Capintalan HS | CARRANGLAN | 2 |  | 1 | [5 empty] | 402027.94 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija |  | Carranglan NHS (SHS) | CARRANGLAN | 2 |  | 1 | [5 empty] | 352136.59 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300870 | Llanera National HIgh School | LLANERA | 2 |  | 1 | [5 empty] | 245855.26 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300866 | Talugtug NHS | TALUGTUG | 2 |  | 1 | [5 empty] | 323471.35 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300816 | Macabaclay National High School | BONGABON | 3 |  | 1 | [5 empty] | 197600.26 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 306812 | Ricardo Dizon Canlas Agr'l. HS (Former Jorge M. Padilla NHS Annex) | LAUR | 3 |  | 1 | [5 empty] | 267018.16 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300858 | Sto. Rosario NHS , Sta. Rosa | SANTA ROSA | 3 |  | 1 | [5 empty] | 299957.65 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300808 | General Tinio NHS | GENERAL TINIO (PAPAYA) | 4 |  | 1 | [5 empty] | 374333.36 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300836 | Lambakin National High School | JAEN | 4 |  | 1 | [5 empty] | 538124.67 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300835 | Putlod-San Jose NHS | JAEN | 4 |  | 1 | [5 empty] | 532712.46 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300832 | Peñaranda National High School | PEÑARANDA | 4 |  | 1 | [5 empty] | 312976.08 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija |  | STA. BARBARA NATIONAL HS (SHS) | SAN ANTONIO | 4 |  | 1 | [5 empty] | 450566.73 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300794 | Calaba National High School | SAN ISIDRO | 4 |  | 1 | [5 empty] | 325560.71 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300834 | Pulo NHS | SAN ISIDRO | 4 |  | 1 | [5 empty] | 452449.94 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300867 | Teodoro A. Dionisio NHS | SAN ISIDRO | 4 |  | 1 | [5 empty] | 384194.55 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300817 | Magpapalayok NHS | SAN LEONARDO | 4 |  | 1 | [5 empty] | 195151.4 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Nueva Ecija | 300821 | Mambangnan NHS | SAN LEONARDO | 4 |  | 1 | [5 empty] | 347681.19 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-A | Antipolo City | 109322 | LIBIS ES | Antipolo City | 2 |  | 1 | [5 empty] | 778402.4915 | UPGRADING | 2 | completed |  | 100% |  |  |  |  | 11-26-18 | 2018-03-12 | 12-14-18 | 12-21-18 | 1-18-19 | Hawkstow Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-A | Antipolo City | 109349 | CANUMAY ES | Antipolo City | 2 |  | 1 | [5 empty] | 783383.1514 | UPGRADING | 2 | completed |  | 100% |  |  |  |  | 11-26-18 | 2018-03-12 | 12-14-18 | 12-21-18 | 1-18-19 | Hawkstow Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-A | Antipolo City | 321502 | Canumay NHS | Antipolo City | 2 |  | 1 | [5 empty] | 751744.6159 | UPGRADING | 2 | completed |  | 100% |  |  |  |  | 11-26-18 | 2018-03-12 | 12-14-18 | 12-21-18 | 1-18-19 | Hawkstow Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-A | Antipolo City | 500391 | APIA IS | Antipolo City | 2 |  | 1 | [5 empty] | 513838.5906 | UPGRADING | 2 | completed |  | 100% |  |  |  |  | 11-26-18 | 2018-03-12 | 12-14-18 | 12-21-18 | 1-18-19 | Hawkstow Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-A | Calamba City | 301514 | Calamba Bayside Integrated School | CITY OF CALAMBA | 2 |  | 1 | [5 empty] | 1863464.5 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-A | Calamba City | 301515 | Calamba Integrated School | CITY OF CALAMBA | 2 |  | 1 | [5 empty] | 2227134.6 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-A | Cavite | 301166 | Amadeo National High School | AMADEO | 6 |  | 1 | [5 empty] | 1591456.9177 | UPGRADING | 2 | completed | 30% | 100% |  |  |  |  | June 21, 218 | June 28, 2018 | August 8, 2018 | August 16, 2018 | August 17, 2018 | R.A Del Rosario | 1554123.06 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-A | Cavite | 307817 | Tanza Trade NHS | TANZA | 6 |  | 1 | [5 empty] | 2324139.6983 | UPGRADING | 2 | completed | 10% | 100% |  |  |  |  | June 21, 218 | June 28, 2018 | August 8, 2018 | August 16, 2018 | August 17, 2018 | R.A Del Rosario | 2259976.58 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-A | Cavite | 301165 | ALFONSO NATIONAL HIGH SCHOOL | ALFONSO | 7 |  | 1 | [5 empty] | 2307918.5169 | UPGRADING | 2 | completed | 10% | 100% |  |  |  |  | June 21, 218 | June 28, 2018 | August 8, 2018 | August 16, 2018 | August 17, 2018 | R.A Del Rosario | 2245684.72 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region IV-A | Quezon | 301307 | Camohaguin National High School | GUMACA | 4 |  | 1 | [5 empty] | 2607323.41 | UPGRADING | 2 | completed | 30% | 100% | [9 empty] | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-A | Quezon | 301386 | San Francisco B NHS | LOPEZ | 4 |  | 1 | [5 empty] | 2832509.36 | UPGRADING | 2 | completed | 30% | 100% | [9 empty] | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-A | Rizal | 301428 | Bagumbong NHS | JALA-JALA | 2 |  | 1 | [5 empty] | 1630063.4 | UPGRADING | 2 | ongoing | 5% | 60% |  |  | INFRA-2018-004 |  | June 05, 2018 | June 13, 2018 | June 25, 2018 | 2018-06-27 | 2018-07-20 | LOURBEL CONSTRUCTION AND SUPPLY | 1618689.15 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-A | Rizal | 308121 | Hulo National High School | PILILLA | 2 |  | 1 | [5 empty] | 1136666.03 | UPGRADING | 2 | completed | 90% | 100% |  |  | INFRA-2018-004 |  | June 05, 2018 | June 13, 2018 | June 25, 2018 | 2018-06-27 | 2018-07-20 | LOURBEL CONSTRUCTION AND SUPPLY | 1128753.89 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-A | Rizal | 301467 | Teresa National High School | TERESA | 2 |  | 1 | [5 empty] | 905229.96 | UPGRADING | 2 | ongoing | 9% | 70% |  |  | INFRA-2018-004 |  | June 05, 2018 | June 13, 2018 | June 25, 2018 | 2018-06-27 | 2018-07-20 | LOURBEL CONSTRUCTION AND SUPPLY | 899714.96 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Oriental Mindoro | 309019 | Pag-asa NHS | BANSUD | 2 |  | 1 | [5 empty] | 747780.62 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IV-B | Puerto Princesa City | 111467 | East Central School | Puerto Princesa City | 3 |  | 1 | [5 empty] | 2493419.72 | UPGRADING | 2 | ongoing |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Puerto Princesa City | 111470 | Puerto Princesa Pilot ES | Puerto Princesa City | 3 |  | 1 | [5 empty] | 3735812.41 | UPGRADING | 2 | ongoing |  | 25% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Puerto Princesa City | 111485 | Mateo Jagmis MES | Puerto Princesa City | 3 |  | 1 | [5 empty] | 2779446.87 | UPGRADING | 2 | ongoing |  | 15% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Puerto Princesa City | 111510 | Buenavista ES | Puerto Princesa City | 3 |  | 1 | [5 empty] | 472895.77 | SOLAR PANEL | 2 | ongoing |  | 10% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Puerto Princesa City | 111520 | Makirawa Elementary School | Puerto Princesa City | 3 |  | 1 | [5 empty] | 462343.27 | UPGRADING | 2 | ongoing |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Puerto Princesa City | 301781 | Cabayugan NHS | Puerto Princesa City | 3 |  | 1 | [5 empty] | 770482.17 | SOLAR PANEL | 2 | ongoing |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Puerto Princesa City | 301781 | Cabayugan NHS | Puerto Princesa City | 3 | [7 empty] | 1506969.15 | SOLAR PANEL | 2 | ongoing |  | 15% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | N
Region IV-B | Puerto Princesa City | 301782 | Inagawan NHS | Puerto Princesa City | 3 |  | 1 | [5 empty] | 1125863.75 | UPGRADING | 2 | ongoing |  | 15% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Puerto Princesa City | 301783 | Irawan NHS - Matahimik - Bucana Annex | Puerto Princesa City | 3 |  | 1 | [5 empty] | 919823.54 | UPGRADING | 2 | ongoing |  | 15% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Puerto Princesa City | 301785 | Buenavista Annex | Puerto Princesa City | 3 |  | 1 | [5 empty] | 462343.27 | UPGRADING | 2 | ongoing |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Puerto Princesa City | 301785 | Macarascas NHS - Buenavista Annex | Puerto Princesa City | 3 | [7 empty] | 826086.38 | SOLAR PANEL | 2 | ongoing |  | 15% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | N
Region IV-B | Puerto Princesa City | 300400 | Ubaldo L. Conde High School | Puerto Princesa City | 3 |  | 1 | [5 empty] | 1070770.36 | UPGRADING | 2 | ongoing |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Puerto Princesa City | 309301 | PALAWAN NATIONAL SCHOOL | Puerto Princesa City | 3 |  | 1 | [5 empty] | 6802283.04 | UPGRADING | 2 | ongoing |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IV-B | Puerto Princesa City | 309302 | Simpucan NHS (Napsan NHS - Simpucan Annex) | Puerto Princesa City | 3 |  | 1 | [5 empty] | 770482.16 | SOLAR PANEL | 2 | ongoing |  | 15% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Puerto Princesa City | 309302 | Simpucan NHS (Napsan NHS - Simpucan Annex) | Puerto Princesa City | 3 | [7 empty] | 1509331.18 | UPGRADING | 2 | ongoing |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | Y
Region IV-B | Puerto Princesa City | 309303 | Tagabinet High School | Puerto Princesa City | 3 |  | 1 | [5 empty] | 590961.71 | SOLAR PANEL | 2 | ongoing |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
Region IV-B | Puerto Princesa City | 309303 | Tagabinet High School | Puerto Princesa City | 3 | [7 empty] | 946895.79 | SOLAR PANEL | 2 | ongoing |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | N
Region IV-B | Puerto Princesa City |  | Mandaragat - San Miguel Senior HS | Puerto Princesa City | 3 |  | 1 | [5 empty] | 1472587.37 | UPGRADING | 2 | ongoing |  | 15% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region IX | Dipolog City | 303893 | Zamboanga Norte NHS | DIPOLOG CITY (Capital) | 2 |  | 1 | [5 empty] | 2011470.98 | UPGRADING | 2 | completed | 98% | 100% | [9 empty] | MAQUESERG CONSTRUCTION & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Dipolog City |  | Zamboanga Norte NHS - Turno Campus | DIPOLOG CITY (Capital) | 2 |  | 1 | [5 empty] | 875609.79 | UPGRADING | 2 | completed | 98% | 100% | [9 empty] | MAQUESERG CONSTRUCTION & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Dipolog City |  | Zamboanga Norte NHS - Miputak Campus | DIPOLOG CITY (Capital) | 2 |  | 1 | [5 empty] | 443826.29 | UPGRADING | 2 | completed | 98% | 100% | [9 empty] | MAQUESERG CONSTRUCTION & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Dipolog City | 303887 | Dipolog City NHS (Barra) | DIPOLOG CITY (Capital) | 2 |  | 1 | [5 empty] | 871922.87 | UPGRADING | 2 | completed | 98% | 100% | [9 empty] | MAQUESERG CONSTRUCTION & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Isabela City | 303895 | Malamawi National High School | CITY OF ISABELA (Capital) | 0 |  | 1 | [5 empty] | 1155357.27 | UPGRADING | 2 | completed | 95% | 100% | [9 empty] | MMP Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Isabela City | 314601 | Isabela City NHS | CITY OF ISABELA (Capital) | 0 |  | 1 | [5 empty] | 939814.63 | UPGRADING | 2 | completed | 100% | 100% | [9 empty] | MMP Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Isabela City | 303894 | Basilan NHS | CITY OF ISABELA (Capital) | 0 |  | 1 | [5 empty] | 4706721.6 | UPGRADING | 2 | completed | 100% | 100% | [9 empty] | MMP Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Isabela City | 303897 | Begang NHS | CITY OF ISABELA (Capital) | 0 |  | 1 | [5 empty] | 2098158.43 | UPGRADING | 2 | completed | 100% | 100% | [9 empty] | MMP Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region IX | Pagadian City | 126054 | Tawagan Sur Elementary School | PAGADIAN CITY (Capital) | 1 |  | 1 | [5 empty] | 1542244.33 | UPGRADING | 2 | REVERTED | [13 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | Reported REVERTED at January 30 2019 - project was not procured since the DE requested central office to change the name to Tawagan Sur NHS | Y
Region IX | Pagadian City |  | Stand Alone - Zamboanga del Sur NHS | PAGADIAN CITY (Capital) | 1 |  | 1 | [5 empty] | 2660165.92 | UPGRADING | 2 | completed | 90% | 100% | 2018-12-27 |  | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | 2018-07-12 |  | 2018-08-01 | 2018-08-07 | 2018-08-22 | ALINAB CONSTRUCTION & SUPPLIES | 2645388.69 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | suspended - Due to the Banking requirements from Cooperative (materials for inspection by ZAMSURCO) | Y | suspended - Due to the Banking requirements from Cooperative
Region IX | Pagadian City | 303904 | Manga NHS | PAGADIAN CITY (Capital) | 1 |  | 1 | [5 empty] | 1284604.6 | UPGRADING | 2 | completed | 90% | 100% | 2018-12-27 |  | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | 2018-07-12 |  | 2018-08-01 | 2018-08-07 | 2018-08-22 | ALINAB CONSTRUCTION & SUPPLIES | 1277620.44 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | suspended - Due to the Banking requirements from Cooperative (materials for inspection by ZAMSURCO) | Y | suspended - Due to the Banking requirements from Cooperative
Region IX | Pagadian City | 303901 | Lala National High School | PAGADIAN CITY (Capital) | 1 |  | 1 | [5 empty] | 1297232.37 | UPGRADING | 2 | completed | 90% | 100% | 2018-12-27 |  | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | 2018-07-12 |  | 2018-08-01 | 2018-08-07 | 2018-08-22 | ALINAB CONSTRUCTION & SUPPLIES | 1290162.54 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | suspended - Due to the Banking requirements from Cooperative (materials for inspection by ZAMSURCO) | Y | suspended - Due to the Banking requirements from Cooperative
Region IX | Pagadian City | 314705 | Co Tek Chun National Trade School | PAGADIAN CITY (Capital) | 1 |  | 1 | [5 empty] | 1470348.25 | UPGRADING | 2 | completed | 90% | 100% | 2018-12-27 |  | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | 2018-07-12 |  | 2018-08-01 | 2018-08-07 | 2018-08-22 | ALINAB CONSTRUCTION & SUPPLIES | 1462436.82 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | suspended - Due to the Banking requirements from Cooperative (materials for inspection by ZAMSURCO) | Y | suspended - Due to the Banking requirements from Cooperative
Region IX | Pagadian City | 314702 | Norberta Guillar NHS (Napolan NHS - Norberta Guillar Mem. School Ext.) | PAGADIAN CITY (Capital) | 1 |  | 1 | [5 empty] | 1483030.63 | UPGRADING | 2 | completed | 90% | 100% | 2018-12-27 |  | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | 2018-07-12 |  | 2018-08-01 | 2018-08-07 | 2018-08-22 | ALINAB CONSTRUCTION & SUPPLIES | 1475015.43 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | suspended - Due to the Banking requirements from Cooperative (materials for inspection by ZAMSURCO) | Y | suspended - Due to the Banking requirements from Cooperative
Region V | Albay | 309503 | Alabangpuro High School | PIO DURAN | 3 |  | 1 | [5 empty] | 1374646.64 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Legaspi City | 302257 | Banquerohan NHS | LEGAZPI CITY (Capital) | 2 |  | 1 | [5 empty] | 2771096.04 | UPGRADING | 2 | completed | 100% | 100% | 2018-09-15 |  |  |  | 2018-04-12 | 2018-04-20 | 2018-05-02 | 2018-05-18 | 2018-05-21 | ZAREPATH Construction and Supply | 2716466.89 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Ligao City | 301837 | Ligao NHS | CITY OF LIGAO | 3 |  | 1 | [5 empty] | 2588654.65 | UPGRADING | 2 | completed | 100% | 100% | 9/24/2018 |  |  | DO LIGAO 04-05-2018 | 2018-04-23 | 2018-05-02 | 2018-05-17 | 2018-06-29 | 2018-07-04 | 3CA Builders | 2250000 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Utilized Savings Completed 325,711.38 | Y
Region V | Masbate | 302129 | Cataingan National High School | CATAINGAN | 3 |  | 1 | [5 empty] | 3548375.59 | UPGRADING | 2 | completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Masbate | 302121 | Buenavista National High School | USON | 3 |  | 1 | [5 empty] | 2529306.31 | UPGRADING | 2 | completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Masbate | 302131 | Del Carmen National High School | USON | 3 |  | 1 | [5 empty] | 3394197.47 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Masbate | 302110 | Temistocles A. Merioles, Sr. Memorial High School | USON | 3 |  | 1 | [5 empty] | 1346259.42 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Masbate City | 302148 | Masbate National Comprehensive High School | CITY OF MASBATE (Capital) | 2 |  | 1 | [5 empty] | 3621816.14 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Masbate City | 302133 | Capitolina O. Legaspi Memorial High School | CITY OF MASBATE (Capital) | 2 |  | 1 | [5 empty] | 1228060.54 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Masbate City |  | Masbate National Comprehensive High School Annex-Senior High School | CITY OF MASBATE (Capital) | 2 |  | 1 | [5 empty] | 1220272.53 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Sorsogon | 302197 | Casiguran Technical Vocational School | CASIGURAN | 1 |  | 1 | [5 empty] | 2652600.35 | UPGRADING | 2 | completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Sorsogon | 302201 | Cumadcad NHS | CASTILLA | 1 |  | 1 | [5 empty] | 1681856.55 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Sorsogon | 302220 | Magallanes National Vocational HS | MAGALLANES | 1 |  | 1 | [5 empty] | 1546296.31 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Sorsogon | 302222 | Magallanes National High School | MAGALLANES | 1 |  | 1 | [5 empty] | 1534901.95 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Sorsogon City | 302278 | Sawanga National High School | CITY OF SORSOGON (Capital) | 1 |  | 1 | [5 empty] | 1818648.95 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 |  | 1 | [5 empty] | 6729139.42 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Aklan | 114625 | Altavas ES | ALTAVAS | 0 |  | 1 | [5 empty] | 1493310.87 | UPGRADING | 2 | ongoing |  | 80% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-20 | HOVERT CONSTRUCTION | 1479478.88 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 114750 | Kalibo Pilot Elementary School | KALIBO (Capital) | 0 |  | 1 | [5 empty] | 1559325.69 | UPGRADING | 2 | ongoing |  | 80% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-20 | HOVERT CONSTRUCTION | 1549237.27 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 302295 | Boracay NHS-Main | MALAY | 0 |  | 1 | [5 empty] | 1424551.34 | UPGRADING | 2 | ongoing |  | 80% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION | 1416036.31 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 310603 | LAMBERTO H. TIROL NATIONAL HIGH SCHOOL | MALAY | 0 |  | 1 | [5 empty] | 1340741.03 | UPGRADING | 2 | ongoing |  | 80% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION | 1332392.44 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 310611 | Manocmanoc National High School | MALAY | 0 |  | 1 | [5 empty] | 1424551.34 | UPGRADING | 2 | ongoing |  | 80% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION | 1416037.9 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 114850 | Malay Elementary School | MALAY | 0 |  | 1 | [5 empty] | 1375101.76 | UPGRADING | 2 | ongoing |  | 80% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION | 1366795.3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 114887 | Nabas ES | NABAS | 0 |  | 1 | [5 empty] | 1359273.01 | UPGRADING | 2 | ongoing |  | 80% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION | 1346335.63 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Aklan | 114907 | New Washington ES | NEW WASHINGTON | 0 |  | 1 | [5 empty] | 1359273.01 | UPGRADING | 2 | ongoing |  | 80% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION | 1346585.61 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Antique | 302356 | Governor Julian Fullon Pacificador National School | HAMTIC | 0 |  | 1 | [5 empty] | 1540311.71 | UPGRADING | 2 | completed | 100% | 100% | August 24, 2018 |  | R6-D2-2018BEFF-06A-E | R6-D2-2018BEFF-06A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Elaectrical Engineering & Supply | 1079396.57 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Antique | 310708 | Eastern Laua-an NHS (Maria NHS) | LAUA-AN | 0 |  | 1 | [5 empty] | 1555222.1 | UPGRADING | 2 | completed | 100% | 100% | August 24, 2018 |  | R6-D2-2018BEFF-06A-E | R6-D2-2018BEFF-06A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Elaectrical Engineering & Supply | 1172199.65 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial NHS | CADIZ CITY | 2 |  | 1 | [5 empty] | 1457684.85 | UPGRADING | 2 | ongoing |  | 0% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | under suspension
Region VI | Cadiz City | 302727 | Sicaba National High School | CADIZ CITY | 2 |  | 1 | [5 empty] | 1457684.85 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Iloilo | 302585 | Zarraga National High School | ZARRAGA | 2 |  | 1 | [5 empty] | 4863807.6433 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Iloilo | 302443 | Ajuy NHS | AJUY | 5 |  | 1 | [5 empty] | 4791597.203 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Iloilo | 302458 | Barotac Viejo National High School | BAROTAC VIEJO | 5 |  | 1 | [5 empty] | 4712460.5419 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Iloilo | 302570 | Sara NHS | SARA | 5 |  | 1 | [5 empty] | 5410620.46 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Kabankalan City | 117862 | Linao ES | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 610781.59 | UPGRADING | 2 | ongoing |  | 95% | October 23,2018 |  | 2018-018 | 2018-018 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders | 602926.46 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Kabankalan City | 117860 | Inapoy ES | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1118972.87 | UPGRADING | 2 | completed |  | 100% | October 30,2018 |  | 2018-017 | 2018-017 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 25,2018 | Rism Builders and Construction Services Inc. | 1107188.35 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Kabankalan City | 117870 | Tagoc ES | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1125610.39 | UPGRADING | 2 | completed |  | 100% | October 30,2018 |  | 2018-017 | 2018-017 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 25,2018 | Rism Builders and Construction Services Inc. | 1113766.43 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Kabankalan City | 117890 | Pacao ES | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 823203.85 | UPGRADING | 2 | ongoing |  | 95% | October 23,2018 |  | 2018-016 | 2018-016 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders | 812381.19 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Kabankalan City | 117876 | Binicuil ES | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1289994.35 | UPGRADING | 2 | ongoing |  | 95% | October 23,2018 |  | 2018-016 | 2018-016 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders | 1279684.23 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Kabankalan City | 117877 | Calabasahan ES | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 524506.15 | UPGRADING | 2 | completed |  | 100% | October 30,2018 |  | 2018-017 | 2018-017 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 25,2018 | Rism Builders and Construction Services Inc. | 518045.22 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Kabankalan City | 117880 | Daan Banua ES | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 1121839.62 | UPGRADING | 2 | ongoing |  | 95% | October 23,2018 |  | 2018-018 | 2018-018 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders | 1111632.05 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Kabankalan City | 117864 | Matama ES | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 886082.7 | UPGRADING | 2 | ongoing |  | 95% | October 23,2018 |  | 2018-018 | 2018-018 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders | 874897.42 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Kabankalan City | 117848 | Orong ES | CITY OF KABANKALAN | 6 |  | 1 | [5 empty] | 739363.37 | UPGRADING | 2 | ongoing |  | 95% | October 23,2018 |  | 2018-016 | 2018-016 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders | 730730.71 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VI | Silay City | 302780 | Doña Montserrat Lopez MHS | SILAY CITY | 3 |  | 1 | [5 empty] | 4612008.25 | UPGRADING | 2 | ongoing |  | 70% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region VII | Bogo City | 500407 | City of Bogo Science and Arts Academy | CITY OF BOGO | 4 |  | 1 | [5 empty] | 2041601.49 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302873 | Mahayag National High School | SAN MIGUEL | 2 |  | 1 | [5 empty] | 1740854.71 | UPGRADING | 2 | completed | 95% | 100% | [9 empty] | RONNYL CONSTRUCTION | 1455092.1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302855 | Guinsularan High School | DUERO | 3 |  | 1 | [5 empty] | 995481.66 | UPGRADING | 2 | completed | 95% | 100% | [9 empty] | RONNYL CONSTRUCTION | 855231.3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Bohol | 302849 | Faraon NHS | JAGNA | 3 |  | 1 | [5 empty] | 1023687.84 | UPGRADING | 2 | completed | 95% | 100% | [9 empty] | RONNYL CONSTRUCTION | 834545.25 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Cebu | 303049 | Magsico NHS | SAN FERNANDO | 1 |  | 1 | [5 empty] | 1133120.63 | UPGRADING | 2 | completed | 100% | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Cebu | 303022 | Julian Enad MNHS | SIBONGA | 1 | 1st District | 1 | [5 empty] | 955332.52 | UPGRADING | 2 | completed | 100% | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Cebu | 303018 | Guiwanon NHS | GINATILAN | 2 |  | 1 | [5 empty] | 1374105.86 | UPGRADING | 2 | completed | 100% | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Cebu | 302939 | Bateria NHS | DAANBANTAYAN | 4 |  | 1 | [5 empty] | 2647612.01 | UPGRADING | 2 | completed | 100% | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Cebu | 302963 | Paypay NHS | DAANBANTAYAN | 4 |  | 1 | [5 empty] | 1337053.81 | UPGRADING | 2 | completed | 100% | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Cebu | 303048 | San Agustin NHS | MADRIDEJOS | 4 |  | 1 | [5 empty] | 1413045.85 | UPGRADING | 2 | completed | 100% | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Cebu | 303027 | Medellin National Science and Technology School | MEDELLIN | 4 |  | 1 | [5 empty] | 841720.41 | UPGRADING | 2 | completed | 100% | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Cebu | 303054 | Medellin National High School | MEDELLIN | 4 |  | 1 | [5 empty] | 1600155.61 | UPGRADING | 2 | completed | 100% | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Cebu | 303041 | Libaong National High School | SAN REMIGIO | 4 |  | 1 | [5 empty] | 828800.91 | UPGRADING | 2 | completed | 100% | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Cebu | 303046 | Luyang NHS | SAN REMIGIO | 4 |  | 1 | [5 empty] | 1237904.04 | UPGRADING | 2 | completed | 100% | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Cebu | 312407 | Arcelo Memorial National Night High School | LILOAN | 5 |  | 1 | [5 empty] | 456948.79 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 2nd Failure of Bidding | Y
Region VII | Cebu City | 303136 | Busay National High School | CEBU CITY (Capital) | 1 |  | 1 | [5 empty] | 492928.39 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Cebu City | 303137 | Paril NHS | CEBU CITY (Capital) | 1 |  | 1 | [5 empty] | 383685.6969 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Cebu City | 303139 | Lahug NHS (Night) | CEBU CITY (Capital) | 1 |  | 1 | [5 empty] | 1386454.8506 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Cebu City | 303151 | MABOLO NATIONAL HIGH SCHOOL | CEBU CITY (Capital) | 1 |  | 1 | [5 empty] | 995711.3531 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Cebu City | 303152 | Barrio Luz NHS (Day & Night) | CEBU CITY (Capital) | 1 |  | 1 | [5 empty] | 1358540.5692 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Cebu City | 303156 | Zapatera NHS (Day & Night) | CEBU CITY (Capital) | 1 |  | 1 | [5 empty] | 2120006.304 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Cebu City | 303157 | Guba NHS | CEBU CITY (Capital) | 1 |  | 1 | [5 empty] | 510261.93 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Cebu City | 303132 | Lusaran NHS | CEBU CITY (Capital) | 1 |  | 1 | [5 empty] | 390803.7096 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Cebu City | 303133 | Don Vicente Rama Mem. NHS (Basak NHS) | CEBU CITY (Capital) | 2 |  | 1 | [5 empty] | 1980550.9437 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Cebu City | 303134 | Bonbon NHS | CEBU CITY (Capital) | 2 |  | 1 | [5 empty] | 324999.5883 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Cebu City | 303141 | Cebu City National Science HS | CEBU CITY (Capital) | 2 |  | 1 | [5 empty] | 1057985.3984 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Cebu City | 303143 | Bulacao Community HS (Day & Night) | CEBU CITY (Capital) | 2 |  | 1 | [5 empty] | 465552.23 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Cebu City | 303145 | Inayawan National High School | CEBU CITY (Capital) | 2 |  | 1 | [5 empty] | 1079973.4794 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Cebu City | 303147 | Pasil NHS (Night) | CEBU CITY (Capital) | 2 |  | 1 | [5 empty] | 858364.18 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Cebu City | 303159 | Pardo NHS (Day & Night) | CEBU CITY (Capital) | 2 |  | 1 | [5 empty] | 864341.69 | UPGRADING | 2 | completed | 0% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | City of Naga, Cebu | 303121 | Uling National High School | CITY OF NAGA | 0 |  | 1 | [5 empty] | 1361639.32 | UPGRADING | 2 | completed | 100% | 100% | 2018-09-09 | 2018-09-24 | cityofnaga 2018-003 |  | April 13-20, 2018 | 2018-04-13 | 2018-04-26 | 2018-05-14 | 2018-06-04 | QCC CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | City of Naga, Cebu | 303120 | Tuyan National High School | CITY OF NAGA | 0 |  | 1 | [5 empty] | 1130846.69 | UPGRADING | 2 | completed | 50% | 100% | 2018-09-09 | 2018-09-24 | cityofnaga 2018-003 |  | April 13-20, 2018 | 2018-04-13 | 2018-04-26 | 2018-05-14 | 2018-06-04 | QCC CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VII | Danao City | 303037 | Maslog National High School | DANAO CITY | 5 |  | 1 | [5 empty] | 1877921.65 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Negros Oriental | 303276 | Tambo National High School | AYUNGON | 1 |  | 1 | [5 empty] | 590808.68 | UPGRADING | 2 | ongoing | 16% | 32% | 2018-09-26 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-18 | SM & MST CONSTRUCTION | 587371.98 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 303228 | Demetrio L. Alviola NHS | BINDOY (PAYABON) | 1 |  | 1 | [5 empty] | 1125370.28 | UPGRADING | 2 | ongoing | 16% | 34% | 2018-09-26 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-18 | SM & MST CONSTRUCTION | 1119476.6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 303255 | Negros Oriental High School | DUMAGUETE CITY (Capital) | 2 |  | 1 | [5 empty] | 643928.75 | UPGRADING | 2 | ongoing | 45% | 45% | 2018-09-26 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-18 | SM & MST CONSTRUCTION | 634357.53 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Terminated |  | recommended for termination
Region VII | Negros Oriental | 303247 | Benedicto P. Tirambulo Mem. National High School | MABINAY | 2 |  | 1 | [5 empty] | 637792.52 | UPGRADING | 2 | ongoing | 16% | 47% | 2018-09-26 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-18 | SM & MST CONSTRUCTION | 640485.86 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Recommended for Termination |  | recommended for termination
Region VII | Negros Oriental | 303226 | Antonio B. Alejado MHS (Mag-aso HS) | DAUIN | 3 |  | 1 | [5 empty] | 502304.6 | UPGRADING | 2 | completed | 100% | 100% | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT | 499512.55 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Negros Oriental |  | Antonio B. Alejado MHS (Campus II) | DAUIN | 3 |  | 1 | [5 empty] | 516957.6 | UPGRADING | 2 | completed | 100% | 100% | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT | 514088.84 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Negros Oriental | 312937 | Aurelia G. Merecido Memorial High School (Cabangahan HS) | SIATON | 3 |  | 1 | [5 empty] | 563035.84 | UPGRADING | 2 | completed | 100% | 100% | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT | 559881.45 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Negros Oriental | 303253 | Maloh PCHS | SIATON | 3 |  | 1 | [5 empty] | 698194.63 | UPGRADING | 2 | completed | 100% | 100% | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT | 693171.23 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Negros Oriental | 303249 | Santiago Delmo MHS (Maluay HS) | ZAMBOANGUITA | 3 |  | 1 | [5 empty] | 855825.17 | UPGRADING | 2 | completed | 100% | 100% | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT | 850910.43 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VII | Tanjay City | 120541 | Alangilan PS | CITY OF TANJAY | 2 |  | 1 | [5 empty] | 1170923.34 | SOLAR PANEL | 2 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VII | Tanjay City | 120565 | Toyupan Elementary School | CITY OF TANJAY | 2 |  | 1 | [5 empty] | 1870833.45 | SOLAR PANEL | 2 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VII | Tanjay City | 120543 | Ballacag ES | CITY OF TANJAY | 2 |  | 1 | [5 empty] | 1306144.33 | SOLAR PANEL | 2 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VII | Tanjay City | 120561 | Ponglo Elementary School | CITY OF TANJAY | 2 |  | 1 | [5 empty] | 1499917.3 | SOLAR PANEL | 2 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VII | Tanjay City | 234004 | Mandalamon Elementary School | CITY OF TANJAY | 2 |  | 1 | [5 empty] | 1157207.78 | SOLAR PANEL | 2 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VII | Toledo City | 303308 | Bato NHS | TOLEDO CITY | 3 |  | 1 | [5 empty] | 858349.32 | UPGRADING | 2 | completed | 20% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VIII | Baybay City | 313312 | Mailhi National High School | CITY OF BAYBAY | 5 |  | 1 | [5 empty] | 2680839.11 | UPGRADING | 2 | completed | 100% | 100% |  |  |  |  | 2018-05-28 | 2018-06-20 | 2018-06-25 | 2018-07-11 | 2018-07-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Baybay City | 313323 | Ciabu National High School | CITY OF BAYBAY | 5 |  | 1 | [5 empty] | 2390942.48 | UPGRADING | 2 | completed | 100% | 100% |  |  |  |  | 2018-05-28 | 2018-06-20 | 2018-06-25 | 2018-07-11 | 2018-07-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Baybay City | 344593 | Baybay City Senior High School | CITY OF BAYBAY | 5 |  | 1 | [5 empty] | 1700496.67 | UPGRADING | 2 | completed | 100% | 100% |  |  |  |  | 2018-05-28 | 2018-06-20 | 2018-06-25 | 2018-07-11 | 2018-07-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Biliran | 313202 | Biliran Science High School | BILIRAN | 0 |  | 1 | [5 empty] | 1482557.79 | UPGRADING | 2 | completed | 100% | 100% | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | W.B ALAGAO CONSTRUCTION | 1471181.88 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Biliran | 303322 | Cabucgayan National School of Arts and Trade | CABUCGAYAN | 0 |  | 1 | [5 empty] | 4379481.59 | UPGRADING | 2 | completed | 100% | 100% | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | QYT CONSTRUCTION | 4345813.3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Biliran | 303328 | Manlabang National High School | CAIBIRAN | 0 |  | 1 | [5 empty] | 4368287.45 | UPGRADING | 2 | completed | 100% | 100% | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | J.CUSTORIO CONSTRUCTION | 4,304,00.00 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Biliran | 303324 | Culaba NVS | CULABA | 0 |  | 1 | [5 empty] | 4315524.95 | UPGRADING | 2 | completed | 100% | 100% | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | MKB BUILDERS & SUPPY | 4273054.68 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Biliran | 303331 | Naval School of Fisheries | NAVAL (Capital) | 0 |  | 1 | [5 empty] | 4724556.18 | UPGRADING | 2 | completed | 100% | 100% | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | BNL CONSTRUCTION | 4685748.31 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Biliran | 303330 | Naval National High School | NAVAL (Capital) | 0 |  | 1 | [5 empty] | 3051257.34 | UPGRADING | 2 | completed | 100% | 100% | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | MB ANG CONSTRUCTION | 3017616 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Biliran | 303327 | Lucsoon NHS | NAVAL (Capital) | 0 |  | 1 | [5 empty] | 1573233.98 | UPGRADING | 2 | completed | 100% | 100% | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | A & B ENTERPRISE | 1554689.64 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Calbayog City | 500807 | Bagacay Integrated School | CALBAYOG CITY | 1 |  | 1 | [5 empty] | 2360813.61 | UPGRADING | 2 | completed | 90% | 100% |  |  | CAL ESUP CY2018 B2 | CAL ESUP CY2018 B2 | 2018-04-20 | 2018-04-21 | 2018-05-11 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | for award | Y
Region VIII | Eastern Samar | 313501 | Can-avid National High School | CAN-AVID | 0 |  | 1 | [5 empty] | 3376983.67 | UPGRADING | 2 | COMPLETED | 85% | 100% |  |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2 ESAMAR-LOT 2 - REBID | CY 2018-BEFF ELECTRIFICATION-02 | 2018-06-04 | 2018-06-14 | 2018-06-26 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Eastern Samar | 303502 | Giporlos National Trade School | GIPORLOS | 0 |  | 1 | [5 empty] | 2850070.88 | UPGRADING | 2 | COMPLETED | 95% | 100% |  |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2 ESAMAR-LOT 1 | CY 2018-BEFF ELECTRIFICATION-01 | 2018-04-16 | 2018-03-11 | 2018-05-31 |  |  | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Eastern Samar | 303520 | Oras National High School | ORAS | 0 |  | 1 | [5 empty] | 2549376.4 | UPGRADING | 2 | COMPLETED | 90% | 100% |  |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2 ESAMAR-LOT 3- REBID | CY 2018-BEFF ELECTRIFICATION-03 | 2018-06-04 | 2018-06-14 | 2018-06-26 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303336 | Alangalang National High School | ALANGALANG | 1 |  | 1 | [5 empty] | 6177826.74 | UPGRADING | 2 | completed | 100% | 100% |  |  | lot 5-cy-2018-E-B2-leyte | lot 5-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | MASS CONSTRUCTION AND CONSTRUCTION SUPPLY | 6036005.25 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303343 | Juan S. Tismo National High School (Babatngon National High School) | BABATNGON | 1 |  | 1 | [5 empty] | 1982220.18 | UPGRADING | 2 | completed | 100% | 100% |  |  | lot 6-cy-2018-E-B2-leyte | lot 6-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | MJM BUILDERS AND INTERPRISES | 1935484.34 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303415 | Palo National High School | PALO | 1 |  | 1 | [5 empty] | 1967538.7 | UPGRADING | 2 | completed | 100% | 100% |  |  | lot 7-cy-2018-E-B2-leyte | lot 7-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | HD GOLDEN BULDERS AND SUPPLY INC. | 1922728.25 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 313305 | Tanauan School of Arts and Trade | TANAUAN | 1 |  | 1 | [5 empty] | 1174573.79 | UPGRADING | 2 | completed | 100% | 100% |  |  | lot 8-cy-2018-E-B2-leyte | lot 8-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | JELM CONSTRUCTION | 1147827.61 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303388 | Tanauan Sch. Of Craftsmanship & Home Industries (LIT-Tanauan Campus)Campus | TANAUAN | 1 |  | 1 | [5 empty] | 1690466.94 | UPGRADING | 2 | completed | 90% | 100% |  |  | lot 9-cy-2018-E-B2-leyte | lot 9-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | J.A. CONST. AND TRADING CORP. (Formerly: J.A. Construction ) | 1658407.13 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303363 | Celestino De Guzman Memorial National High School | BARUGO | 2 |  | 1 | [5 empty] | 1788212.64 | UPGRADING | 2 | completed | 100% | 100% |  |  | lot 10-cy-2018-E-B2-leyte | lot 10-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | FJ. TIU & ASSOCIATES CONSTRUCTION & DEVELOPMENT CORP. | 1762836.24 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303341 | Asuncion S. Melgar National High School | CAPOOCAN | 2 |  | 1 | [5 empty] | 1715056.46 | UPGRADING | 2 | completed | 100% | 100% |  |  | lot 11-cy-2018-E-B2-leyte | lot 11-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | YFL BUILDERS | 1677900.42 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 313307 | Jugaban National High School | CARIGARA | 2 |  | 1 | [5 empty] | 1677277.16 | UPGRADING | 2 | completed | 100% | 100% |  |  | lot 12-cy-2018-E-B2-leyte | lot 12-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | HARDLINES BUILDERS AND SALES | 1642209.33 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303362 | Carigara National Vocational School | CARIGARA | 2 |  | 1 | [5 empty] | 2036324.97 | UPGRADING | 2 | completed | 100% | 100% |  |  | lot 13-cy-2018-E-B2-leyte | lot 13-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | LRD CONSTRUCTION AND SUPPLY | 2000351.02 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303387 | Leyte Agro Industrial School | LEYTE | 3 |  | 1 | [5 empty] | 3214202.53 | UPGRADING | 2 | completed | 100% | 100% |  |  | lot 14-cy-2018-E-B2-leyte | lot 14-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | J. CUSTORIO CONSTRUCTION | 3139000 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303368 | Dr. Geronimo B. Zaldivar Memorial School of Fisheries | ALBUERA | 4 |  | 1 | [5 empty] | 1655671.04 | UPGRADING | 2 | completed | 100% | 100% |  |  | lot 15-cy-2018-E-B2-leyte | lot 15-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | BENCH CONSTRUCTION AND SUPPLY | 1616917.39 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303406 | Matlang National High School | ISABEL | 4 |  | 1 | [5 empty] | 2134188.44 | UPGRADING | 2 | completed | 100% | 100% |  |  | lot 16-cy-2018-E-B2-leyte | lot 16-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | MAGA CONSTRUTION AND SUPPLIES | 2091336.37 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303374 | Hilongos National Vocational School | HILONGOS | 5 |  | 1 | [5 empty] | 1666610.71 | UPGRADING | 2 | completed | 100% | 100% |  |  | lot 17-cy-2018-E-B2-leyte | lot 17-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | MASS CONSTRUCTION AND CONSTRUCTION SUPPLY | 1619847.86 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303356 | Cahagnaan National High School | MATALOM | 5 |  | 1 | [5 empty] | 1673096.47 | UPGRADING | 2 | completed | 100% | 100% |  |  | lot 18-cy-2018-E-B2-leyte | lot 18-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | GPUY CONSTRUCTION AND SUPPLY | 1636201.66 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Maasin City | 303454 | Dongon NHS | CITY OF MAASIN (Capital) | 0 |  | 1 | [5 empty] | 1628954.86 | UPGRADING | 2 | completed | 85% | 100% |  |  | ELECTRIFICATION-18-6-001 | ELECTRIFICATION-18-6-001 | 2018-06-11 | 2018-06-20 | 2018-07-02 | 2018-07-18 | 2018-12-10 | DAYBREAK ENTERPRISES ENGINEERING & CONSTRUCTION | 1620850.61 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Maasin City | 323101 | Ibarra National High School | CITY OF MAASIN (Capital) | 0 |  | 1 | [5 empty] | 1639879.93 | UPGRADING | 2 | completed | 85% | 100% |  |  | ELECTRIFICATION-18-6-002 | ELECTRIFICATION-18-6-002 | 2018-06-11 | 2018-06-20 | 2018-07-02 | 2018-07-18 | 2018-12-10 | DAYBREAK ENTERPRISES ENGINEERING & CONSTRUCTION | 1631721.33 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Northern Samar | 303577 | San Isidro Agro-Industrial High School | SAN ISIDRO | 1 |  | 1 | [5 empty] | 2694755.8 | UPGRADING | 2 | completed | 100% | 100% |  |  | BEFF2018-B2-E-NS-L1 | BEFF2018-B2-E-NS-L1 | June 6, 2018 | June 14, 2018 | 2018-07-02 | 2018-07-25 |  | MAGA CONSTRUCTION & SUPPLY | 2252210.12 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Northern Samar | 303580 | San Jose Technical HS | SAN JOSE | 1 |  | 1 | [5 empty] | 2123000.01 | UPGRADING | 2 | completed | 100% | 100% |  |  | BEFF2018-B2-E-NS-L2 | BEFF2018-B2-E-NS-L2 | June 6, 2019 | June 14, 2019 | 2018-07-02 | 2018-07-25 |  | MAGA CONSTRUCTION & SUPPLY | 1774492.2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Northern Samar | 303556 | Laoang National Technical High School | LAOANG | 2 |  | 1 | [5 empty] | 2131770.4 | UPGRADING | 2 | completed | 100% | 100% |  |  | BEFF2018-B2-E-NS-L3 | BEFF2018-B2-E-NS-L3 | June 6, 2020 | June 14, 2020 | 2018-07-02 | 2018-07-25 |  | ROSS ENGINEERING & CONSTRUCTION | 2089873.18 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Northern Samar | 303564 | Mapanas Agro-Industrial High School | MAPANAS | 2 |  | 1 | [5 empty] | 2634837.55 | UPGRADING | 2 | completed | 100% | 100% |  |  | BEFF2018-B2-E-NS-L4 | BEFF2018-B2-E-NS-L4 | June 6, 2021 | June 14, 2021 | 2018-07-02 | 2018-07-25 |  | MAGA CONSTRUCTION & SUPPLY | 2202290.21 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 313905 | Ormoc City Night High School | ORMOC CITY | 4 |  | 1 | [5 empty] | 1282907.11 | UPGRADING | 2 | completed | 100% | 100% |  |  | 2018-beff-e-b2-c8 | 2018-beff-e-b2-c8 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124221 | San Pablo Elementary School (Simangan) | ORMOC CITY | 4 |  | 1 | [5 empty] | 1772034.2 | UPGRADING | 2 | completed | 100% | 100% |  |  | 2018-beff-e-b2-c4 | 2018-beff-e-b2-c4 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124198 | Punta Elementary School | ORMOC CITY | 4 |  | 1 | [5 empty] | 1674516.68 | UPGRADING | 2 | completed | 100% | 100% |  |  | 2018-beff-e-b2-c5 | 2018-beff-e-b2-c5 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124201 | Bagong Buhay Elementary School | ORMOC CITY | 4 |  | 1 | [5 empty] | 1381598.37 | UPGRADING | 2 | completed | 100% | 100% |  |  | 2018-beff-e-b2-c7 | 2018-beff-e-b2-c7 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124148 | Can-adieng Elementary School | ORMOC CITY | 4 |  | 1 | [5 empty] | 2245826.86 | UPGRADING | 2 | completed | 100% | 100% |  |  | 2018-beff-e-b2-c3 | 2018-beff-e-b2-c3 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124203 | Cogon Central School | ORMOC CITY | 4 |  | 1 | [5 empty] | 2757663.47 | UPGRADING | 2 | completed | 100% | 100% |  |  | 2018-beff-e-b2-c2 | 2018-beff-e-b2-c2 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 194501 | Ormoc City Central School | ORMOC CITY | 4 |  | 1 | [5 empty] | 3776008.61 | UPGRADING | 2 | completed | 80% | 100% |  |  | 2018-beff-e-b2-c1 | 2018-beff-e-b2-c1 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124194 | Alegria Batuan ES | ORMOC CITY | 4 |  | 1 | [5 empty] | 1576999.15 | UPGRADING | 2 | completed | 100% | 100% |  |  | 2018-beff-e-b2-c6 | 2018-beff-e-b2-c6 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Samar (Western Samar) | 123498 | Beslig ES | GANDARA | 1 |  | 1 | [5 empty] | 655750.5 | UPGRADING | 2 | completed | 100% | 100% | 2018-10-11 |  | CY2018BEFF-ELB2-L1 | CY2018BEFF-ELB2-L1 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | MAGA Const. & Supply | 647586.2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Samar (Western Samar) | 303599 | Clarencio Calagos Mem SOF | SANTA MARGARITA | 1 |  | 1 | [5 empty] | 2280064.55 | UPGRADING | 2 | completed | 100% | 100% | 2018-10-11 |  | CY2018BEFF-ELB2-L2 | CY2018BEFF-ELB2-L2 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | NV & C Const. Supply | 2253634.61 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Samar (Western Samar) | 303609 | Jiabong National High School | JIABONG | 2 |  | 1 | [5 empty] | 2133635.11 | UPGRADING | 2 | completed | 100% | 100% | 2018-10-11 |  | CY2018BEFF-ELB2-L3 | CY2018BEFF-ELB2-L3 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | NV & C Const. Supply | 2121485.36 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Samar (Western Samar) | 303631 | Sta. Rita NHS | SANTA RITA | 2 |  | 1 | [5 empty] | 2002105.61 | UPGRADING | 2 | completed | 100% | 100% | 2018-10-11 |  | CY2018BEFF-ELB2-L4 | CY2018BEFF-ELB2-L4 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | MAGA Const. & Supply | 1970291.48 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Samar (Western Samar) | 303605 | Guintarcan NHS | VILLAREAL | 2 |  | 1 | [5 empty] | 1535226.82 | UPGRADING | 2 | completed | 100% | 100% | 2018-10-11 |  | CY2018BEFF-ELB2-L5 | CY2018BEFF-ELB2-L5 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | NV & C Const. Supply | 1511737.82 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Southern Leyte | 303475 | Paku NHS | BONTOC | 0 |  | 1 | [5 empty] | 2380206.32 | UPGRADING | 2 | completed | 100% | 100% |  |  | 18-5-001 | 18-5-001 | 2018-05-25 | 2018-06-01 | 2018-06-18 | 2018-07-04 | 2018-07-10 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION | 2356522.67 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Southern Leyte | 303460 | Himbangan National High School | SAINT BERNARD | 0 |  | 1 | [5 empty] | 3051800.83 | UPGRADING | 2 | completed | 100% | 100% |  |  | 18-5-002 | 18-5-002 | 2018-05-25 | 2018-06-01 | 2018-06-18 | 2018-07-04 | 2018-07-10 | VHITS D. G. BUILDERS & ENTERPRISES | 3021434.65 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Tacloban City | 314005 | Scandinavian National High School | TACLOBAN CITY (Capital) | 1 |  | 1 | [5 empty] | 1530499.13 | UPGRADING | 2 | completed | 100% | 100% | 2018-07-30 |  | CY 2018_BEFF ELECTRIFICATION-Batch 2_C1 | CY 2018_BEFF ELECTRIFICATION-Batch 2_C1 | 2018-04-26 | 2018-05-03 | 2018-05-15 | 2018-05-18 | 2018-05-22 | MASS CONSTRUCTION AND CONSTRUCTION SUPPLY | 1507884.51 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Tacloban City | 330503 | V&G National High School | TACLOBAN CITY (Capital) | 1 |  | 1 | [5 empty] | 1728949.63 | UPGRADING | 2 | completed | 100% | 100% | 2018-07-30 |  | CY 2018_BEFF ELECTRIFICATION-Batch 2_C2 | CY 2018_BEFF ELECTRIFICATION-Batch 2_C2 | 2018-04-26 | 2018-05-03 | 2018-05-15 | 2018-05-18 | 2018-05-22 | TITANYA CONSTRUCTION & DEVELOPMENT CORPORATION | 1701750.55 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Bukidnon | 303948 | Bocboc NHS | DON CARLOS | 3 |  | 1 | [5 empty] | 1377615.56 | UPGRADING | 2 | ongoing | 5% | 60% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Cagayan de Oro City | 304112 | Carmen National High School | CAGAYAN DE ORO CITY (Capital) | 1 |  | 1 | [5 empty] | 2496894.65 | UPGRADING | 2 | ongoing | 66% | 70% |  |  |  |  | 2018-07-31 | 2018-08-08 | 2018-08-29 |  |  | BREMA CONSTRUCTON | 2473358.01 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Cagayan de Oro City | 304106 | Bayabas National High School | CAGAYAN DE ORO CITY (Capital) | 1 |  | 1 | [5 empty] | 2935952.5 | UPGRADING | 2 | ongoing | 65% | 70% |  |  |  |  | 2018-07-31 | 2018-08-08 | 2018-08-29 |  |  | BREMA CONSTRUCTON | 2911668.44 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Cagayan de Oro City | 304125 | Taglimao National High School | CAGAYAN DE ORO CITY (Capital) | 1 |  | 1 | [5 empty] | 1534398.56 | UPGRADING | 2 | ongoing | 75% | 89% |  |  |  |  | 2018-07-31 | 2018-08-08 | 2018-08-29 |  |  | BREMA CONSTRUCTON | 1516689.22 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | El Salvador | 304065 | Cogon NHS | CITY OF EL SALVADOR | 2 |  | 1 | [5 empty] | 3640724.85 | UPGRADING | 2 | completed | 100% | 100% | 2018-11-05 |  |  | 2018-04-0087 | 2018-04-28 | 2018-05-15 | 2018-06-05 | 2018-06-20 | 2018-06-28 | Joash AR Engineering | 3602767.26 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Gingoog City | 304136 | Jacinto D. Malimas Sr. National High School | GINGOOG CITY | 1 |  | 1 | [5 empty] | 1235494.03 | UPGRADING | 2 | ongoing | 90% | 90% | 2018-11-05 |  |  |  |  | 2018-05-28 | 2018-06-03 | 2018-07-27 |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Gingoog City | 315502 | Odiongan NHS - Talisay NHS Annex | GINGOOG CITY | 1 |  | 1 | [5 empty] | 1335344.6 | UPGRADING | 2 | ongoing | 90% | 90% | 2018-11-05 |  |  |  |  | 2018-05-28 | 2018-06-03 | 2018-07-27 |  |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Lanao del Norte | 304012 | MATUNGAO NATIONAL HIGH SCHOOL | MATUNGAO | 1 |  | 1 | [5 empty] | 1575318.14 | UPGRADING | 2 | ongoing | 20% | 25% | 2018-12-13 |  |  |  | 2018-06-08 | 2018-06-18 | 2018-07-03 | 2018-07-11 | 2018-07-18 | GREEN BUILDERS | 1550017.52 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Lanao del Norte | 304018 | Pantao Ragat Agro-Ind. HS | PANTAO RAGAT | 2 |  | 1 | [5 empty] | 2290379.34 | UPGRADING | 2 | ongoing | 20% | 20% | 2018-12-13 |  |  |  | 2018-06-08 | 2018-06-18 | 2018-07-03 | 2018-07-11 | 2018-07-18 | GREEN BUILDERS | 2233156.57 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Misamis Occidental | 304024 | Aloran Trade HS | ALORAN | 1 |  | 1 | [5 empty] | 2803883.95 | UPGRADING | 2 | completed | 100% | 100% | 2018-12-05 |  |  | 013-2018 | 2018-04-27 |  | 2018-05-10 | 2018-06-08 | 2018-07-31 | JEFY CONSTRUCTION | 2786248.77 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Misamis Occidental | 304037 | Jimenez NCHS | JIMENEZ | 1 |  | 1 | [5 empty] | 1149848.54 | UPGRADING | 2 | completed | 100% | 100% | 2018-12-05 |  |  | 012-2018 | 2018-04-27 |  | 2018-05-10 | 2018-06-08 | 2018-07-31 | JEFY CONSTRUCTION | 1140754.84 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Misamis Occidental | 315207 | Sibugon IS | LOPEZ JAENA | 1 |  | 1 | [5 empty] | 3088427.99 | UPGRADING | 2 | completed | 100% | 100% | 2018-12-05 |  |  | 016-2018 | 2018-04-27 |  | 2018-05-10 | 2018-06-08 | 2018-08-03 | MAQUESERQ CONSTRUCTION & GEN. MDSE. | 3059883.65 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Ozamis City | 304169 | Pulot National High School | OZAMIS CITY | 2 |  | 1 | [5 empty] | 2548844.06 | UPGRADING | 2 | completed | 100% | 100% |  |  |  | 092-INFRA18-008 | 2018-08-16 | - | 2018-08-22 |  |  | EDTAHA BUILDERS, INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Tangub City | 304041 | Lorenzo Tan NHS | TANGUB CITY | 2 |  | 1 | [5 empty] | 2506678.54 | UPGRADING | 2 | ongoing | 80% | 80% |  |  |  |  | 2018-08-07 | 2018-08-20 | 2018-09-05 | 2018-09-08 | 2018-09-13 |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region X | Valencia City |  | Valencia City NHS | CITY OF VALENCIA | 4 |  | 1 | [5 empty] | 4667328.3 | UPGRADING | 2 | ongoing | 50% | 85% |  |  |  |  | 2018-06-08 | 2018-06-14 | 2018-07-02 | 2018-07-10 | 2018-08-07 |  | 4638510.61 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | suspended | Y
Region XI | Compostela Valley | 304205 | Nabunturan NCHS | NABUNTURAN (Capital) | 2 |  | 1 | [5 empty] | 4870283.68 | UPGRADING | 2 | ongoing | 95% | 98% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Compostela Valley | 304175 | Araibo NHS | PANTUKAN | 2 |  | 1 | [5 empty] | 1488006.88 | UPGRADING | 2 | COMPLETED | 99% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 304396 | Talomo National High School | DAVAO CITY | 1 |  | 1 | [5 empty] | 1136880.49 | UPGRADING | 2 | COMPLETED | 45% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Rebid | Y
Region XI | Davao City | 304376 | Mabini NHS | DAVAO CITY | 1 |  | 1 | [5 empty] | 525546.17 | UPGRADING | 2 | COMPLETED | 45% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Rebid | Y
Region XI | Davao City | 304377 | JESUS J. SORIANO NATIONAL HIGH SCHOOL | DAVAO CITY | 1 |  | 1 | [5 empty] | 6449590.2 | UPGRADING | 2 | COMPLETED | 65% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Rebid | Y
Region XI | Davao City | 316202 | Catalunan Pequeno National High School | DAVAO CITY | 1 |  | 1 | [5 empty] | 278196.92 | UPGRADING | 2 | COMPLETED | 35% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Rebid | Y
Region XI | Davao City | 304379 | Malabog National High School | DAVAO CITY | 2 |  | 1 | [5 empty] | 591519.51 | UPGRADING | 2 | ongoing | 30% | 35% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Rebid | Y
Region XI | Davao City | 304380 | Mandug NHS (Pablo Lorenzo NHS) | DAVAO CITY | 2 |  | 1 | [5 empty] | 412886.5 | UPGRADING | 2 | ongoing | 30% | 35% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Rebid | Y
Region XI | Davao City | 304364 | E. Ramos NHS | DAVAO CITY | 2 |  | 1 | [5 empty] | 317915.81 | UPGRADING | 2 | ongoing | 55% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Rebid | Y
Region XI | Davao City | 316201 | Bernardino B. Bosque NHS | DAVAO CITY | 2 |  | 1 | [5 empty] | 233327.26 | UPGRADING | 2 | ongoing | 30% | 35% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Rebid | Y
Region XI | Davao City | 304381 | Marilog High School of Agriculture (Tech-Voc School) | DAVAO CITY | 3 |  | 1 | [5 empty] | 695170.9 | UPGRADING | 2 | ongoing | 50% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Rebid | Y
Region XI | Davao City | 304387 | Mintal NCHS - Tugbok National HS | DAVAO CITY | 3 |  | 1 | [5 empty] | 370656.24 | UPGRADING | 2 | COMPLETED | 35% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Rebid | Y
Region XI | Davao City | 304355 | Wangan National High School | DAVAO CITY | 3 |  | 1 | [5 empty] | 515482.7 | UPGRADING | 2 | ongoing | 30% | 35% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Rebid | Y
Region XI | Davao City | 304386 | Sto. Niño National High School | DAVAO CITY | 3 |  | 1 | [5 empty] | 388721.87 | UPGRADING | 2 | COMPLETED | 55% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Rebid | Y
Region XI | Davao City | 304392 | Sirib NHS | DAVAO CITY | 3 |  | 1 | [5 empty] | 329202.03 | UPGRADING | 2 | ongoing | 55% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Rebid | Y
Region XI | Davao City | 304388 | Optaciano Hilay NHS | DAVAO CITY | 3 |  | 1 | [5 empty] | 291703.36 | UPGRADING | 2 | COMPLETED | 35% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Rebid | Y
Region XI | Davao City | 304382 | Marilog National High School | DAVAO CITY | 3 |  | 1 | [5 empty] | 380451.14 | UPGRADING | 2 | ongoing | 55% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Rebid | Y
Region XI | Davao City | 304342 | Ma. Cristina P. Belcar Agricultural High School | DAVAO CITY | 3 |  | 1 | [5 empty] | 331453.28 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Rebid | Y
Region XI | Davao City | 304373 | Los Amigos NHS | DAVAO CITY | 3 |  | 1 | [5 empty] | 256124.71 | UPGRADING | 2 | ongoing | 60% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Rebid | Y
Region XI | Davao City | 304395 | Emilio J. Estipona- Guinga NHS | DAVAO CITY | 3 |  | 1 | [5 empty] | 366616.43 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Rebid | Y
Region XI | Davao City | 304361 | Dona Carmen Denia NHS | DAVAO CITY | 3 |  | 1 | [5 empty] | 1150615.64 | UPGRADING | 2 | ongoing | 25% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Rebid | Y
Region XI | Davao City | 304350 | Binugao NHS | DAVAO CITY | 3 |  | 1 | [5 empty] | 499043.45 | UPGRADING | 2 | ongoing | 60% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Rebid | Y
Region XI | Davao City | 304348 | Talandang National High School | DAVAO CITY | 3 |  | 1 | [5 empty] | 699926.67 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Rebid | Y
Region XI | Davao City | 304394 | Tagakpan NHS | DAVAO CITY | 3 |  | 1 | [5 empty] | 292433.51 | UPGRADING | 2 | ongoing | 25% | 35% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Rebid | Y
Region XI | Davao Oriental | 304300 | Baganga NHS | BAGANGA | 1 |  | 1 | [5 empty] | 3765128.18 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao Oriental | 304311 | Cateel Vocational High School | CATEEL | 1 |  | 1 | [5 empty] | 4353915.65 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Digos City | 129771 | Ramon Magsaysay CES | CITY OF DIGOS (Capital) | 1 |  | 1 | [5 empty] | 1574224.53 | UPGRADING | 2 | completed | 100% | 100% | February 27, 2019 | February 27, 2019 | 18-04-059 | 18-04-059 | sept. 14-21, 2019 | sept.18, 2018 | sept. 21, 2018 | nov. 13, 2018 | Nov. 21, 2018 | NLC Construction and Supplies | 1566392.57 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Mati City | 304326 | Mati SAT | CITY OF MATI (Capital) | 2 |  | 1 | [5 empty] | 6004556.65 | UPGRADING | 2 | completed | 100% | 100% | 2019-01-24 |  |  |  | 2018-06-14 | 2018-05-29 | 2018-06-26 | 2018-07-10 | 2018-07-24 | MATT GLASS | 5944653.73 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Mati City | 304321 | Lupon NCHS | LUPON | 2 |  | 1 | [5 empty] | 2039801.11 | UPGRADING | 2 | completed | 100% | 100% | 2019-01-24 |  |  |  | 2018-06-14 | 2018-05-29 | 2018-06-26 | 2018-07-10 | 2018-07-24 | MATT GLASS | 2024474.47 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Mati City | 304319 | Lupon Vocational High School | LUPON | 2 |  | 1 | [5 empty] | 6223202.35 | UPGRADING | 2 | completed | 100% | 100% | 2019-01-24 |  |  |  | 2018-06-14 | 2018-05-29 | 2018-06-26 | 2018-07-10 | 2018-07-24 | MATT GLASS | 6186729.69 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Panabo City | 304405 | Don Manuel A. Javellana Memorial National High School | CITY OF PANABO | 2 |  | 1 | [5 empty] | 2086018.36 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Panabo City | 316401 | Southern Davao National High School | CITY OF PANABO | 2 |  | 1 | [5 empty] | 2972771.38 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Tagum City | 304231 | Jose Tuason Jr. Memorial National High School | CITY OF TAGUM (Capital) | 1 |  | 1 | [5 empty] | 884175.83 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Tagum City | 304232 | Pipisan Maug National High School | CITY OF TAGUM (Capital) | 1 |  | 1 | [5 empty] | 523181.14 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Tagum City | 322401 | Canocotan National High School | CITY OF TAGUM (Capital) | 1 |  | 1 | [5 empty] | 319590.45 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Tagum City | 500426 | PANDAPAN INTEGRATED SCHOOL | CITY OF TAGUM (Capital) | 1 |  | 1 | [5 empty] | 195718.99 | UPGRADING | 2 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XII | Cotabato City | 304634 | Notre Dame Village National High School | COTABATO CITY | 1 |  | 1 | [5 empty] | 4427334.88 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | General Santos City | 500302 | General Santos City SPED Integrated School | GENERAL SANTOS CITY (DADIANGAS) | 1 |  | 1 | [5 empty] | 2502091.86 | UPGRADING | 2 | completed |  | 100% | Oct. 21, 2018 | [5 empty] | May 15, 2018 |  | July 16, 2018 | Automatgeneric Trading and Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | General Santos City | 304646 | Gen. Santos City High School - Lanton High School Annex | GENERAL SANTOS CITY (DADIANGAS) | 1 |  | 1 | [5 empty] | 2029337.58 | UPGRADING | 2 | completed |  | 100% | Oct. 21, 2018 | Oct. 30, 2018 |  |  |  |  | May 15, 2018 |  | July 16, 2018 | Kupler Industries Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | General Santos City | 304650 | Labangal National High School (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 |  | 1 | [5 empty] | 2441996.22 | UPGRADING | 2 | completed |  | 100% | Oct. 21, 2018 | Oct. 30, 2018 |  |  |  |  | May 15, 2018 |  | July 16, 2018 | Kupler Industries Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | Kidapawan City | 304661 | Kidapawan City National High School | CITY OF KIDAPAWAN (Capital) | 2 |  | 1 | [5 empty] | 4189628.61 | UPGRADING | 2 | ongoing |  | 30% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2 |  | 1 | [5 empty] | 5136663.58 | UPGRADING | 2 | ongoing |  | 5% | January 24 2018 |  | GEPS 5410273 | I-2018-09-008 | June 8, 2018 | July 16, 2018 | July 30, 2018 | September 12, 2018 | September 24, 2018 | EC SOLICON BUILDERS | 4599881.29 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region XII | South Cotabato | 304559 | Poblacion Polomolok NHS | POLOMOLOK | 1 |  | 1 | [5 empty] | 9864781.29 | UPGRADING | 2 | completed | 40% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | South Cotabato | 304556 | Maltana NHS | TAMPAKAN | 1 |  | 1 | [5 empty] | 6800902.85 | UPGRADING | 2 | completed | 95% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region XII | Sultan Kudarat | 304597 | Lambayong National High School | LAMBAYONG (MARIANO MARCOS) | 1 |  | 1 | [5 empty] | 3336871.31 | UPGRADING | 2 | completed | 100% | 100% |  |  |  |  | Dec. 07, 2018 | Dec. 14, 2018 | Dec. 27, 2018 | Dec. 28, 2018 |  | 3K'S Industrial Maintenance and Services, Inc. | 2500055.17 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XII | Tacurong City | 304624 | Tacurong NHS | CITY OF TACURONG | 1 |  | 1 | [5 empty] | 4563975.22 | UPGRADING | 2 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CAR | Apayao | 135259 | Conner Central School | CONNER | 0 |  | 1 | [5 empty] | 976624.7 | UPGRADING | 3 | ongoing | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Apayao | 219020 | Mabiga Elementary School | CONNER | 0 |  | 1 | [5 empty] | 398700.3 | UPGRADING | 3 | ongoing | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | N
CAR | Apayao | 305112 | Conner Natl. HS | CONNER | 0 |  | 1 | [5 empty] | 1317860.01 | UPGRADING | 3 | ongoing | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Apayao | 305114 | Gov. Benjamin Leguiab, Sr. Mem. NHS Main | CONNER | 0 |  | 1 | [5 empty] | 1162205.15 | UPGRADING | 3 | ongoing | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Apayao | 318802 | Conner Central NHS Talifugo Annex | CONNER | 0 |  | 1 | [5 empty] | 1282984.59 | UPGRADING | 3 | ongoing | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Apayao | 318812 | Conner Central NHS Ili Annex | CONNER | 0 |  | 1 | [5 empty] | 1253305.67 | UPGRADING | 3 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
CAR | Apayao | 135287 | Balasi Elementary School | FLORA | 0 |  | 1 | [5 empty] | 739360.4 | UPGRADING | 3 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
CAR | Apayao | 135289 | Flora CS | FLORA | 0 |  | 1 | [5 empty] | 1214859.9 | UPGRADING | 3 | ongoing | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Apayao | 135294 | Mallig ES | FLORA | 0 |  | 1 | [5 empty] | 723531.26 | UPGRADING | 3 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
CAR | Apayao | 135336 | Luna CS | LUNA | 0 |  | 1 | [5 empty] | 1314374.58 | UPGRADING | 3 | ongoing | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Apayao | 135356 | Mataguisi ES | PUDTOL | 0 |  | 1 | [5 empty] | 513708.94 | UPGRADING | 3 | COMPLETED | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
CAR | Apayao | 135357 | Pudtol CS | PUDTOL | 0 |  | 1 | [5 empty] | 1415078.72 | UPGRADING | 3 | ongoing | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Apayao | 318810 | Swan National Agricultural and Trade High School | PUDTOL | 0 |  | 1 | [5 empty] | 1224974.42 | UPGRADING | 3 | ongoing | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Apayao | 305124 | Sipa-Imelda NHS | SANTA MARCELA | 0 |  | 1 | [5 empty] | 1368646.52 | UPGRADING | 3 | ongoing | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CAR | Apayao | 318805 | CONSUELO NATIONAL HIGH SCHOOL | SANTA MARCELA | 0 |  | 1 | [5 empty] | 1280614.31 | UPGRADING | 3 | ongoing | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
CARAGA | Siargao | 304782 | San Isidro National High School | SAN ISIDRO | 1 |  | 1 | [5 empty] | 3050000 | UPGRADING | 3 | awaiting for energization of Elec. Coop | 95% | 95% | 95% | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Y
CARAGA | Siargao | 304785 | Sapao National High School | SANTA MONICA (SAPAO) | 1 |  | 1 | [5 empty] | 3050000 | UPGRADING | 3 | awaiting for energization of Elec. Coop | 95% | 95% | 95% | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Y
CARAGA | Siargao | 132224 | Socorro Central Elementary School and SPED Center | SOCORRO | 1 |  | 1 | [5 empty] | 3000000 | UPGRADING | 3 | awaiting for energization of Elec. Coop | 95% | 95% | 95% | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Y
CARAGA | Siargao | 304788 | SOCORRO NATIONAL HIGH SCHOOL | SOCORRO | 1 |  | 1 | [5 empty] | 3700000 | UPGRADING | 3 | awaiting for energization of Elec. Coop | 95% | 95% | 95% | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Y
CARAGA | Siargao | 304790 | Pamosaingan National High School | SOCORRO | 1 |  | 1 | [5 empty] | 3050000 | UPGRADING | 3 | awaiting for energization of Elec. Coop | 95% | 95% | 95% | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Y
CARAGA | Surigao City | 304795 | Ipil NHS | SURIGAO CITY (Capital) | 2 |  | 1 | [5 empty] | 1348769.53 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For Award
CARAGA | Surigao City | 317701 | Taft NHS | SURIGAO CITY (Capital) | 2 |  | 1 | [5 empty] | 987826.51 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For Award
CARAGA | Surigao City | 317704 | Lipata National High School | SURIGAO CITY (Capital) | 2 |  | 1 | [5 empty] | 953359.27 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | For Award
CARAGA | Surigao del Norte | 340416 | Alegria Stand Alone Senior High School | ALEGRIA | 2 |  | 1 | [5 empty] | 1657085.43 | UPGRADING | 3 | completed | 80% | 100% | 2019-02-20 |  |  | 025-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 132460 | Malimono Central Elementary School | MALIMONO | 2 |  | 1 | [5 empty] | 1593266.33 | UPGRADING | 3 | completed | 80% | 100% | 2019-02-20 |  |  | 026-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 304833 | Malimono NHS | MALIMONO | 2 |  | 1 | [5 empty] | 1943819.1 | UPGRADING | 3 | completed | 80% | 100% | 2019-02-20 |  |  | 027-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 132478 | Placer Central Elementary School | PLACER | 2 |  | 1 | [5 empty] | 1493969.85 | UPGRADING | 3 | completed | 80% | 100% | 2019-02-20 |  |  | 028-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 132479 | Placer West CES | PLACER | 2 |  | 1 | [5 empty] | 1405226.13 | UPGRADING | 3 | completed | 80% | 100% | 2019-03-29 |  |  | 031-2018 | 2018-11-30 | 2018-12-07 | 2018-12-21 | 2018-12-27 | 2018-12-29 | RCDG Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 132482 | Sta Cruz ES | PLACER | 2 |  | 1 | [5 empty] | 1627085.43 | UPGRADING | 3 | completed | 80% | 100% | 2019-02-20 |  |  | 029-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 132331 | Anao-aon CES | SAN FRANCISCO (ANAO-AON) | 2 |  | 1 | [5 empty] | 1582814.07 | UPGRADING | 3 | completed | 80% | 100% | 2019-02-20 |  |  | 030-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
CARAGA | Surigao del Norte | 304850 | Mayag National High School | SISON | 2 |  | 1 | [5 empty] | 1858090.45 | UPGRADING | 3 | Completed | 100% | 100% | 2019-03-29 |  |  | 032-2018 | 2018-11-30 | 2018-12-07 | 2018-11-07 | 2018-12-27 | 2018-12-29 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
NCR | Paranaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 |  | 1 | [5 empty] | 6470050.58 | UPGRADING | 3 | completed | 60% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
NCR | Taguig | 305464 | Tipas National High School | TAGUIG CITY | 1 |  | 1 | [5 empty] | 2626512.25 | UPGRADING | 3 | completed | 60% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | San Carlos City | 500059 | Agdao Integrated School | SAN CARLOS CITY | 3 |  | 1 | [5 empty] | 1427586.4 | UPGRADING | 3 | ongoing | 20% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | San Carlos City | 300384 | Mabalbalino NHS | SAN CARLOS CITY | 3 |  | 1 | [5 empty] | 1187919.87 | UPGRADING | 3 | ongoing | 27% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region I | San Carlos City | 300389 | Tamayo National High School | SAN CARLOS CITY | 3 |  | 1 | [5 empty] | 1252621.19 | UPGRADING | 3 | completed | 20% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region I | San Carlos City | 500057 | Tarece Integrated School | SAN CARLOS CITY | 3 |  | 1 | [5 empty] | 1996698.46 | UPGRADING | 3 | ongoing |  | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region II | Isabela | 103145 | Cabagan Science Elementary School | CABANGAN | 1 |  | 1 | [5 empty] | 868239.54 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 103269 | Delfin Albano Central School | DELFIN ALBANO (MAGSAYSAY) | 1 |  | 1 | [5 empty] | 3325977.82 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 300587 | Ragan Sur National High School | DELFIN ALBANO (MAGSAYSAY) | 1 |  | 1 | [5 empty] | 2637011.33 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 306133 | Aneg National High School | DELFIN ALBANO (MAGSAYSAY) | 1 |  | 1 | [5 empty] | 995822.45 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 306162 | Bayabo Integrated School | DELFIN ALBANO (MAGSAYSAY) | 1 |  | 1 | [5 empty] | 1046855.62 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 103554 | Divilacan Central School | DIVILACAN | 1 |  | 1 | [5 empty] | 2574707.64 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 103854 | Sta. Maria Central School | SANTA MARIA | 1 |  | 1 | [5 empty] | 1992023.28 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 300605 | Buenaventura G. Masigan National High School | SANTA MARIA | 1 |  | 1 | [5 empty] | 1382139.14 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 103871 | Sto. Tomas Central School | SANTO TOMAS | 1 |  | 1 | [5 empty] | 1190764.76 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 103884 | Tumauini North Central School | TUMAUINI | 1 |  | 1 | [5 empty] | 1896448.69 | UPGRADING | 3 | completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 103903 | Tumauini South Central School | TUMAUINI | 1 |  | 1 | [5 empty] | 2222813.05 | UPGRADING | 3 | completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 103904 | Tumauini West Central School | TUMAUINI | 1 |  | 1 | [5 empty] | 1898495.2 | UPGRADING | 3 | completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 300547 | Antagan National High School | TUMAUINI | 1 |  | 1 | [5 empty] | 2155606.72 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 300551 | Lanna National High School | TUMAUINI | 1 |  | 1 | [5 empty] | 2321207.03 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 300556 | Lalauanan National High School | TUMAUINI | 1 |  | 1 | [5 empty] | 2201117.74 | UPGRADING | 3 | completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 306109 | Fermeldy National High School | TUMAUINI | 1 |  | 1 | [5 empty] | 2709258.71 | UPGRADING | 3 | completed | 90% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 103072 | Aurora Central School | AURORA | 2 |  | 1 | [5 empty] | 1176056.83 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 103102 | Benito Soliven Central School | BENITO SOLIVEN | 2 |  | 1 | [5 empty] | 1012396.63 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 500019 | Yeban Integrated School | BENITO SOLIVEN | 2 |  | 1 | [5 empty] | 1414672.6 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 500072 | Villaluz Integrated School | BENITO SOLIVEN | 2 |  | 1 | [5 empty] | 896259.08 | UPGRADING | 3 | completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 500079 | Maluno Integrated School - Main | BENITO SOLIVEN | 2 |  | 1 | [5 empty] | 1468714.47 | UPGRADING | 3 | completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 103128 | Burgos Central School | BURGOS | 2 |  | 1 | [5 empty] | 1153599.18 | UPGRADING | 3 | completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 103343 | Gamu Central School | GAMU | 2 |  | 1 | [5 empty] | 1113294.27 | UPGRADING | 3 | completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 300559 | Mabini National High School | GAMU | 2 |  | 1 | [5 empty] | 1639894.93 | UPGRADING | 3 | COMPLETED | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 103496 | Mallig Central School - Main | MALLIG | 2 |  | 1 | [5 empty] | 1628332.69 | UPGRADING | 3 | completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 103520 | Naguilian Central School | NAGUILIAN | 2 |  | 1 | [5 empty] | 2080920.05 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 103571 | Quezon CS | QUEZON | 2 |  | 1 | [5 empty] | 2092542.49 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 306112 | Barucboc National High School | QUEZON | 2 |  | 1 | [5 empty] | 1222637.7 | UPGRADING | 3 | completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 500071 | San Juan Integrated School | QUEZON | 2 |  | 1 | [5 empty] | 872096.39 | UPGRADING | 3 | completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 103580 | Quirino Central School | QUIRINO | 2 |  | 1 | [5 empty] | 1860295.48 | UPGRADING | 3 | completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 500068 | Villa Cacho Integrated School | QUIRINO | 2 |  | 1 | [5 empty] | 1736088.03 | UPGRADING | 3 | ongoing | 80% | 100% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0
Region II | Isabela | 500086 | Dicamay Integrated School | SAN MARIANO | 2 |  | 1 | [5 empty] | 964475.61 | UPGRADING | 3 | completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 300593 | Alibadabad National High School | SAN MARIANO | 2 |  | 1 | [5 empty] | 430415.85 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 500020 | Lomboy Integrated School | ANGADANAN | 3 |  | 1 | [5 empty] | 876175.06 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 103624 | Reina Mercedes Central School | REINA MERCEDES | 3 |  | 1 | [5 empty] | 974739.09 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region II | Isabela | 103600 | Gen. Aguinaldo ES - Villa Verde PS Annex | RAMON | 4 |  | 1 | [5 empty] | 939585.17 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region III | Bulacan | 300742 | Guiguinto Nat'l Voc'l. High School | GUIGUINTO | 2 |  | 1 | [5 empty] | 6709671.39 | UPGRADING | 3 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 281503 | Palis Elementary School | BOTOLAN | 2 |  | 1 | [5 empty] | 1790672.54 | UPGRADING | 3 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 101788 | Owaog-Nebloc Elementary School | BOTOLAN | 2 |  | 1 | [5 empty] | 1963474.05 | UPGRADING | 3 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 281505 | Moraza Elementary School | BOTOLAN | 2 |  | 1 | [5 empty] | 1979019.54 | UPGRADING | 3 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 106891 | Inhobol Elementary School | MASINLOC | 2 |  | 1 | [5 empty] | 432186.19 | UPGRADING | 3 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 301007 | Coto High School | MASINLOC | 2 |  | 1 | [5 empty] | 524075.44 | UPGRADING | 3 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 106884 | Felipe E. Estella Elementary School | MASINLOC | 2 |  | 1 | [5 empty] | 502782.07 | UPGRADING | 3 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 307104 | San Rafael Technical Vocational High School | SAN FELIPE | 2 |  | 1 | [5 empty] | 551263.58 | UPGRADING | 3 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region III | Zambales | 301021 | Gov. Manuel D. Barretto National High School | SAN FELIPE | 2 |  | 1 | [5 empty] | 562157.84 | UPGRADING | 3 | Completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IX | Pagadian City | 126086 | Banale ES | PAGADIAN CITY (Capital) | 1 |  | 1 | [5 empty] | 637234.95 | UPGRADING | 3 | completed | 95% | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE | 633785.58 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IX | Pagadian City | 126037 | Bogo ES | PAGADIAN CITY (Capital) | 1 |  | 1 | [5 empty] | 616609.25 | UPGRADING | 3 | completed | 95% | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE | 611977.36 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IX | Pagadian City | 126060 | Bulatok ES | PAGADIAN CITY (Capital) | 1 |  | 1 | [5 empty] | 709967.65 | UPGRADING | 3 | completed | 95% | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE | 702771.47 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IX | Pagadian City | 126039 | Danlugan ES | PAGADIAN CITY (Capital) | 1 |  | 1 | [5 empty] | 690065.67 | UPGRADING | 3 | completed | 95% | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE | 683848.14 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IX | Pagadian City | 126050 | Kawit ES | PAGADIAN CITY (Capital) | 1 |  | 1 | [5 empty] | 964515.41 | UPGRADING | 3 | completed | 95% | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE | 956340.56 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IX | Pagadian City | 126075 | Napolan ES | PAGADIAN CITY (Capital) | 1 |  | 1 | [5 empty] | 724441.83 | UPGRADING | 3 | completed | 95% | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE | 719003.36 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IX | Pagadian City | 303908 | Pagadian City NHS | PAGADIAN CITY (Capital) | 1 |  | 1 | [5 empty] | 1614991.95 | UPGRADING | 3 | completed | 95% | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE | 1595444.32 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IX | Pagadian City | 198502 | Rotary Inner Wheel Village Elementary School | PAGADIAN CITY (Capital) | 1 |  | 1 | [5 empty] | 683190.44 | UPGRADING | 3 | completed | 95% | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE | 675872.5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IX | Pagadian City | 126052 | San Pedro Central Elementary School | PAGADIAN CITY (Capital) | 1 |  | 1 | [5 empty] | 802766.55 | UPGRADING | 3 | completed | 95% | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE | 798127.74 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IX | Pagadian City | 126079 | Sta. Lucia Central Elementary School | PAGADIAN CITY (Capital) | 1 |  | 1 | [5 empty] | 847998.33 | UPGRADING | 3 | completed | 95% | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE | 840631.43 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region IX | Pagadian City | 126054 | Tawagan Sur Elementary School | PAGADIAN CITY (Capital) | 1 |  | 1 | [5 empty] | 762798.38 | UPGRADING | 3 | completed | 95% | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE | 754866.03 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region V | Masbate City | 113695 | Jose Zurbito Sr. Elementary School | CITY OF MASBATE (Capital) | 2 |  | 1 | [5 empty] | 1472274.9 | UPGRADING | 3 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VI | Capiz | 115552 | Dominador T. Esmeralda ES | MA-AYON | 1 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115553 | Cabungahan Elementary School | MA-AYON | 1 |  | 1 | [5 empty] | 682466.98 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115554 | Canapian ES | MA-AYON | 1 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115555 | Carataya ES | MA-AYON | 1 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115557 | East Villaflores ES | MA-AYON | 1 |  | 1 | [5 empty] | 682466.98 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115558 | Fernandez ES | MA-AYON | 1 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115560 | Ilawod Elementary School | MA-AYON | 1 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115561 | Indayagan PS | MA-AYON | 1 |  | 1 | [5 empty] | 511754.5 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115562 | Jebaca ES | MA-AYON | 1 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115563 | Maalan Primary School | MA-AYON | 1 |  | 1 | [5 empty] | 511754.5 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115564 | Maayon ES | MA-AYON | 1 |  | 1 | [5 empty] | 849437.03 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115565 | Manayupit ES | MA-AYON | 1 |  | 1 | [5 empty] | 570194.02 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115566 | New Guia ES | MA-AYON | 1 |  | 1 | [5 empty] | 794739.95 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115567 | Old Guia PS | MA-AYON | 1 |  | 1 | [5 empty] | 540542.44 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115568 | Palaguian ES | MA-AYON | 1 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115569 | Parallan Elementary School | MA-AYON | 1 |  | 1 | [5 empty] | 653679.04 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115570 | Piña ES | MA-AYON | 1 |  | 1 | [5 empty] | 570194.02 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115571 | Quevedo ES (ngalan es) | MA-AYON | 1 |  | 1 | [5 empty] | 765952.01 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115572 | Quinabonglan ES | MA-AYON | 1 |  | 1 | [5 empty] | 932922.06 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115573 | Quinat-uyan ES | MA-AYON | 1 |  | 1 | [5 empty] | 765952.01 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115574 | Salgan ES | MA-AYON | 1 |  | 1 | [5 empty] | 682466.98 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115575 | Tapulang Elementary School | MA-AYON | 1 |  | 1 | [5 empty] | 653679.04 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115576 | Tepacla ES | MA-AYON | 1 |  | 1 | [5 empty] | 682466.98 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115577 | Tuburan ES | MA-AYON | 1 |  | 1 | [5 empty] | 682466.98 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115578 | West Villaflores ES | MA-AYON | 1 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115713 | Cubay-Ibaca ES | PRESIDENT ROXAS | 1 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115711 | DOMINGO M. LOCSIN ES (CABUGCABUG) | PRESIDENT ROXAS | 1 |  | 1 | [5 empty] | 682466.98 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115714 | Goce ES | PRESIDENT ROXAS | 1 |  | 1 | [5 empty] | 682466.98 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115715 | Madulano ES | PRESIDENT ROXAS | 1 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115716 | Manoling ES | PRESIDENT ROXAS | 1 |  | 1 | [5 empty] | 682466.98 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115717 | Marita ES | PRESIDENT ROXAS | 1 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115718 | Pandan ES | PRESIDENT ROXAS | 1 |  | 1 | [5 empty] | 682466.98 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115719 | Pondol ES | PRESIDENT ROXAS | 1 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115720 | Pres. Roxas East ES | PRESIDENT ROXAS | 1 |  | 1 | [5 empty] | 904134.12 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115721 | Pres. Roxas West Elementary School | PRESIDENT ROXAS | 1 |  | 1 | [5 empty] | 653679.04 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115722 | Quiajo ES | PRESIDENT ROXAS | 1 |  | 1 | [5 empty] | 656557.83 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115723 | Sangkal ES | PRESIDENT ROXAS | 1 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115724 | Vedasto T. Javellosa ES | PRESIDENT ROXAS | 1 |  | 1 | [5 empty] | 682466.98 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115416 | Bun-od Primary School | CUARTERO | 2 |  | 1 | [5 empty] | 511754.5 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115417 | Carataya ES (cuartero) | CUARTERO | 2 |  | 1 | [5 empty] | 682466.98 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115418 | Cuartero CES | CUARTERO | 2 |  | 1 | [5 empty] | 765952.01 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115419 | Lunayan E/S | CUARTERO | 2 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115420 | Mahabang Sapa PS | CUARTERO | 2 |  | 1 | [5 empty] | 540542.44 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115421 | Mahunodhunod ES | CUARTERO | 2 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115422 | Maindang Elementary School | CUARTERO | 2 |  | 1 | [5 empty] | 682466.98 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115423 | Mainit Elementary School | CUARTERO | 2 |  | 1 | [5 empty] | 682466.98 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115424 | Malagab-i ES | CUARTERO | 2 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115425 | Nagba ES | CUARTERO | 2 |  | 1 | [5 empty] | 682466.98 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115426 | Putian ES | CUARTERO | 2 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115427 | San Antonio ES (Cuartero) | CUARTERO | 2 |  | 1 | [5 empty] | 708376.13 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115428 | SINABSABAN ELEMENTARY SCHOOL | CUARTERO | 2 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115415 | Vicente F. Fabuna ES (Bito-on Ilaya) | CUARTERO | 2 |  | 1 | [5 empty] | 653679.04 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115441 | Manhoy ES | DAO | 2 |  | 1 | [5 empty] | 682466.98 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115442 | Mapulang Bato Primary School | DAO | 2 |  | 1 | [5 empty] | 540542.44 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115443 | Matagnop Elementary School | DAO | 2 |  | 1 | [5 empty] | 765952.01 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115436 | Nicanor Escutin ES | DAO | 2 |  | 1 | [5 empty] | 765952.01 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115446 | Quinayuya Elementary School | DAO | 2 |  | 1 | [5 empty] | 598981.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Capiz | 115447 | Tabuc ES | DAO | 2 |  | 1 | [5 empty] | 737164.07 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | Under Procurement | [13 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Region VI | Roxas City | 117652 | Barra ES | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 950120.23 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 117654 | Culasi ES | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 955368.14 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 311704 | Don Ynocencio A. Del Rosario National High School formerly Tanque NHS-Dayao Extension | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 988944.69 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 117661 | Pres. Manuel Roxas MS - North | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 889037.46 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 117662 | Pres. Manuel Roxas MS - South | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 890228.23 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 117666 | Banica Elementary School | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 869082.18 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 117667 | Don Amando Bayot, Sr. MS | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 869435.16 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 117685 | Lawa-an ES | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 1104086.97 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 117686 | Loctugan ES | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 986563.15 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 117689 | Venancio Alba ES | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 884274.36 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VI | Roxas City | 500195 | Sofronio A. Cordovero Integrated School | ROXAS CITY (Capital) | 1 |  | 1 | [5 empty] | 913755.83 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed |  | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Region VIII | Leyte | 313398 | Borseth National High School | ALANGALANG | 1 |  | 1 | [5 empty] | 1190462.69 | UPGRADING | 3 | completed | 90% | 100% | [9 empty] | FM4 BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 121736 | Anahaway Elementary School | PALO | 1 |  | 1 | [5 empty] | 591708.82 | UPGRADING | 3 | completed | 90% | 100% | [9 empty] | FOUR K BUILDERS & CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121738 | Canhidoc Elementary School | PALO | 1 |  | 1 | [5 empty] | 666114.39 | UPGRADING | 3 | completed | 40% | 100% | [9 empty] | LJPM BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121739 | Capirawan Elementary School | PALO | 1 |  | 1 | [5 empty] | 610371.35 | UPGRADING | 3 | completed | 90% | 100% | [9 empty] | FOUR K BUILDERS & CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121740 | Castilla ElementarySchool | PALO | 1 |  | 1 | [5 empty] | 586218.65 | UPGRADING | 3 | completed | 40% | 100% | [9 empty] | CAFRENCILLO ARCH DESIGN & BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121741 | Gacao Elementary School | PALO | 1 |  | 1 | [5 empty] | 622190.03 | UPGRADING | 3 | completed | 90% | 100% | [9 empty] | FOUR K BUILDERS & CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121742 | Luntad Elementary School | PALO | 1 |  | 1 | [5 empty] | 772659.86 | UPGRADING | 3 | completed | 40% | 100% | [9 empty] | LJPM BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121743 | Palo I Central School | PALO | 1 |  | 1 | [5 empty] | 2496173.72 | UPGRADING | 3 | completed | 40% | 100% | [9 empty] | HD GOLDEN BUILDERS & SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 121744 | Salvacion Elementary School | PALO | 1 |  | 1 | [5 empty] | 399138.7 | UPGRADING | 3 | completed | 40% | 100% | [9 empty] | LJPM BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 303339 | Anahaway National High School | PALO | 1 |  | 1 | [5 empty] | 1277292.87 | UPGRADING | 3 | completed | 80% | 100% | [9 empty] | CAFRENCILLO ARCH DESIGN & BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 121946 | Burak Elementary School | TOLOSA | 1 |  | 1 | [5 empty] | 897652.53 | UPGRADING | 3 | completed | 100% | 100% | [9 empty] | BENCH CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121950 | Daniel Z. Romualdez Memorial Elementary School | TOLOSA | 1 |  | 1 | [5 empty] | 945617.42 | UPGRADING | 3 | completed | 100% | 100% | [9 empty] | BENCH CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121957 | Telegrafo Elementary School | TOLOSA | 1 |  | 1 | [5 empty] | 750365.63 | UPGRADING | 3 | completed | 100% | 100% | [9 empty] | BENCH CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121154 | Burauen North Central School | BARAUEN | 2 |  | 1 | [5 empty] | 914305.38 | UPGRADING | 3 | completed | 100% | 100% | [9 empty] | H.A.H REVERIE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121177 | Toloyao Elementary School | BARAUEN | 2 |  | 1 | [5 empty] | 513506.71 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121179 | Villa Rosas Elementary School | BARAUEN | 2 |  | 1 | [5 empty] | 855843.81 | UPGRADING | 3 | completed | 40% | 100% | [9 empty] | H.A.H REVERIE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121181 | Arado Elementary School | BARAUEN | 2 |  | 1 | [5 empty] | 575754.28 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121185 | Burauen South Central School | BARAUEN | 2 |  | 1 | [5 empty] | 766640.52 | UPGRADING | 3 | completed | 100% | 100% | [9 empty] | AGB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121199 | Paghudlan Elementary School | BARAUEN | 2 |  | 1 | [5 empty] | 795067.68 | UPGRADING | 3 | completed | 100% | 100% | [9 empty] | AGB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121205 | San Isidro Elementary School | BARAUEN | 2 |  | 1 | [5 empty] | 567475.63 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 303357 | Calingcaguing National High School | BARUGO | 2 |  | 1 | [5 empty] | 1213545.38 | UPGRADING | 3 | completed | 86% | 100% | [9 empty] | FM4 BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303433 | Sta. Rosa National High School | BARUGO | 2 |  | 1 | [5 empty] | 1876187.49 | UPGRADING | 3 | ongoing | 86% | 86% | [9 empty] | FM4 BUILDERS |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VIII | Leyte | 313324 | Barugo National High School | BARUGO | 2 |  | 1 | [5 empty] | 2013502.03 | UPGRADING | 3 | ongoing | 86% | 86% | [9 empty] | FM4 BUILDERS |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VIII | Leyte | 303418 | Pinamopoan National High School | CAPOOCAN | 2 |  | 1 | [5 empty] | 1328911.74 | UPGRADING | 3 | completed | 87% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 121319 | Bulod Elementary School | DULAG | 2 |  | 1 | [5 empty] | 589524.03 | UPGRADING | 3 | completed | 100% | 100% | [9 empty] | J. CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121320 | Cabatoan Elementary School | DULAG | 2 |  | 1 | [5 empty] | 994077.4 | UPGRADING | 3 | completed | 100% | 100% | [9 empty] | CAFRENCILLO ARCH DESIGN & BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121321 | Calipayan Elementary School | DULAG | 2 |  | 1 | [5 empty] | 576756.16 | UPGRADING | 3 | completed | 80% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121331 | San Agustin Elementary School | DULAG | 2 |  | 1 | [5 empty] | 807290.52 | UPGRADING | 3 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121336 | Tabu Elementary School | DULAG | 2 |  | 1 | [5 empty] | 577762.85 | UPGRADING | 3 | completed | 100% | 100% | [9 empty] | CAFRENCILLO ARCH DESIGN & BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121337 | Tigbao Elementary School | DULAG | 2 |  | 1 | [5 empty] | 984888.74 | UPGRADING | 3 | completed | 100% | 100% | [9 empty] | PALMERA BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121350 | RIZAL ELEMENTARY SCHOOL | DULAG | 2 |  | 1 | [5 empty] | 758435.92 | UPGRADING | 3 | completed | 100% | 100% | [9 empty] | PALMERA BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 121353 | San Miguel Elementary School | DULAG | 2 |  | 1 | [5 empty] | 748968.36 | UPGRADING | 3 | completed | 100% | 100% | [9 empty] | PALMERA BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | N
Region VIII | Leyte | 303355 | Cabacungan National High School | DULAG | 2 |  | 1 | [5 empty] | 1333806.21 | UPGRADING | 3 | completed | 75% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303434 | Tabango National High School | TABANGO | 3 |  | 1 | [5 empty] | 1241888.42 | UPGRADING | 3 | ongoing | 75% | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VIII | Leyte | 313306 | Palompon National High School | PALOMPON | 4 |  | 1 | [5 empty] | 1962688.7 | UPGRADING | 3 | completed | 80% | 100% | [9 empty] | BCG DESIGN & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 313315 | San Guillermo National High School | PALOMPON | 4 |  | 1 | [5 empty] | 1547694.85 | UPGRADING | 3 | completed | 100% | 100% | [9 empty] | J. CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303373 | Hampipila National High School | ABUYOG | 5 |  | 1 | [5 empty] | 1345005.47 | UPGRADING | 3 | completed | 75% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303365 | Concepcion National High School | HILONGOS | 5 |  | 1 | [5 empty] | 1493207.13 | UPGRADING | 3 | completed | 100% | 100% | [9 empty] | JAMT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 303431 | Sta. Margarita National High School | HILONGOS | 5 |  | 1 | [5 empty] | 1978115.07 | UPGRADING | 3 | ongoing | 75% | 80% | [9 empty] | JAMT CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VIII | Leyte | 303379 | Javier National High School | JAVIER (BUGHO) | 5 |  | 1 | [5 empty] | 1504649.55 | UPGRADING | 3 | completed | 90% | 100% | [9 empty] | VITHS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Leyte | 313337 | Sta. Paz Integrated School | MATALOM | 5 |  | 1 | [5 empty] | 1898479.64 | UPGRADING | 3 | ongoing | 75% | 80% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region VIII | Ormoc City | 124150 | Dolores Elementary School | ORMOC CITY | 4 |  | 1 | [5 empty] | 2493754.39 | UPGRADING | 3 | completed | 87% | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C1 | 2018-BEFF-E-B3-C1 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | NV and C Construction and General Supply | 4495169.05 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124151 | Don Carlos Rivilla Elemetary School | ORMOC CITY | 4 |  | 1 | [5 empty] | 1282939.18 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed | 67% | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C2 | 2018-BEFF-E-B3-C2 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction | 3962356.38 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124152 | Donghol Elementary School | ORMOC CITY | 4 |  | 1 | [5 empty] | 1883203.55 | UPGRADING | 3 | completed | 76% | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C5 | 2018-BEFF-E-B3-C5 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction | 3552520.68 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124153 | Gaas Elementary School | ORMOC CITY | 4 |  | 1 | [5 empty] | 1277662.8 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed | 75% | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C1 | 2018-BEFF-E-B3-C1 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | NV and C Construction and General Supply | 4495169.05 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124155 | Ipil Central School | ORMOC CITY | 4 |  | 1 | [5 empty] | 2878625.57 | UPGRADING | 3 | completed | 89% | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C2 | 2018-BEFF-E-B3-C2 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction | 3962356.38 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124160 | Mabini Elementary School | ORMOC CITY | 4 |  | 1 | [5 empty] | 1293491.95 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed | 67% | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C2 | 2018-BEFF-E-B3-C2 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction | 3962356.38 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124167 | Patag Elementary School | ORMOC CITY | 4 |  | 1 | [5 empty] | 1379888.1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed | 67% | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C5 | 2018-BEFF-E-B3-C5 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction | 3552520.68 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124177 | Concepcion Elementary School | Ormoc City | 4 |  | 1 | [5 empty] | 1478463.34 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed | 67% | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C6 | 2018-BEFF-E-B3-C6 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. | 3602646.96 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124178 | Guintiguian Elementary School | Ormoc City | 4 |  | 1 | [5 empty] | 1582314.96 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed | 67% | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C3 | 2018-BEFF-E-B3-C3 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. | 4614565.47 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124184 | Manlilinao Elementary School | Ormoc City | 4 |  | 1 | [5 empty] | 1592867.72 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed | 67% | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C6 | 2018-BEFF-E-B3-C6 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. | 3602646.96 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124190 | San Jose Elementary School | Ormoc City | 4 |  | 1 | [5 empty] | 1774189.06 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed | 70% | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C3 | 2018-BEFF-E-B3-C3 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. | 4614565.47 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124193 | Valencia Central School | Ormoc City | 4 |  | 1 | [5 empty] | 2459994.63 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | completed | 75% | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C3 | 2018-BEFF-E-B3-C3 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. | 4614565.47 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124195 | Linao Central School | Ormoc City | 4 |  | 1 | [5 empty] | 3128610.73 | UPGRADING | 3 | completed | 100% | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C4 | 2018-BEFF-E-B3-C4 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Tubigan Builders | 5180301.57 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124196 | Naungan Elementary School | Ormoc City | 4 |  | 1 | [5 empty] | 2124989.86 | UPGRADING | 3 | completed | 100% | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C4 | 2018-BEFF-E-B3-C4 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Tubigan Builders | 5180301.57 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124197 | Ormoc City SPED Center | Ormoc City | 4 |  | 1 | [5 empty] | 1628071.74 | UPGRADING | 3 | completed | 87% | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C5 | 2018-BEFF-E-B3-C5 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction | 3552520.68 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124202 | Cabintan Elementary School | Ormoc City | 4 |  | 1 | [5 empty] | 1293491.95 | UPGRADING | 3 | completed | 67% | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C1 | 2018-BEFF-E-B3-C1 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | NV and C Construction and General Supply | 4495169.04 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region VIII | Ormoc City | 124207 | Doña Feliza Z. Mejia Elementary School | Ormoc City | 4 |  | 1 | [5 empty] | 1480326.64 | UPGRADING | 3 | completed | 67% | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C6 | 2018-BEFF-E-B3-C6 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. | 3602646.96 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region X | Tangub City | 304171 | Tangub City NHS | TANGUB CITY | 2 |  | 1 | [5 empty] | 3504891.44 | UPGRADING | 3 | ongoing | 20% | 75% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Davao del Norte | 304252 | Sonlon NHS | ASUNCION (SAUG) | 1 |  | 1 | [5 empty] | 4621351.67 | UPGRADING | 3 | completed | 98% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
NCR | Quezon City | 136540 | Pres. Corazon C. Aquino E/S | QUEZON CITY | 2 |  | 1 | [5 empty] | 1744063.97 | UPGRADING | 4 | completed | 30% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 129557 | Kapt. T. Monteverde Sr. CES | DAVAO CITY | 1 |  | 1 | [5 empty] | 6321696.54 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 129711 | A. Mabini Elementary School | DAVAO CITY | 1 |  | 1 | [5 empty] | 3755429.04 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 129554 | Bolton ES | DAVAO CITY | 1 |  | 1 | [5 empty] | 3370166.21 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 129531 | Calinan Central ES | DAVAO CITY | 3 |  | 1 | [5 empty] | 4522920.58 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 304354 | Calinan NHS | DAVAO CITY | 3 |  | 1 | [5 empty] | 2924771.08 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 129715 | Catalunan Grande ES | DAVAO CITY | 1 |  | 1 | [5 empty] | 2693686.59 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 129716 | Catalunan Pequeño Elementary School | DAVAO CITY | 1 |  | 1 | [5 empty] | 1880086.11 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 316202 | Catalunan Pequeno National High School | DAVAO CITY | 1 |  | 1 | [5 empty] | 2342306.55 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 304356 | CROSSING BAYABAS NHS | DAVAO CITY | 3 |  | 1 | [5 empty] | 3392495.11 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 304359 | Daniel R. Aguinaldo NHS (Matina NHS) | DAVAO CITY | 1 |  | 1 | [5 empty] | 3012928.03 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 304360 | Davao City NHS | DAVAO CITY | 1 |  | 1 | [5 empty] | 9527632.08 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 304363 | Davao City Special National High School | DAVAO CITY | 1 |  | 1 | [5 empty] | 836317.44 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 129640 | Don Manuel Gutierrez ES | DAVAO CITY | 1 |  | 1 | [5 empty] | 2710768.98 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 129734 | Imelda Elementary School | DAVAO CITY | 3 |  | 1 | [5 empty] | 4241723.96 | UPGRADING | 4 | ongoing | 95% | 95% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 |  | Y
Region XI | Davao City | 129735 | Los Amigos Elementary School | DAVAO CITY | 3 |  | 1 | [5 empty] | 2517477.99 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 304373 | Los Amigos NHS | DAVAO CITY | 3 |  | 1 | [5 empty] | 2150634.55 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 129645 | Maa CES | DAVAO CITY | 1 |  | 1 | [5 empty] | 4949650.65 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 129538 | Lt. C. Villafuerte, Sr. ES | DAVAO CITY | 3 |  | 1 | [5 empty] | 4173960.12 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 129558 | Magallanes Elementary School | DAVAO CITY | 1 |  | 1 | [5 empty] | 3557366.18 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 129648 | Matina CES | DAVAO CITY | 1 |  | 1 | [5 empty] | 3501218.5 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 304385 | Mintal Comprehensive High School | DAVAO CITY | 3 |  | 1 | [5 empty] | 1903999.24 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 129738 | Mintal ES | DAVAO CITY | 3 |  | 1 | [5 empty] | 1918342.63 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 304393 | Sta. Ana National High School | DAVAO CITY | 1 |  | 1 | [5 empty] | 2746820.78 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 129743 | Tugbok Central ES SPED Center | DAVAO CITY | 3 |  | 1 | [5 empty] | 4267840.04 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 129708 | STA. ANA CENTRAL ELEM. SCHOOL | DAVAO CITY | 1 |  | 1 | [5 empty] | 2927961.31 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Region XI | Davao City | 304387 | Mintal NCHS - Tugbok National HS | DAVAO CITY | 3 |  | 1 | [5 empty] | 2441028.74 | UPGRADING | 4 | completed | 100% | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | Y
Formulas:
Target Completion Date = [Issuance of Notice to Proceed]+120
Target Completion Date = [Issuance of Notice to Proceed]+120+4
Note on S99: USER: lacking transformer for installation of electric coop
Note on Q413: User: error on reporting. Reported failed bidding August 7, 2019. Actual
Note on Q415: User: error on reporting. Reported failed bidding August 7, 2019. Actual
Note on Q416: User: error on reporting. Reported failed bidding August 7, 2019. Actual
Note on Q537: User: NOT PROCURED; for issuance of Negative Sub-ARO
Note on D568: Lenovo: Not included in SARO
Note on D574: Lenovo: Not included in SARO
Note on Q985: User: Terminated
Note on Q986: User: Terminated
Note on Q987: User: Terminated
Note on Q988: User: Terminated
Note on Q989: User: Terminated
Note on Q992: User: Terminated
Note on Q993: User: Terminated
Note on Q996: User: Terminated
Note on Q998: User: Terminated
Note on Q1010: User: Terminated
Note on Q1012: User: Terminated
Note on Q1013: User: Terminated
Note on Q1014: User: Terminated
Note on Q1016: User: Terminated
Note on Q1017: User: Terminated
Note on Q1018: User: Terminated
Note on Q1019: User: Terminated
Note on S1300: USER: lacking transformer for installation of electric coop
Note on D1302: User: Re-ALLIGN TO ANOMAR AND CARAGA RSHS
Note on Q1578: User: Terminated
Note on Q1579: User: Terminated
Note on Q1580: User: Terminated
Note on Q1581: User: Termianted
Note on S1720: USER: lacking transformer for installation of electric coop

## PIVOT_Batch123&4
REPUBLIC OF THE PHILIPPINES
DEPARTMENT OF EDUCATION
CY 2018 BASIC EDUCATIONAL FACILITIES FUND
ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 123&4
As of February 25, 2019
Row Labels | Sum of ALLOCATION | Count of NO. OF SITES | Sum of No. of Sites Completed | Sum of No. of Sites On Going | Sum of No. of Sites Under Procurement | Sum of No. of Sites Not yet started | Sum of No. of Sites Reverted
CAR | 174489129.66 | 116 | 95 | 21 | 0 | 0 | 0
CARAGA | 205401609.0323 | 124 | 73 | 51 | 0 | 0 | 0
NCR | 72740456.8 | 27 | 20 | 3 | 0 | 4 | 0
Region I | 117619981.0162 | 121 | 53 | 68 | 0 | 0 | 0
Region II | 229293028.01 | 187 | 149 | 38 | 0 | 0 | 0
Region III | 120820900.2 | 109 | 109 | 0 | 0 | 0 | 0
Region IV-A | 40643981.3926 | 34 | 25 | 9 | 0 | 0 | 0
Region IV-B | 147003956.21 | 96 | 27 | 69 | 0 | 0 | 0
Region IX | 89597405.46 | 99 | 90 | 0 | 8 | 0 | 1
Region V | 194781958.49 | 99 | 59 | 38 | 2 | 0 | 0
Region VI | 403086124.0019 | 321 | 130 | 125 | 66 | 0 | 0
Region VII | 340966862.5234 | 232 | 159 | 66 | 4 | 0 | 3
Region VIII | 297953703.86 | 162 | 157 | 5 | 0 | 0 | 0
Region X | 173462564.2886 | 59 | 17 | 42 | 0 | 0 | 0
Region XI | 280414488.77 | 130 | 77 | 49 | 4 | 0 | 0
Region XII | 81723848.5413 | 28 | 26 | 2 | 0 | 0 | 0
Grand Total | 2969999998.2562 | 1944 | 1266 | 586 | 84 | 4 | 4